## README
Type 31 Frigate – Whole-Life Cost, Sensitivity and Risk Model
Prepared by Sino Lam · Illustrative model built entirely from publicly available data · All costs in £m, approximate 2023-24 prices unless stated
Purpose
Estimate the whole-life cost (WLC) of the Royal Navy's five Type 31 (Inspiration-class) general-purpose frigates, test which assumptions drive that cost, and quantify the uncertainty around it.
Questions answered
1. How much will the class cost over its life? (Summary, WLC_Model)
2. Is the estimate consistent with comparable programmes? (Benchmarks – US, Canadian, Australian and Danish data)
3. Which assumptions matter most? (Sensitivity – one-way tornado analysis; Assumptions_Log)
4. How confident can we be in the estimate? (Risk_Results – 2,000-iteration Monte Carlo simulation)
Workbook structure
Inputs – every input in one place, with low / base / high values, type (Sourced, Derived, Benchmark, Assumption) and source.
Assumptions_Log – the reasoning, evidence, confidence rating and cost impact of every analyst assumption.
Benchmarks – international comparators used to calibrate and sense-check the estimate.
WLC_Model – annual cost profile 2019-2065 by cost category, ships in service, discounted present value, and reconciliation checks.
Summary – headline results, cost breakdown and charts.
Sensitivity – each uncertain input moved to its low and high value (others held at base); tornado chart ranks the drivers.
MC_Iterations / Risk_Results – 2,000 random draws from triangular distributions; percentiles, histogram and S-curve.
Sources – full references for every sourced figure.
Method
WLC = Acquisition × (1 + growth) + Ships × Service life × (Operating + Maintenance) × (1 + Indirect uplift) + Ships × (Mid-life update + Disposal).
Operating cost: the published Type 23 average direct operating cost (MoD FOI, FY2013-14) is uplifted to 2023-24 prices with the HM Treasury GDP deflator, and its personnel element is scaled by the ratio of Type 31 to Type 23 crew size.
Maintenance: published Type 23 upkeep spend since 2014 is converted to a cost per ship-year and scaled for a newer ship.
Indirect & sustaining support: the UK figures above are direct costs only. They are uplifted using the ratio of sustaining support and other costs to direct costs in the US Navy's FFG-62 frigate estimate, and the result is checked against US, Canadian and Australian evidence on the Benchmarks sheet.
Present value: future costs (from the base year) are discounted at the HM Treasury Green Book real discount rate of 3.5%. Spend before the base year is treated as sunk.
Risk: inputs are sampled from triangular distributions using the inverse-CDF method with RAND(). Press F9 to re-run the simulation; results will move slightly each time.
Colour key
Blue text = hard-coded input (change these) · Black text = formula · Green text = link to another sheet · Yellow fill = key assumption · Orange fill = benchmark-calibrated input
Key limitations
• The £2.2bn acquisition budget is an outturn (cash) figure that includes forecast inflation from 2019; it is treated here as approximately 2023-24 prices. Inflation since 2022 is not in the approved figure (MoD, 2023), which is why an acquisition growth range is modelled.
• The Type 31 through-life support business case has not been published, so running costs are estimated by analogy with the Type 23 and calibrated to overseas programmes, whose cost structures differ from the UK's.
• International benchmarks are compared as ratios (shares and multiples), which avoids currency conversion but assumes cost structures are broadly comparable.
• Several values are analyst assumptions; each is explained and rated on the Assumptions_Log sheet.

## Summary
Type 31 Frigate – Whole-Life Cost Summary
£m, approx. 2023-24 prices · Five ships · Calibrated to international benchmarks (see Benchmarks)
Headline results | £m
Whole-life cost (deterministic, undiscounted) | 6039.9817
Whole-life cost per ship | 1207.9963
Acquisition cost | 2310
Support cost (operate, maintain, support, update, dispose) | 3729.9817
Support share of whole-life cost | 61.75%
Direct-cost-only WLC (before benchmark calibration) | 4765.5443
Present value of future costs (from base year, 3.5%) | 3117.9205
Risk: P50 whole-life cost (Monte Carlo) | 6297.3155
Risk: P80 whole-life cost (Monte Carlo) | 6737.487
Risk: contingency P80 minus deterministic | 697.5053
Risk: probability WLC exceeds deterministic estimate | 72.4%
Cost breakdown | £m | Share
Acquisition | 2310 | 38.25%
Operating (crew, fuel, port) | 1342.514 | 22.23%
Maintenance / upkeep | 713.0303 | 11.81%
Indirect & sustaining support | 1274.4375 | 21.1%
Mid-life updates | 375 | 6.209%
Disposal | 25 | 0.4139%
Total | 6039.9817 | 100%
Key findings
1. The five-ship class is estimated to cost about £6.0bn over its life; the £2.3bn purchase price is only 38% of that.
2. Support is 62% of whole-life cost, in line with US (c.59-70%) and Canadian (72%) frigate evidence. Using UK direct costs alone would understate WLC by about £1.3bn.
3. Allowing for uncertainty, there is an 80% chance the WLC is below £6.7bn – a contingency of about £698m above the point estimate.

## Assumptions_Log
Assumptions log
Every analyst assumption, why it was chosen, the evidence behind it, how confident we are, and how much it moves the answer. Values link live to Inputs; impact links to Sensitivity.
ID | Assumption | Base | Low | High | Why this value | Evidence | Confidence | WLC swing low→high (£m)
L | Each ship stays in service for 25 years, with 20 and 30 years as the range. | 25 | 20 | 30 | 25 years is the standard planning life for modern frigates and the life used in the US FFG-62 estimate. Type 23s show lives can stretch well beyond plan when replacements slip. | FFG-62 SAR (25-year life per ship); Type 23 planned for 18 years, some served 30+ (Naval Technology, 2025). | Medium | 1331.9927
G | Acquisition costs grow 5% above the £2.2bn budget (range 0-20%). | 5% | 0% | 20% | MoD's approved figure excludes inflation since 2022, and the prime contractor has reported cost pressures. A modest base with a fat upside reflects a fixed-price contract that shifts some, but not all, risk to industry. | MoD letter to PAC (May 2023); Babcock £90m loss and dispute over cost increases (Naval Technology 2024; Janes 2023). | Medium | 440
PS | Crew pay is 70% of direct operating cost (range 60-80%). | 70% | 60% | 80% | Used to scale Type 23 running costs to Type 31's smaller crew. US FFG-62 data puts manpower at 75% of manpower-plus-operations. | FFG-62 SAR Dec 2022 (unit-level manpower $16.6m vs unit operations $5.4m per ship-year). | Medium | 269.7516
OPU | Running costs estimated by analogy may be 10% lower to 25% higher than calculated. | 1 | 0.9 | 1.25 | Estimating a new class from an older one is uncertain; history shows support costs are usually underestimated, so the range is skewed upward. | GAO-20-2: Navy underestimated sustainment costs by $130bn across six ship classes. | Low | 761.2054
UKY / UKF | Type 23 upkeep spend covers 11 years and an average fleet of 12 ships. |  |  |  | Turns a published total into a cost per ship-year. Fleet size fell from 13 to 8 over the period, so 12 is a rough average weighted to the earlier years. | Written PQ, 17 Mar 2025 (£941.2m since 2014); Type 23 fleet numbers (Naval Technology, 2025). | Low | –
MF | Type 31 needs 80% of the Type 23's upkeep (range 60-120%). | 0.8 | 0.6 | 1.2 | A new ship on a proven commercial-standard hull should be cheaper to maintain than 30-year-old Type 23s, but costs rise as ships age. | Type 31 based on the Danish Iver Huitfeldt / Arrowhead 140 design; Type 23 upkeep evidence. | Low | 866.3318
IND | Indirect and sustaining support adds 62% on top of direct running costs (range 30-82%). | 0.62 | 0.3 | 0.82 | UK published figures cover only direct costs. The US FFG-62 estimate breaks down full support costs, giving the ratio of indirect to direct support. Without this, support would be far below international norms. | FFG-62 SAR Dec 2022; cross-checked against GAO (c.70%) and Canadian PBO (72%) support shares. | Medium | 1068.883
MLU | Each ship has a £75m mid-life update in its 13th year (range £50-150m). | 75 | 50 | 150 | Frigates typically receive a major refit and capability update halfway through life. Type 23 refits have cost over £100m, but Type 31 is simpler and designed for upgrades. | HMS Iron Duke refit >£100m (Naval Technology, 2025); FFG-62 continuous system improvements c.11% of annual O&S. | Low | 500
D | Disposal costs £5m per ship (range £2-15m). | 5 | 2 | 15 | Disposal is a small share of whole-life cost in every comparator, so precision matters little. | FFG-62 SAR (c.$9m per ship); Canadian PBO (0.6% of life-cycle cost). | Medium | 65
ISD1 / INT | First ship in service 2027, then one per year. |  |  |  | Matches published in-service plans for HMS Venturer and the class. Timing affects present value but not undiscounted WLC. | Naval Technology (2024): five ships into service from 2027; Royal Navy (2025). | Medium | –
Profile | Acquisition spend profile 2019-2031 (WLC_Model row 5). |  |  |  | Spreads the £2.2bn from contract award to final delivery, peaking during main build. Affects timing and present value only. | Contract award Nov 2019; Babcock had recognised over £600m revenue by April 2023. | Low | –
Price base | The £2.2bn budget is treated as approximately 2023-24 prices. |  |  |  | The MoD figure mixes years and includes 2019 inflation forecasts. No published breakdown allows exact rebasing, so the acquisition growth range absorbs this. | MoD letter to PAC (May 2023). | Low | –
BY / R | Present values use 2026 as base year and a 3.5% real discount rate. |  |  |  | Green Book standard for public sector appraisal; costs before 2026 are sunk and excluded from present value. | HM Treasury Green Book. | High | –

## Benchmarks
International benchmarks
Comparators are expressed as ratios (shares, multiples) so no currency conversion is needed. Blue = published figure, black = calculation.
A. Support (operating & support) share of whole-life cost
Programme | Acquisition | Operating & support | Other (dev't, disposal) | Total | Support share | Source and notes
US Navy ships – GAO rule of thumb |  |  |  |  | 70% | GAO-20-2 (2019): about 70% of a ship's life-cycle cost is operations and maintenance.
Canada – Canadian Surface Combatant (15 ships), C$bn | 80.2 | 219.8 | 6 | 306 | 71.83% | Parliamentary Budget Officer, Life Cycle Cost of the Canadian Surface Combatants, Oct 2022. Development C$4.3bn, disposal C$1.7bn.
US Navy – FFG-62 Constellation frigate (20 ships), US$m CY2020 | 20342.5 | 29000 |  | 49342.5 | 58.77% | Selected Acquisition Report, Dec 2022. O&S = $57.9m per ship-year × 20 ships × 25 years (disposal included in O&S).
Type 31 – this model, direct costs only | 2310 | 2455.5443 |  | 4765.5443 | 51.53% | UK direct costs: crew, fuel, port visits, upkeep periods, mid-life update and disposal.
Type 31 – this model, calibrated (used for results) | 2310 | 3729.9817 |  | 6039.9817 | 61.75% | Adds indirect and sustaining support calibrated to FFG-62 (section B).
B. US Navy FFG-62 annual operating & support cost per ship, by element (US$m, CY2020)
Cost element | US$m per ship-year | Share | Equivalent in UK model
Unit-level manpower | 16.6 | 28.62% | Direct: operating cost (crew)
Unit operations (fuel, consumables) | 5.4 | 9.31% | Direct: operating cost (non-crew)
Maintenance | 9.8 | 16.9% | Direct: maintenance / upkeep
Sustaining support | 10.7 | 18.45% | Indirect & sustaining support
Continued system improvements | 6.5 | 11.21% | Mid-life update (partly)
Other (indirect support) | 9 | 15.52% | Indirect & sustaining support
Total O&S per ship-year | 58
Calibrated uplift: (sustaining support + other) ÷ (manpower + operations + maintenance) |  | 0.62 | → feeds Inputs: Indirect & sustaining support uplift (base case)
FFG-62 manpower share of direct operating cost (manpower ÷ (manpower + operations)) |  | 75.45% | → supports Inputs: personnel share of direct operating cost (70%)
FFG-62 annual O&S as % of unit acquisition cost |  | 5.702%
Type 31 (calibrated) annual running cost as % of unit acquisition cost |  | 5.766% | Very close to FFG-62 – an independent cross-check that calibrated running costs are proportionate to the ship's value
Source: FFG(62) Selected Acquisition Report, December 2022 (Component Independent Cost Estimate, April 2020).
C. Other comparators (context only, not used in calculations)
Comparator | Value | Unit | Per ship |  | Confidence | Source and notes
Australia – ANZAC class frigate sustainment, 2018-19 budget (8 ships) | 374 | A$m/yr | 46.75 |  | Medium | ANAO, Anzac Class Frigates – Sustainment (2019). Materiel sustainment only; shows support of an in-service frigate class running at tens of millions per ship per year.
Denmark – Iver Huitfeldt class (parent design of Type 31), build cost | 325 | US$m/ship |  |  | Low | Wikipedia infobox (uncited). Supports Type 31's low build cost (c.£250m production cost per ship) from reusing a proven hull.
Denmark – Iver Huitfeldt class crew | 165 | people |  |  | Low | Wikipedia infobox (uncited). Type 31 is planned to run with a much smaller crew (105-115).
UK – Type 23 crew (HMS St Albans) | 185 | people |  |  | High | Royal Navy ship page: crew of 185, accommodation for up to 205.
UK – Type 31 average production cost per ship | 250 | £m/ship |  |  | High | Babcock contract, Nov 2019 (Naval Technology, 2024). Excludes MoD-side costs within the £2.2bn.
What the benchmarks changed
Using UK direct costs alone, support would be 52% of whole-life cost – well below the 59-72% seen in US and Canadian frigate programmes. Adding indirect and sustaining support calibrated to FFG-62 raises it to 62%, within the benchmark range.

## Inputs
Inputs and assumptions
All costs £m, approx. 2023-24 prices. Low and High feed the Sensitivity sheet; Low / Base / High are the min / most likely / max for the Monte Carlo. Reasoning for each assumption is on Assumptions_Log.
ID | Parameter | Unit | Low | Base | High | Type | Source / notes
N | Number of ships | ships |  | 5 |  | Sourced | Five Inspiration-class ships on contract with Babcock (MoD letter to PAC, 25 May 2023).
ISD1 | First ship in service (financial year) | year |  | 2027 |  | Assumption | HMS Venturer planned to enter service c.2027; five ships in service from 2027 with final handover around 2028-2030 (Naval Technology, 2024). See Assumptions_Log.
INT | Interval between ship in-service dates | years |  | 1 |  | Assumption | Simplifying assumption: one ship per year.
L | Service life per ship | years | 20 | 25 | 30 | Assumption | 25 years matches the planning life in the US Navy FFG-62 estimate and early Type 26 planning. Type 23s were planned for 18 years but extended past 30.
ACQ | Approved acquisition budget (5 ships) | £m |  | 2200 |  | Sourced | Uplifted from £2.0bn to £2.2bn in 2022. Covers Babcock contract, c.£100m GFX, trials, spares, integration facility (MoD letter to PAC, 25 May 2023).
G | Acquisition cost growth above approved budget | % | 0% | 5% | 20% | Assumption | MoD states recent inflation is not reflected in the £2.2bn; Babcock booked a £90m loss citing design changes and labour costs (Naval Technology, July 2024).
OP23 | Type 23 average direct operating cost per ship (FY13-14) | £m/yr |  | 11.735 |  | Sourced | MoD FOI 2015/06440, Annex A. Includes personnel, fuel, port visits, travel. Excludes maintenance, base support, overheads, aircraft, training.
DEF14 | GDP deflator 2013-14 (2023-24 = 100) | index |  | 76.189 |  | Sourced | HM Treasury GDP deflators at market prices, June 2024 release.
DEF24 | GDP deflator 2023-24 | index |  | 100 |  | Sourced | HM Treasury GDP deflators, June 2024 release (base year).
UPL | Price uplift 2013-14 to 2023-24 | factor |  | 1.3125 |  | Derived | Deflator 2023-24 ÷ deflator 2013-14.
PS | Personnel share of direct operating cost | % | 60% | 70% | 80% | Benchmark | US Navy FFG-62: unit-level manpower is 75% of manpower + unit operations ($16.6m of $22.0m per ship-year, SAR Dec 2022). 70% used, as UK fuel and port costs are proportionally higher.
C23 | Type 23 crew complement | people |  | 185 |  | Sourced | Royal Navy, HMS St Albans ship page: 'sailed by a crew of 185, but with accommodation for up to 205'. Crew varies between ships and over time; 185 used for the class.
C31 | Type 31 crew complement | people | 100 | 105 | 115 | Sourced | Crew of up to 105 (GOV.UK, 2021); Royal Navy now cites around 115 for HMS Venturer.
OPU | Operating cost estimating uncertainty factor | factor | 0.9 | 1 | 1.25 | Assumption | Captures the uncertainty of estimating by analogy with an older class. Skewed upward because new-ship running costs are usually underestimated (GAO-20-2).
OP31 | Type 31 direct operating cost per ship-year | £m/yr |  | 10.7401 |  | Derived | T23 cost × price uplift × (personnel share × crew ratio + non-personnel share) × uncertainty factor.
UK23 | Type 23 upkeep spend on completed upkeeps since 2014 | £m |  | 941.2 |  | Sourced | Written parliamentary answer, 17 March 2025 (reported by Naval Technology). Cash prices.
UKY | Years covered by upkeep spend | years |  | 11 |  | Assumption | 2014 to 2024 inclusive.
UKF | Average Type 23 fleet size over the period | ships |  | 12 |  | Assumption | Fleet fell from 13 to 8 over the period; 12 used as a rough average.
M23 | Type 23 upkeep cost per ship-year | £m/yr |  | 7.1303 |  | Derived | Upkeep spend ÷ (years × fleet size).
MF | Type 31 maintenance scaling factor vs Type 23 | factor | 0.6 | 0.8 | 1.2 | Assumption | A newer ship based on a proven Danish design should need less maintenance than an ageing Type 23; the high case allows for ageing later in life.
M31 | Type 31 maintenance cost per ship-year | £m/yr |  | 5.7042 |  | Derived | Type 23 upkeep per ship-year × scaling factor.
IND | Indirect & sustaining support uplift on direct running costs | factor | 0.3 | 0.62 | 0.82 | Benchmark | Base calibrated to US Navy FFG-62 (SAR Dec 2022): (sustaining support + other) ÷ (manpower + unit operations + maintenance) = 0.62. High (0.82) adds continuous system improvements; low (0.30) assumes leaner UK overheads. Covers base support, training, spares and in-service support missing from the UK direct-cost figures.
MLU | Mid-life update cost per ship | £m | 50 | 75 | 150 | Assumption | Scaled from Type 23 experience: HMS Iron Duke's 2023 refit cost over £100m (Naval Technology, 2025).
MLUY | Mid-life update in year of service | year no. |  | 13 |  | Assumption | Roughly halfway through a 25-year life.
D | Disposal cost per ship | £m | 2 | 5 | 15 | Benchmark | US FFG-62 disposal is c.$9m per ship (SAR Dec 2022, $179.6m for 20 ships); Canadian CSC disposal is 0.6% of life-cycle cost (PBO 2022). £5m base.
R | Real discount rate | % |  | 3.5% |  | Sourced | HM Treasury Green Book social time preference rate (years 0-30).
BY | Present value base year | year |  | 2026 |  | Assumption | Current year; spend before this is treated as sunk.

## Sensitivity
One-way sensitivity analysis (tornado)
Each input is moved to its Low and High value from the Inputs sheet while all others stay at Base. Output: undiscounted whole-life cost (£m).
Base whole-life cost (£m): |  |  | 6039.9817
Input varied | Low value | High value | WLC at low (£m) | WLC at high (£m) | Change at low (£m) | Change at high (£m) | Swing (£m) | Swing as % of base
Disposal cost per ship | 2 | 15 | 6024.9817 | 6089.9817 | -15 | 50 | 65 | 1.076%
Type 31 crew complement | 100 | 115 | 5980.9736 | 6157.9981 | -59.0082 | 118.0163 | 177.0245 | 2.931%
Personnel share of direct operating cost | 60% | 80% | 6174.8576 | 5905.1059 | 134.8758 | -134.8758 | 269.7516 | 4.466%
Acquisition cost growth above approved budget | 0% | 20% | 5929.9817 | 6369.9817 | -110 | 330 | 440 | 7.285%
Mid-life update cost per ship | 50 | 150 | 5914.9817 | 6414.9817 | -125 | 375 | 500 | 8.278%
Operating cost estimating uncertainty factor | 0.9 | 1.25 | 5822.4945 | 6583.6999 | -217.4873 | 543.7182 | 761.2054 | 12.6%
Type 31 maintenance scaling factor vs Type 23 | 0.6 | 1.2 | 5751.2045 | 6617.5363 | -288.7773 | 577.5545 | 866.3318 | 14.34%
Indirect & sustaining support uplift on direct running costs | 0.3 | 0.82 | 5382.2076 | 6451.0906 | -657.7742 | 411.1089 | 1068.883 | 17.7%
Service life per ship | 20 | 30 | 5373.9854 | 6705.9781 | -665.9963 | 665.9963 | 1331.9927 | 22.05%
Rows are ordered by swing, smallest first, so the largest driver appears at the top of the tornado chart. If you change Low/High values substantially, re-order rows by column H.

## Risk_Results
Risk analysis – Monte Carlo results
2,000 iterations · Undiscounted whole-life cost, £m approx. 2023-24 prices · Results change slightly each recalculation (F9).
| Statistic | £m
| Deterministic (base case) estimate | 6039.9817
| Mean | 6331.7941
| P10 (10% chance of being lower) | 5735.0201
| P50 (median) | 6297.3155
| P80 (common budgeting confidence level) | 6737.487
| P90 | 6983.7825
| Minimum simulated | 5002.7657
| Maximum simulated | 8153.072
| Standard deviation | 474.3689
| Probability WLC exceeds deterministic estimate | 72.4%
| Contingency needed for P80 confidence (P80 − deterministic) | 697.5053
| Contingency as % of deterministic estimate | 11.55%
| Histogram and S-curve |  |  |  | Bin width (£m): | 126.0123
| Bin upper bound (£m) | Count | Frequency | Cumulative %
| 5128.7779 | 2 | 0.1% | 0.1%
| 5254.7902 | 9 | 0.45% | 0.55%
| 5380.8024 | 14 | 0.7% | 1.25%
| 5506.8147 | 33 | 1.65% | 2.9%
| 5632.8269 | 63 | 3.15% | 6.05%
| 5758.8392 | 101 | 5.05% | 11.1%
| 5884.8514 | 129 | 6.45% | 17.55%
| 6010.8637 | 166 | 8.3% | 25.85%
| 6136.8759 | 190 | 9.5% | 35.35%
| 6262.8882 | 240 | 12% | 47.35%
| 6388.9004 | 201 | 10.05% | 57.4%
| 6514.9127 | 191 | 9.55% | 66.95%
| 6640.9249 | 177 | 8.85% | 75.8%
| 6766.9372 | 109 | 5.45% | 81.25%
| 6892.9494 | 107 | 5.35% | 86.6%
| 7018.9617 | 89 | 4.45% | 91.05%
| 7144.9739 | 69 | 3.45% | 94.5%
| 7270.9862 | 57 | 2.85% | 97.35%
| 7396.9984 | 23 | 1.15% | 98.5%
| 7523.0107 | 16 | 0.8% | 99.3%
| 7649.023 | 3 | 0.15% | 99.45%
| 7775.0352 | 4 | 0.2% | 99.65%
| 7901.0475 | 5 | 0.25% | 99.9%
| 8027.0597 | 1 | 0.05% | 99.95%
| 8153.072 | 1 | 0.05% | 100%

## WLC_Model
Whole-life cost model – annual profile (£m, approx. 2023-24 prices)
Every cell is a formula driven by the Inputs sheet, except the acquisition spend profile (blue), which is an analyst assumption.
Line | ISD | Total | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | 2058 | 2059 | 2060 | 2061 | 2062 | 2063 | 2064 | 2065
Acquisition spend profile (% of total) |  | 100% | 2% | 4% | 8% | 10% | 12% | 13% | 13% | 12% | 9% | 7% | 5% | 3% | 2% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Ships in service
Ship 1 in service (1 = yes) | 2027 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ship 2 in service (1 = yes) | 2028 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ship 3 in service (1 = yes) | 2029 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ship 4 in service (1 = yes) | 2030 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ship 5 in service (1 = yes) | 2031 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total ships in service |  | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Costs (£m)
Acquisition |  | 2310 | 46.2 | 92.4 | 184.8 | 231 | 277.2 | 300.3 | 300.3 | 277.2 | 207.9 | 161.7 | 115.5 | 69.3 | 46.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Operating (crew, fuel, port) |  | 1342.514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.7401 | 21.4802 | 32.2203 | 42.9604 | 53.7006 | 53.7006 | 53.7006 | 53.7006 | 53.7006 | 53.7006 | 53.7006 | 53.7006 | 53.7006 | 53.7006 | 53.7006 | 53.7006 | 53.7006 | 53.7006 | 53.7006 | 53.7006 | 53.7006 | 53.7006 | 53.7006 | 53.7006 | 53.7006 | 42.9604 | 32.2203 | 21.4802 | 10.7401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maintenance / upkeep |  | 713.0303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.7042 | 11.4085 | 17.1127 | 22.817 | 28.5212 | 28.5212 | 28.5212 | 28.5212 | 28.5212 | 28.5212 | 28.5212 | 28.5212 | 28.5212 | 28.5212 | 28.5212 | 28.5212 | 28.5212 | 28.5212 | 28.5212 | 28.5212 | 28.5212 | 28.5212 | 28.5212 | 28.5212 | 28.5212 | 22.817 | 17.1127 | 11.4085 | 5.7042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Indirect & sustaining support |  | 1274.4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.1955 | 20.391 | 30.5865 | 40.782 | 50.9775 | 50.9775 | 50.9775 | 50.9775 | 50.9775 | 50.9775 | 50.9775 | 50.9775 | 50.9775 | 50.9775 | 50.9775 | 50.9775 | 50.9775 | 50.9775 | 50.9775 | 50.9775 | 50.9775 | 50.9775 | 50.9775 | 50.9775 | 50.9775 | 40.782 | 30.5865 | 20.391 | 10.1955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mid-life updates |  | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 75 | 75 | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Disposal |  | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total cost |  | 6039.9817 | 46.2 | 92.4 | 184.8 | 231 | 277.2 | 300.3 | 300.3 | 277.2 | 234.5399 | 214.9797 | 195.4196 | 175.8594 | 179.3993 | 133.1993 | 133.1993 | 133.1993 | 133.1993 | 133.1993 | 133.1993 | 133.1993 | 208.1993 | 208.1993 | 208.1993 | 208.1993 | 208.1993 | 133.1993 | 133.1993 | 133.1993 | 133.1993 | 133.1993 | 133.1993 | 133.1993 | 133.1993 | 111.5594 | 84.9196 | 58.2797 | 31.6399 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative cost |  |  | 46.2 | 138.6 | 323.4 | 554.4 | 831.6 | 1131.9 | 1432.2 | 1709.4 | 1943.9399 | 2158.9196 | 2354.3391 | 2530.1985 | 2709.5978 | 2842.7971 | 2975.9963 | 3109.1956 | 3242.3949 | 3375.5942 | 3508.7934 | 3641.9927 | 3850.192 | 4058.3912 | 4266.5905 | 4474.7898 | 4682.989 | 4816.1883 | 4949.3876 | 5082.5868 | 5215.7861 | 5348.9854 | 5482.1847 | 5615.3839 | 5748.5832 | 5860.1426 | 5945.0622 | 6003.3419 | 6034.9817 | 6039.9817 | 6039.9817 | 6039.9817 | 6039.9817 | 6039.9817 | 6039.9817 | 6039.9817 | 6039.9817 | 6039.9817 | 6039.9817
Discount factor (future years only) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.96618 | 0.93351 | 0.90194 | 0.87144 | 0.84197 | 0.8135 | 0.78599 | 0.75941 | 0.73373 | 0.70892 | 0.68495 | 0.66178 | 0.6394 | 0.61778 | 0.59689 | 0.57671 | 0.5572 | 0.53836 | 0.52016 | 0.50257 | 0.48557 | 0.46915 | 0.45329 | 0.43796 | 0.42315 | 0.40884 | 0.39501 | 0.38165 | 0.36875 | 0.35628 | 0.34423 | 0.33259 | 0.32134 | 0.31048 | 0.29998 | 0.28983 | 0.28003 | 0.27056 | 0.26141
Present value of future cost |  | 3117.9205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 277.2 | 226.6086 | 200.6859 | 176.2572 | 153.2513 | 151.0494 | 108.3577 | 104.6934 | 101.1531 | 97.7324 | 94.4275 | 91.2343 | 88.1491 | 133.1235 | 128.6217 | 124.2722 | 120.0697 | 116.0094 | 71.7093 | 69.2844 | 66.9414 | 64.6777 | 62.4905 | 60.3773 | 58.3356 | 56.3629 | 45.6097 | 33.5443 | 22.2427 | 11.6671 | 1.7814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Check: closed-form WLC |  | 6039.9817
Check: difference vs annual profile (should be 0) |  | 0
Check: acquisition profile sums to 100% |  | OK
Note on C5: Must equal 100%. Analyst assumption: contract award 2019, peak build spend 2023-2026, deliveries to c.2031. Consistent with Babcock recognising over £600m revenue by April 2023.

## MC_Iterations
Monte Carlo iterations (triangular distributions, inverse-CDF sampling)
Each row is one simulated future. U = uniform random number RAND(); value = triangular inverse CDF using Low (min), Base (most likely) and High (max) from Inputs. Press F9 to re-sample.
Iteration | U L | Service life per ship | U G | Acquisition cost growth above approved budget | U PS | Personnel share of direct operating cost | U C31 | Type 31 crew complement | U OPU | Operating cost estimating uncertainty factor | U MF | Type 31 maintenance scaling factor vs Type 23 | U IND | Indirect & sustaining support uplift on direct running costs | U MLU | Mid-life update cost per ship | U D | Disposal cost per ship | Whole-life cost (£m)
1 | 0.22976 | 23 | 0.1161 | 0.034074 | 0.70344 | 0.72299 | 0.45572 | 106 | 0.18257 | 0.97994 | 0.61413 | 0.89568 | 0.28957 | 0.51951 | 0.49105 | 88.2168 | 0.56329 | 7.4653 | 5692.5777
2 | 0.57818 | 25 | 0.41151 | 0.067129 | 0.52368 | 0.7024 | 0.67792 | 108 | 0.11855 | 0.96442 | 0.60641 | 0.89265 | 0.33661 | 0.53667 | 0.66975 | 100.2318 | 0.96138 | 12.7594 | 6154.3572
3 | 0.77289 | 27 | 0.29295 | 0.054358 | 0.91858 | 0.75965 | 0.27059 | 105 | 0.29054 | 1.0008 | 0.97731 | 1.1262 | 0.44651 | 0.57258 | 0.15559 | 69.7226 | 0.41168 | 6.2546 | 6601.8995
4 | 0.20494 | 23 | 0.87257 | 0.13817 | 0.34413 | 0.68296 | 0.37227 | 105 | 0.15824 | 0.97442 | 0.91417 | 1.0565 | 0.72704 | 0.65151 | 0.14015 | 68.7186 | 0.69128 | 8.6649 | 6330.2149
5 | 0.88664 | 28 | 0.93857 | 0.15707 | 0.37419 | 0.68651 | 0.66515 | 108 | 0.45441 | 1.0315 | 0.1697 | 0.7427 | 0.87052 | 0.70396 | 0.66481 | 99.8611 | 0.40289 | 6.1895 | 7046.2522
6 | 0.86979 | 27 | 0.43348 | 0.069633 | 0.86662 | 0.74835 | 0.50848 | 106 | 0.67425 | 1.0812 | 0.68456 | 0.92485 | 0.64572 | 0.62805 | 0.9805 | 137.9059 | 0.92891 | 11.96 | 7042.3261
7 | 0.54737 | 25 | 0.34166 | 0.059465 | 0.3771 | 0.68685 | 0.45153 | 106 | 0.1235 | 0.96574 | 0.65674 | 0.91297 | 0.40744 | 0.56038 | 0.7818 | 109.5466 | 0.15461 | 4.4556 | 6220.9006
8 | 0.64635 | 26 | 0.21092 | 0.045926 | 0.39701 | 0.68911 | 0.76534 | 109 | 0.92098 | 1.1668 | 0.091609 | 0.70485 | 0.31653 | 0.5295 | 0.60041 | 95.2556 | 0.27067 | 5.2628 | 6364.8207
9 | 0.78885 | 27 | 0.66844 | 0.10027 | 0.9673 | 0.77443 | 0.049743 | 102 | 0.00053192 | 0.90431 | 0.58815 | 0.88561 | 0.21391 | 0.48867 | 0.21494 | 73.181 | 0.63962 | 8.1554 | 5922.9855
10 | 0.78777 | 27 | 0.83617 | 0.12989 | 0.7513 | 0.72947 | 0.7477 | 109 | 0.95412 | 1.1866 | 0.51197 | 0.85776 | 0.54626 | 0.60149 | 0.58925 | 94.4966 | 0.58494 | 7.6544 | 7086.1948
11 | 0.22994 | 23 | 0.21035 | 0.045864 | 0.88556 | 0.75216 | 0.085169 | 103 | 0.72677 | 1.0954 | 0.86266 | 1.0184 | 0.39823 | 0.55742 | 0.46693 | 86.7701 | 0.43643 | 6.4405 | 6081.9068
12 | 0.1746 | 23 | 0.020388 | 0.014279 | 0.059158 | 0.6344 | 0.55053 | 107 | 0.61111 | 1.0655 | 0.21548 | 0.7608 | 0.017305 | 0.35366 | 0.52541 | 90.3389 | 0.04606 | 3.3403 | 5415.7785
13 | 0.92651 | 28 | 0.57708 | 0.08736 | 0.52568 | 0.7026 | 0.63823 | 108 | 0.62011 | 1.0677 | 0.67055 | 0.91881 | 0.67014 | 0.63478 | 0.8815 | 120.1882 | 0.091214 | 3.8861 | 7175.0715
14 | 0.79715 | 27 | 0.30135 | 0.055226 | 0.90542 | 0.75651 | 0.54582 | 107 | 0.62998 | 1.0701 | 0.64207 | 0.90691 | 0.55561 | 0.60406 | 0.76719 | 108.2137 | 0.80467 | 9.9608 | 6743.3724
15 | 0.32646 | 24 | 0.086237 | 0.029366 | 0.74013 | 0.72791 | 0.51862 | 107 | 0.038548 | 0.93673 | 0.154 | 0.73594 | 0.93619 | 0.73854 | 0.74119 | 105.9421 | 0.032823 | 3.1314 | 5990.9742
16 | 0.85335 | 27 | 0.80756 | 0.12402 | 0.1011 | 0.64497 | 0.71718 | 108 | 0.48059 | 1.0368 | 0.65548 | 0.91245 | 0.6722 | 0.63536 | 0.69073 | 101.8383 | 0.37752 | 6.0043 | 7027.6233
17 | 0.022753 | 21 | 0.65445 | 0.098184 | 0.89309 | 0.75376 | 0.49096 | 106 | 0.14219 | 0.97055 | 0.052446 | 0.67933 | 0.53861 | 0.59937 | 0.80285 | 111.5473 | 0.92634 | 11.9055 | 5549.0895
18 | 0.060385 | 22 | 0.27947 | 0.052976 | 0.97425 | 0.77731 | 0.56235 | 107 | 0.76253 | 1.1059 | 0.46059 | 0.8402 | 0.88586 | 0.71105 | 0.27133 | 76.0741 | 0.70885 | 8.8478 | 6023.9227
19 | 0.30017 | 24 | 0.3647 | 0.061946 | 0.36538 | 0.68548 | 0.53868 | 107 | 0.10362 | 0.96022 | 0.33137 | 0.79941 | 0.25712 | 0.50684 | 0.33467 | 79.3601 | 0.077261 | 3.7358 | 5683.8447
20 | 0.66579 | 26 | 0.13325 | 0.036504 | 0.7723 | 0.73252 | 0.97542 | 113 | 0.8918 | 1.1527 | 0.96411 | 1.1072 | 0.9967 | 0.80147 | 0.26864 | 75.938 | 0.35839 | 5.8672 | 7510.7372
21 | 0.56512 | 25 | 0.1687 | 0.041073 | 0.41318 | 0.6909 | 0.71741 | 108 | 0.78113 | 1.1116 | 0.79668 | 0.9791 | 0.96762 | 0.76197 | 0.12804 | 67.8911 | 0.51321 | 7.045 | 6889.198
22 | 0.17774 | 23 | 0.1726 | 0.041546 | 0.74247 | 0.72823 | 0.2702 | 105 | 0.85735 | 1.1383 | 0.028171 | 0.65814 | 0.45709 | 0.57579 | 0.26759 | 75.8846 | 0.21206 | 4.8758 | 5722.2189
23 | 0.47164 | 25 | 0.32171 | 0.057351 | 0.78706 | 0.73474 | 0.22841 | 104 | 0.00099553 | 0.9059 | 0.58273 | 0.88354 | 0.66026 | 0.63203 | 0.81546 | 112.7976 | 0.3281 | 5.654 | 6134.4261
24 | 0.81172 | 27 | 0.56052 | 0.085176 | 0.81498 | 0.73917 | 0.65373 | 108 | 0.88559 | 1.1499 | 0.33077 | 0.79923 | 0.13617 | 0.45053 | 0.27735 | 76.3804 | 0.20933 | 4.8573 | 6310.845
25 | 0.20182 | 23 | 0.31849 | 0.057013 | 0.89185 | 0.75349 | 0.58178 | 107 | 0.28638 | 1.0001 | 0.32232 | 0.79667 | 0.72929 | 0.65221 | 0.23172 | 74.0688 | 0.19524 | 4.7594 | 5795.9255
26 | 0.59861 | 26 | 0.081905 | 0.028619 | 0.23418 | 0.66844 | 0.51101 | 106 | 0.14582 | 0.97144 | 0.60567 | 0.89237 | 0.19 | 0.47781 | 0.94664 | 129.9945 | 0.45806 | 6.6064 | 6222.3954
27 | 0.38546 | 24 | 0.88152 | 0.14038 | 0.80659 | 0.73781 | 0.02202 | 101 | 0.77232 | 1.1089 | 0.30694 | 0.79192 | 0.46287 | 0.57753 | 0.43449 | 84.8743 | 0.4698 | 6.6979 | 6185.6444
28 | 0.38023 | 24 | 0.26738 | 0.051748 | 0.097315 | 0.64412 | 0.8997 | 111 | 0.25154 | 0.99383 | 0.85594 | 1.0141 | 0.18349 | 0.47473 | 0.90919 | 123.9021 | 0.45442 | 6.5783 | 6256.8097
29 | 0.5755 | 25 | 0.19526 | 0.044188 | 0.68225 | 0.72028 | 0.23949 | 104 | 0.72496 | 1.0949 | 0.89155 | 1.0387 | 0.89444 | 0.71522 | 0.55341 | 92.1256 | 0.52938 | 7.1782 | 6856.978
30 | 0.92413 | 28 | 0.58679 | 0.088661 | 0.45903 | 0.69582 | 0.57039 | 107 | 0.60188 | 1.0634 | 0.8151 | 0.98934 | 0.23808 | 0.49904 | 0.62055 | 96.6535 | 0.69903 | 8.7449 | 6831.368
31 | 0.32608 | 24 | 0.46584 | 0.073411 | 0.065772 | 0.63627 | 0.056704 | 102 | 0.14926 | 0.97228 | 0.13154 | 0.72564 | 0.12049 | 0.4416 | 0.16092 | 70.0573 | 0.62732 | 8.0396 | 5498.1574
32 | 0.46733 | 25 | 0.4197 | 0.068057 | 0.42162 | 0.69183 | 0.11488 | 103 | 0.45094 | 1.0308 | 0.38828 | 0.81684 | 0.014257 | 0.34871 | 0.3726 | 81.4035 | 0.3233 | 5.6207 | 5622.6468
33 | 0.14572 | 23 | 0.37429 | 0.062991 | 0.81224 | 0.73872 | 0.54359 | 107 | 0.24016 | 0.99168 | 0.91985 | 1.0613 | 0.21576 | 0.48948 | 0.59437 | 94.8437 | 0.40869 | 6.2325 | 5941.6468
34 | 0.03056 | 21 | 0.45564 | 0.072208 | 0.24976 | 0.67068 | 0.62265 | 107 | 0.062628 | 0.94682 | 0.31817 | 0.7954 | 0.20897 | 0.48648 | 0.65783 | 99.3415 | 0.16031 | 4.5004 | 5395.7981
35 | 0.6221 | 26 | 0.37329 | 0.062882 | 0.03046 | 0.62468 | 0.28943 | 105 | 0.91455 | 1.1635 | 0.28005 | 0.78332 | 0.44751 | 0.57288 | 0.76516 | 108.0325 | 0.30884 | 5.521 | 6722.7255
36 | 0.15638 | 23 | 0.19987 | 0.044707 | 0.64725 | 0.71601 | 0.23293 | 104 | 0.01062 | 0.91928 | 0.3447 | 0.80343 | 0.071541 | 0.40911 | 0.85578 | 117.1114 | 0.040312 | 3.2539 | 5403.656
37 | 0.44142 | 25 | 0.83758 | 0.1302 | 0.84696 | 0.74468 | 0.76007 | 109 | 0.016753 | 0.92421 | 0.66527 | 0.91657 | 0.36728 | 0.54721 | 0.043309 | 60.4054 | 0.14154 | 4.3494 | 5985.0441
38 | 0.54992 | 25 | 0.96025 | 0.16547 | 0.76881 | 0.732 | 0.044265 | 102 | 0.95835 | 1.1896 | 0.025234 | 0.65503 | 0.44537 | 0.57223 | 0.49599 | 88.5178 | 0.60098 | 7.7978 | 6381.9304
39 | 0.70983 | 26 | 0.61952 | 0.093161 | 0.50365 | 0.70037 | 0.080969 | 102 | 0.085898 | 0.95483 | 0.91088 | 1.0537 | 0.6272 | 0.6231 | 0.44865 | 85.6948 | 0.27301 | 5.2784 | 6573.2915
40 | 0.39615 | 24 | 0.1084 | 0.032923 | 0.73636 | 0.72739 | 0.27148 | 105 | 0.31333 | 1.0049 | 0.16319 | 0.73994 | 0.34993 | 0.5413 | 0.29618 | 77.3455 | 0.042934 | 3.294 | 5613.7054
41 | 0.66264 | 26 | 0.92121 | 0.15138 | 0.2723 | 0.6738 | 0.83321 | 110 | 0.53731 | 1.0488 | 0.40297 | 0.82147 | 0.56487 | 0.60659 | 0.25853 | 75.4277 | 0.34811 | 5.7943 | 6614.7361
42 | 0.99679 | 30 | 0.91982 | 0.15096 | 0.17498 | 0.65916 | 0.56665 | 107 | 0.89726 | 1.1552 | 0.20947 | 0.75854 | 0.42352 | 0.56547 | 0.11221 | 66.7485 | 0.98677 | 13.6886 | 7221.2846
43 | 0.46386 | 25 | 0.51419 | 0.079275 | 0.41928 | 0.69157 | 0.16879 | 104 | 0.20218 | 0.98412 | 0.28266 | 0.78417 | 0.44178 | 0.57113 | 0.26931 | 75.9716 | 0.1267 | 4.2229 | 5948.971
44 | 0.22253 | 23 | 0.0052369 | 0.0072367 | 0.62056 | 0.71289 | 0.92012 | 112 | 0.74332 | 1.1001 | 0.099799 | 0.70943 | 0.68861 | 0.64004 | 0.98792 | 140.4798 | 0.81613 | 10.111 | 6219.7991
45 | 0.23407 | 23 | 0.33656 | 0.058921 | 0.21783 | 0.666 | 0.99108 | 114 | 0.045963 | 0.94011 | 0.371 | 0.81146 | 0.018968 | 0.35618 | 0.69021 | 101.7983 | 0.47509 | 6.7394 | 5455.7846
46 | 0.23413 | 23 | 0.16883 | 0.041089 | 0.32019 | 0.68002 | 0.93375 | 112 | 0.19734 | 0.98311 | 0.83453 | 1.0007 | 0.63174 | 0.6243 | 0.94233 | 129.203 | 0.27641 | 5.3012 | 6365.2949
47 | 0.31887 | 24 | 0.75573 | 0.1144 | 0.20563 | 0.66413 | 0.96599 | 113 | 0.45261 | 1.0311 | 0.54815 | 0.87069 | 0.28219 | 0.51669 | 0.38868 | 82.2883 | 0.95554 | 12.5959 | 6199.4948
48 | 0.52824 | 25 | 0.90145 | 0.14563 | 0.0088148 | 0.61328 | 0.071574 | 102 | 0.077737 | 0.95216 | 0.46203 | 0.84068 | 0.69288 | 0.64128 | 0.40223 | 83.0426 | 0.58433 | 7.649 | 6384.5682
49 | 0.1063 | 22 | 0.94281 | 0.15858 | 0.37931 | 0.6871 | 0.69157 | 108 | 0.90037 | 1.1566 | 0.95461 | 1.0956 | 0.4266 | 0.56643 | 0.73634 | 105.5311 | 0.75899 | 9.4026 | 6661.4232
50 | 0.99203 | 29 | 0.56163 | 0.085322 | 0.47427 | 0.69739 | 0.2555 | 104 | 0.6028 | 1.0636 | 0.55577 | 0.87348 | 0.60957 | 0.61848 | 0.21486 | 73.1766 | 0.88333 | 11.1055 | 6941.3191
51 | 0.41353 | 25 | 0.93478 | 0.15577 | 0.2637 | 0.67262 | 0.36857 | 105 | 0.50423 | 1.0417 | 0.98632 | 1.1427 | 0.87993 | 0.70825 | 0.65179 | 98.8965 | 0.089402 | 3.8673 | 7225.9185
52 | 0.44877 | 25 | 0.013672 | 0.011693 | 0.55208 | 0.70535 | 0.3384 | 105 | 0.81739 | 1.1236 | 0.54489 | 0.8695 | 0.8756 | 0.70625 | 0.97849 | 137.2994 | 0.82742 | 10.2635 | 6851.0928
53 | 0.81134 | 27 | 0.9531 | 0.16249 | 0.42893 | 0.69262 | 0.53153 | 107 | 0.67319 | 1.0809 | 0.64941 | 0.90993 | 0.73661 | 0.65449 | 0.023041 | 57.5897 | 0.30129 | 5.4694 | 6954.5736
54 | 0.062039 | 22 | 0.78492 | 0.11967 | 0.049732 | 0.63154 | 0.69683 | 108 | 0.55123 | 1.0518 | 0.6276 | 0.90104 | 0.1068 | 0.43331 | 0.29887 | 77.4848 | 0.16298 | 4.5211 | 5769.1488
55 | 0.014902 | 21 | 0.30613 | 0.055722 | 0.86862 | 0.74874 | 0.36766 | 105 | 0.62236 | 1.0682 | 0.60163 | 0.8908 | 0.97847 | 0.77268 | 0.51886 | 89.9291 | 0.13644 | 4.3068 | 6046.9208
56 | 0.78643 | 27 | 0.14112 | 0.037566 | 0.96944 | 0.77528 | 0.050982 | 102 | 0.5515 | 1.0519 | 0.43134 | 0.83057 | 0.6647 | 0.63326 | 0.8229 | 113.555 | 0.53734 | 7.2446 | 6522.2334
57 | 0.60967 | 26 | 0.47808 | 0.074869 | 0.036822 | 0.62714 | 0.4455 | 106 | 0.17533 | 0.97834 | 0.89724 | 1.043 | 0.96754 | 0.7619 | 0.83133 | 114.4329 | 0.62443 | 8.0126 | 7207.4118
58 | 0.58194 | 25 | 0.95131 | 0.16178 | 0.075309 | 0.63881 | 0.23032 | 104 | 0.94283 | 1.1793 | 0.34979 | 0.80497 | 0.12404 | 0.44367 | 0.10646 | 66.3141 | 0.11798 | 4.145 | 6304.9938
59 | 0.040099 | 21 | 0.5281 | 0.081017 | 0.36548 | 0.6855 | 0.98576 | 114 | 0.54433 | 1.0503 | 0.36914 | 0.81089 | 0.39368 | 0.55595 | 0.48696 | 87.9692 | 0.91958 | 11.7666 | 5769.2019
60 | 0.36375 | 24 | 0.38534 | 0.064207 | 0.5075 | 0.70075 | 0.7008 | 108 | 0.68238 | 1.0833 | 0.73254 | 0.94664 | 0.51971 | 0.59407 | 0.67101 | 100.3269 | 0.9438 | 12.2972 | 6456.3582
61 | 0.4921 | 25 | 0.96019 | 0.16544 | 0.90096 | 0.75549 | 0.20834 | 104 | 0.5655 | 1.055 | 0.63694 | 0.90481 | 0.48194 | 0.58319 | 0.88571 | 120.7219 | 0.71129 | 8.8737 | 6640.7847
62 | 0.47572 | 25 | 0.84562 | 0.13195 | 0.92358 | 0.7609 | 0.61657 | 107 | 0.43777 | 1.0282 | 0.59709 | 0.88904 | 0.14426 | 0.45494 | 0.16029 | 70.018 | 0.2336 | 5.0184 | 5974.5277
63 | 0.057158 | 22 | 0.33768 | 0.059041 | 0.46477 | 0.69641 | 0.89907 | 111 | 0.74258 | 1.0999 | 0.58182 | 0.8832 | 0.63593 | 0.62542 | 0.15028 | 69.3827 | 0.54231 | 7.2864 | 6024.4678
64 | 0.75102 | 26 | 0.41894 | 0.06797 | 0.94959 | 0.76825 | 0.018004 | 101 | 0.58519 | 1.0595 | 0.37749 | 0.81347 | 0.9412 | 0.7418 | 0.75445 | 107.0857 | 0.44281 | 6.4891 | 6636.9538
65 | 0.70541 | 26 | 0.90196 | 0.14577 | 0.18699 | 0.66115 | 0.53347 | 107 | 0.20357 | 0.98441 | 0.61353 | 0.89545 | 0.98769 | 0.78423 | 0.043816 | 60.4661 | 0.22638 | 4.9713 | 6865.3641
66 | 0.78629 | 27 | 0.24302 | 0.049297 | 0.070268 | 0.63749 | 0.91659 | 111 | 0.39353 | 1.0196 | 0.0023974 | 0.61696 | 0.7392 | 0.65531 | 0.098034 | 65.6552 | 0.040614 | 3.2585 | 6250.7046
67 | 0.081686 | 22 | 0.52763 | 0.080958 | 0.052913 | 0.63253 | 0.28822 | 105 | 0.98746 | 1.2169 | 0.35329 | 0.80603 | 0.2166 | 0.48985 | 0.45671 | 86.1665 | 0.70819 | 8.8409 | 6026.4909
68 | 0.0079187 | 21 | 0.048348 | 0.021988 | 0.50962 | 0.70097 | 0.26868 | 104 | 0.68948 | 1.0852 | 0.98628 | 1.1426 | 0.60079 | 0.61618 | 0.80155 | 111.4202 | 0.37507 | 5.9866 | 6183.8701
69 | 0.17213 | 23 | 0.94302 | 0.15865 | 0.76486 | 0.73142 | 0.41015 | 106 | 0.12663 | 0.96657 | 0.39501 | 0.81895 | 0.59384 | 0.61435 | 0.88404 | 120.5096 | 0.16431 | 4.5315 | 6158.9507
70 | 0.40349 | 24 | 0.40386 | 0.066269 | 0.45691 | 0.69559 | 0.34005 | 105 | 0.63507 | 1.0713 | 0.58604 | 0.8848 | 0.40245 | 0.55878 | 0.5516 | 92.0088 | 0.88546 | 11.1411 | 6199.7604
71 | 0.41378 | 25 | 0.69334 | 0.10408 | 0.65003 | 0.71634 | 0.094694 | 103 | 0.91646 | 1.1645 | 0.43125 | 0.83054 | 0.34196 | 0.53854 | 0.10826 | 66.4514 | 0.23491 | 5.0269 | 6279.4925
72 | 0.43575 | 25 | 0.78449 | 0.11959 | 0.33767 | 0.68218 | 0.086018 | 103 | 0.52076 | 1.0452 | 0.11777 | 0.71888 | 0.13751 | 0.45127 | 0.74573 | 106.3307 | 0.38385 | 6.0502 | 5992.2973
73 | 0.51956 | 25 | 0.27576 | 0.052599 | 0.92717 | 0.76183 | 0.31223 | 105 | 0.86184 | 1.14 | 0.65384 | 0.91177 | 0.5024 | 0.58913 | 0.31953 | 78.561 | 0.80286 | 9.9376 | 6388.564
74 | 0.14522 | 23 | 0.95431 | 0.16298 | 0.060856 | 0.63489 | 0.74511 | 109 | 0.45222 | 1.0311 | 0.28243 | 0.7841 | 0.58644 | 0.61238 | 0.19822 | 72.2612 | 0.045806 | 3.3366 | 6149.9072
75 | 0.68897 | 26 | 0.16131 | 0.040163 | 0.36898 | 0.6859 | 0.23419 | 104 | 0.98705 | 1.2163 | 0.4222 | 0.82761 | 0.78177 | 0.66935 | 0.6009 | 95.2895 | 0.81897 | 10.1488 | 6940.9095
76 | 0.27931 | 24 | 0.7524 | 0.11381 | 0.95055 | 0.76855 | 0.27298 | 105 | 0.5214 | 1.0454 | 0.01661 | 0.64465 | 0.24208 | 0.5007 | 0.73615 | 105.5157 | 0.33618 | 5.7104 | 5770.1888
77 | 0.61372 | 26 | 0.0078954 | 0.0088856 | 0.39323 | 0.68868 | 0.49661 | 106 | 0.49939 | 1.0407 | 0.14709 | 0.73286 | 0.97133 | 0.76539 | 0.12087 | 67.3834 | 0.17645 | 4.6233 | 6375.7402
78 | 0.93246 | 28 | 0.79291 | 0.12118 | 0.84004 | 0.74344 | 0.49948 | 106 | 0.39949 | 1.0208 | 0.63682 | 0.90476 | 0.89865 | 0.71733 | 0.73665 | 105.5573 | 0.52483 | 7.1405 | 7161.1756
79 | 0.44596 | 25 | 0.58526 | 0.088456 | 0.15876 | 0.65635 | 0.8172 | 110 | 0.42885 | 1.0264 | 0.049398 | 0.67699 | 0.15944 | 0.46288 | 0.72021 | 104.1917 | 0.028186 | 3.0484 | 5935.2322
80 | 0.082703 | 22 | 0.84566 | 0.13195 | 0.31494 | 0.67937 | 0.14801 | 103 | 0.84384 | 1.1331 | 0.14375 | 0.73134 | 0.036779 | 0.37823 | 0.35671 | 80.5401 | 0.21361 | 4.8863 | 5557.1714
81 | 0.80296 | 27 | 0.092761 | 0.030457 | 0.54259 | 0.70435 | 0.17187 | 104 | 0.81944 | 1.1243 | 0.48944 | 0.84995 | 0.92977 | 0.73454 | 0.14234 | 68.8639 | 0.2809 | 5.3314 | 6861.576
82 | 0.60549 | 26 | 0.41039 | 0.067002 | 0.69188 | 0.7215 | 0.54082 | 107 | 0.93801 | 1.1764 | 0.30056 | 0.78991 | 0.074724 | 0.41151 | 0.089176 | 64.9312 | 0.71367 | 8.8989 | 6063.4069
83 | 0.45689 | 25 | 0.87366 | 0.13844 | 0.057292 | 0.63385 | 0.1103 | 103 | 0.23918 | 0.99149 | 0.57411 | 0.88029 | 0.67318 | 0.63564 | 0.072303 | 63.4446 | 0.1618 | 4.512 | 6372.7629
84 | 0.55111 | 25 | 0.10604 | 0.032563 | 0.72905 | 0.72639 | 0.36976 | 105 | 0.95679 | 1.1885 | 0.40014 | 0.82057 | 0.51936 | 0.59397 | 0.049336 | 61.1058 | 0.15236 | 4.4376 | 6266.856
85 | 0.32006 | 24 | 0.20715 | 0.045514 | 0.036045 | 0.62685 | 0.96213 | 113 | 0.6398 | 1.0725 | 0.034058 | 0.66393 | 0.73007 | 0.65245 | 0.38102 | 81.8651 | 0.55959 | 7.4334 | 6161.7939
86 | 0.12046 | 22 | 0.86185 | 0.13562 | 0.52669 | 0.70271 | 0.26323 | 104 | 0.2161 | 0.98697 | 0.37014 | 0.8112 | 0.21026 | 0.48705 | 0.67567 | 100.6795 | 0.2652 | 5.2263 | 5695.5994
87 | 0.069792 | 22 | 0.44493 | 0.070957 | 0.75378 | 0.72983 | 0.59654 | 107 | 0.64367 | 1.0734 | 0.48568 | 0.84866 | 0.8707 | 0.70404 | 0.052312 | 61.4359 | 0.38625 | 6.0676 | 5973.3621
88 | 0.86833 | 27 | 0.72079 | 0.10848 | 0.6761 | 0.71951 | 0.10615 | 103 | 0.42477 | 1.0257 | 0.86473 | 1.0198 | 0.26857 | 0.5114 | 0.97952 | 137.6056 | 0.48478 | 6.8159 | 6839.7908
89 | 0.032854 | 21 | 0.78316 | 0.11934 | 0.67531 | 0.71942 | 0.97698 | 113 | 0.98299 | 1.2114 | 0.24431 | 0.77122 | 0.25339 | 0.50534 | 0.50492 | 89.0651 | 0.65341 | 8.2876 | 5941.9949
90 | 0.98412 | 29 | 0.72646 | 0.10941 | 0.40057 | 0.68951 | 0.44368 | 106 | 0.31588 | 1.0053 | 0.67395 | 0.92027 | 0.24184 | 0.50061 | 0.73223 | 105.1861 | 0.51883 | 7.091 | 6807.0858
91 | 0.67911 | 26 | 0.013953 | 0.011812 | 0.52957 | 0.703 | 0.066228 | 102 | 0.78368 | 1.1124 | 0.7126 | 0.93737 | 0.88078 | 0.70865 | 0.85475 | 116.9945 | 0.22878 | 4.9871 | 6926.0226
92 | 0.98391 | 29 | 0.30006 | 0.055093 | 0.54564 | 0.70467 | 0.75552 | 109 | 0.93467 | 1.1744 | 0.63643 | 0.90461 | 0.31665 | 0.52954 | 0.38404 | 82.0318 | 0.25368 | 5.15 | 7038.0433
93 | 0.74426 | 26 | 0.13249 | 0.036399 | 0.56528 | 0.70676 | 0.71664 | 108 | 0.47134 | 1.0349 | 0.28795 | 0.78589 | 0.65768 | 0.63132 | 0.0020306 | 52.2531 | 0.23395 | 5.0207 | 6140.8885
94 | 0.10523 | 22 | 0.71922 | 0.10822 | 0.18463 | 0.66077 | 0.37742 | 105 | 0.12737 | 0.96677 | 0.22009 | 0.76251 | 0.43662 | 0.56954 | 0.51274 | 89.5481 | 0.24521 | 5.0943 | 5686.2633
95 | 0.8777 | 28 | 0.023846 | 0.015442 | 0.51831 | 0.70185 | 0.3325 | 105 | 0.45486 | 1.0316 | 0.044182 | 0.67281 | 0.20097 | 0.48287 | 0.41475 | 83.7476 | 0.48411 | 6.8106 | 5980.1926
96 | 0.63764 | 26 | 0.56619 | 0.085919 | 0.33974 | 0.68243 | 0.62943 | 108 | 0.24877 | 0.99331 | 0.83062 | 0.99838 | 0.53182 | 0.59748 | 0.15737 | 69.8347 | 0.956 | 12.6085 | 6554.4152
97 | 0.010974 | 21 | 0.81385 | 0.12527 | 0.87655 | 0.75031 | 0.87205 | 111 | 0.27748 | 0.99855 | 0.9981 | 1.1786 | 0.29389 | 0.52114 | 0.36623 | 81.0561 | 0.10067 | 3.9814 | 5962.3257
98 | 0.80925 | 27 | 0.82142 | 0.1268 | 0.98703 | 0.7839 | 0.36144 | 105 | 0.2999 | 1.0025 | 0.55407 | 0.87285 | 0.862 | 0.7002 | 0.17648 | 71.005 | 0.45131 | 6.5543 | 6637.9994
99 | 0.88609 | 28 | 0.7644 | 0.11593 | 0.10603 | 0.64605 | 0.31385 | 105 | 0.070735 | 0.94976 | 0.089007 | 0.70335 | 0.45408 | 0.57488 | 0.097005 | 65.5728 | 0.69005 | 8.6523 | 6256.19
100 | 0.6125 | 26 | 0.72264 | 0.10878 | 0.060555 | 0.6348 | 0.48435 | 106 | 0.27199 | 0.99757 | 0.97418 | 1.1213 | 0.9881 | 0.78483 | 0.2002 | 72.3719 | 0.016966 | 2.8134 | 7269.0197
101 | 0.36159 | 24 | 0.24025 | 0.049015 | 0.31728 | 0.67966 | 0.59743 | 107 | 0.42479 | 1.0257 | 0.72007 | 0.9408 | 0.039834 | 0.38141 | 0.58158 | 93.9807 | 0.83683 | 10.3944 | 5810.0657
102 | 0.21339 | 23 | 0.96361 | 0.16696 | 0.64821 | 0.71612 | 0.44509 | 106 | 0.24808 | 0.99318 | 0.99993 | 1.1959 | 0.98159 | 0.77625 | 0.55755 | 92.3947 | 0.49795 | 6.9213 | 6975.0002
103 | 0.13654 | 23 | 0.24273 | 0.049268 | 0.56186 | 0.70639 | 0.73501 | 109 | 0.55427 | 1.0525 | 0.27013 | 0.78004 | 0.76971 | 0.66524 | 0.89648 | 122.1363 | 0.43354 | 6.4186 | 6219.8923
104 | 0.7845 | 27 | 0.17376 | 0.041684 | 0.28002 | 0.67484 | 0.92079 | 112 | 0.33322 | 1.0085 | 0.9814 | 1.1332 | 0.1422 | 0.45383 | 0.57596 | 93.6061 | 0.29908 | 5.4543 | 6609.602
105 | 0.8172 | 27 | 0.21725 | 0.04661 | 0.65522 | 0.71696 | 0.049434 | 102 | 0.69761 | 1.0873 | 0.13046 | 0.72512 | 0.31249 | 0.52803 | 0.28315 | 76.6762 | 0.1305 | 4.256 | 6117.2707
106 | 0.4899 | 25 | 0.53626 | 0.08205 | 0.93012 | 0.76261 | 0.77001 | 109 | 0.098061 | 0.95858 | 0.53149 | 0.86467 | 0.22194 | 0.49217 | 0.92732 | 126.6534 | 0.66085 | 8.36 | 6096.693
107 | 0.56176 | 25 | 0.39218 | 0.064964 | 0.37194 | 0.68625 | 0.24234 | 104 | 0.62899 | 1.0698 | 0.096069 | 0.70737 | 0.13094 | 0.44761 | 0.66218 | 99.6645 | 0.54614 | 7.3187 | 5876.3231
108 | 0.58448 | 25 | 0.3015 | 0.055242 | 0.70344 | 0.72299 | 0.86634 | 111 | 0.65256 | 1.0756 | 0.57085 | 0.87907 | 0.72112 | 0.6497 | 0.50309 | 88.9524 | 0.18276 | 4.6698 | 6510.6021
109 | 0.56901 | 25 | 0.76436 | 0.11592 | 0.58629 | 0.70904 | 0.77797 | 109 | 0.73327 | 1.0972 | 0.31781 | 0.79529 | 0.52424 | 0.59535 | 0.29019 | 77.0373 | 0.60209 | 7.8078 | 6398.603
110 | 0.93656 | 28 | 0.82077 | 0.12667 | 0.79716 | 0.73631 | 0.043142 | 102 | 0.95668 | 1.1884 | 0.78715 | 0.97398 | 0.30711 | 0.52606 | 0.71287 | 103.5944 | 0.90186 | 11.4281 | 7156.4295
111 | 0.083184 | 22 | 0.78926 | 0.12049 | 0.3521 | 0.68392 | 0.48999 | 106 | 0.49664 | 1.0401 | 0.9838 | 1.1376 | 0.98949 | 0.78693 | 0.80803 | 112.0553 | 0.2159 | 4.9017 | 6873.6909
112 | 0.52872 | 25 | 0.8799 | 0.13998 | 0.86781 | 0.74858 | 0.99403 | 114 | 0.93881 | 1.1768 | 0.15724 | 0.73736 | 0.20186 | 0.48328 | 0.19765 | 72.229 | 0.81927 | 10.1528 | 6289.8918
113 | 0.26105 | 24 | 0.16917 | 0.041131 | 0.64306 | 0.71551 | 0.38668 | 105 | 0.59456 | 1.0617 | 0.62046 | 0.89819 | 0.28507 | 0.5178 | 0.60023 | 95.2433 | 0.72278 | 8.9968 | 6034.9334
114 | 0.0726 | 22 | 0.74837 | 0.11311 | 0.73719 | 0.7275 | 0.062986 | 102 | 0.29756 | 1.0021 | 0.018373 | 0.64696 | 0.90305 | 0.71959 | 0.94348 | 129.4116 | 0.77512 | 9.5931 | 5983.0507
115 | 0.53896 | 25 | 0.28641 | 0.053686 | 0.034505 | 0.62627 | 0.93929 | 112 | 0.42807 | 1.0263 | 0.89474 | 1.0411 | 0.83259 | 0.68805 | 0.26101 | 75.5523 | 0.08046 | 3.7714 | 6792.2559
116 | 0.1092 | 22 | 0.2536 | 0.05036 | 0.60387 | 0.71099 | 0.76322 | 109 | 0.81706 | 1.1235 | 0.45337 | 0.8378 | 0.41917 | 0.5641 | 0.86906 | 118.6625 | 0.61227 | 7.9004 | 6079.0371
117 | 0.56495 | 25 | 0.48764 | 0.076021 | 0.64114 | 0.71528 | 0.38831 | 105 | 0.16962 | 0.97705 | 0.033765 | 0.66365 | 0.59505 | 0.61467 | 0.76637 | 108.1403 | 0.6243 | 8.0114 | 6000.9816
118 | 0.38261 | 24 | 0.21644 | 0.046523 | 0.073428 | 0.63832 | 0.75707 | 109 | 0.48653 | 1.038 | 0.26651 | 0.77883 | 0.86101 | 0.69977 | 0.97872 | 137.3678 | 0.11376 | 4.1063 | 6548.449
119 | 0.86942 | 27 | 0.92454 | 0.15242 | 0.62283 | 0.71315 | 0.39376 | 105 | 0.91353 | 1.163 | 0.66664 | 0.91715 | 0.63317 | 0.62468 | 0.42055 | 84.0766 | 0.64159 | 8.174 | 7148.2327
120 | 0.89879 | 28 | 0.28049 | 0.053081 | 0.0064598 | 0.61137 | 0.82076 | 110 | 0.02062 | 0.92686 | 0.38099 | 0.81456 | 0.33785 | 0.5371 | 0.48976 | 88.1389 | 0.57682 | 7.5829 | 6355.944
121 | 0.85427 | 27 | 0.55551 | 0.084524 | 0.1576 | 0.65614 | 0.25565 | 104 | 0.14996 | 0.97245 | 0.3978 | 0.81983 | 0.88678 | 0.71149 | 0.89674 | 122.171 | 0.82836 | 10.2763 | 6865.3246
122 | 0.12824 | 23 | 0.015529 | 0.012462 | 0.94501 | 0.76684 | 0.94713 | 112 | 0.32872 | 1.0076 | 0.12134 | 0.72067 | 0.49541 | 0.58712 | 0.57048 | 93.2426 | 0.40828 | 6.2294 | 5638.2324
123 | 0.58572 | 25 | 0.89007 | 0.14257 | 0.78754 | 0.73481 | 0.77497 | 109 | 0.39011 | 1.019 | 0.97036 | 1.1157 | 0.33688 | 0.53676 | 0.53278 | 90.8043 | 0.50443 | 6.9735 | 6635.4886
124 | 0.79711 | 27 | 0.77535 | 0.11791 | 0.31911 | 0.67989 | 0.23912 | 104 | 0.95706 | 1.1887 | 0.24968 | 0.7731 | 0.85369 | 0.69665 | 0.84483 | 115.8855 | 0.20426 | 4.8224 | 7270.7975
125 | 0.61219 | 26 | 0.63534 | 0.095407 | 0.25912 | 0.67199 | 0.029615 | 101 | 0.19051 | 0.98166 | 0.51986 | 0.86054 | 0.29194 | 0.52041 | 0.84188 | 115.5631 | 0.49389 | 6.8886 | 6311.5834
126 | 0.92169 | 28 | 0.66678 | 0.10002 | 0.0095509 | 0.61382 | 0.041062 | 102 | 0.84851 | 1.1349 | 0.70082 | 0.93204 | 0.26504 | 0.51001 | 0.91863 | 125.2959 | 0.41387 | 6.2709 | 7160.3887
127 | 0.47045 | 25 | 0.63193 | 0.094918 | 0.94531 | 0.76693 | 0.95203 | 112 | 0.2651 | 0.99632 | 0.18175 | 0.74768 | 0.56663 | 0.60706 | 0.25331 | 75.1655 | 0.39134 | 6.1047 | 6035.93
128 | 0.91741 | 28 | 0.052621 | 0.022939 | 0.0024383 | 0.60698 | 0.8188 | 110 | 0.36687 | 1.0146 | 0.11207 | 0.71596 | 0.82132 | 0.68368 | 0.9762 | 136.64 | 0.044696 | 3.3203 | 6930.8581
129 | 0.69532 | 26 | 0.82954 | 0.12849 | 0.31251 | 0.67906 | 0.62952 | 108 | 0.5554 | 1.0528 | 0.97873 | 1.1286 | 0.47946 | 0.58246 | 0.8906 | 121.3556 | 0.12837 | 4.2375 | 7159.016
130 | 0.42734 | 25 | 0.11624 | 0.034094 | 0.44596 | 0.69444 | 0.82435 | 110 | 0.88637 | 1.1503 | 0.4982 | 0.85297 | 0.97416 | 0.76816 | 0.77866 | 109.2566 | 0.21392 | 4.8884 | 7003.3853
131 | 0.66156 | 26 | 0.29474 | 0.054543 | 0.86442 | 0.74793 | 0.38951 | 105 | 0.082149 | 0.95362 | 0.8337 | 1.0002 | 0.10265 | 0.43069 | 0.75193 | 106.8664 | 0.40399 | 6.1977 | 6060.0672
132 | 0.59001 | 25 | 0.34802 | 0.060145 | 0.94113 | 0.76569 | 0.13858 | 103 | 0.79673 | 1.1166 | 0.43235 | 0.8309 | 0.42674 | 0.56648 | 0.17588 | 70.9687 | 0.31829 | 5.5861 | 6099.9415
133 | 0.34208 | 24 | 0.36098 | 0.061542 | 0.94894 | 0.76804 | 0.43247 | 106 | 0.80789 | 1.1203 | 0.82949 | 0.99771 | 0.19443 | 0.47987 | 0.41956 | 84.0204 | 0.62826 | 8.0483 | 6118.4292
134 | 0.47989 | 25 | 0.15405 | 0.039249 | 0.22017 | 0.66636 | 0.5169 | 106 | 0.76909 | 1.1079 | 0.80985 | 0.98637 | 0.64964 | 0.62912 | 0.67857 | 100.9011 | 0.50557 | 6.9828 | 6744.0666
135 | 0.12088 | 22 | 0.15553 | 0.039437 | 0.18059 | 0.6601 | 0.5077 | 106 | 0.08097 | 0.95323 | 0.91166 | 1.0544 | 0.58113 | 0.61097 | 0.24846 | 74.9227 | 0.10044 | 3.9792 | 5881.92
136 | 0.37142 | 24 | 0.27138 | 0.052153 | 0.41135 | 0.6907 | 0.60782 | 107 | 0.22388 | 0.98852 | 0.60064 | 0.89041 | 0.25922 | 0.50769 | 0.3109 | 78.1093 | 0.79334 | 9.8168 | 5855.4944
137 | 0.13005 | 23 | 0.67647 | 0.10148 | 0.41833 | 0.69147 | 0.88388 | 111 | 0.20021 | 0.98371 | 0.19472 | 0.75286 | 0.47868 | 0.58223 | 0.57229 | 93.3624 | 0.39616 | 6.14 | 5891.9236
138 | 0.27208 | 24 | 0.77405 | 0.11767 | 0.47417 | 0.69738 | 0.31429 | 105 | 0.92698 | 1.1701 | 0.97238 | 1.1186 | 0.86883 | 0.7032 | 0.53086 | 90.6825 | 0.14472 | 4.3757 | 7136.8887
139 | 0.033694 | 21 | 0.71663 | 0.1078 | 0.79236 | 0.73556 | 0.17912 | 104 | 0.10228 | 0.95983 | 0.25785 | 0.7759 | 0.8311 | 0.68746 | 0.97595 | 136.569 | 0.43345 | 6.418 | 5908.1903
140 | 0.11999 | 22 | 0.99342 | 0.18595 | 0.20951 | 0.66473 | 0.45583 | 106 | 0.79926 | 1.1175 | 0.090352 | 0.70413 | 0.84464 | 0.69289 | 0.25602 | 75.3018 | 0.24046 | 5.0632 | 6241.1649
141 | 0.40338 | 24 | 0.92431 | 0.15235 | 0.39942 | 0.68938 | 0.71144 | 108 | 0.68455 | 1.0839 | 0.73788 | 0.94918 | 0.31524 | 0.52903 | 0.78978 | 110.2928 | 0.69637 | 8.7173 | 6556.2423
142 | 0.56638 | 25 | 0.54574 | 0.083262 | 0.32799 | 0.68099 | 0.64724 | 108 | 0.7928 | 1.1154 | 0.91778 | 1.0595 | 0.063231 | 0.40257 | 0.036019 | 59.4893 | 0.80105 | 9.9143 | 6212.9086
143 | 0.84661 | 27 | 0.44032 | 0.070423 | 0.61583 | 0.71235 | 0.69216 | 108 | 0.54885 | 1.0513 | 0.29914 | 0.78946 | 0.75093 | 0.65906 | 0.94611 | 129.8952 | 0.26408 | 5.2189 | 6842.7332
144 | 0.24679 | 24 | 0.26267 | 0.051272 | 0.43606 | 0.69339 | 0.20857 | 104 | 0.44442 | 1.0295 | 0.30488 | 0.79127 | 0.1651 | 0.46575 | 0.70485 | 102.9506 | 0.63038 | 8.0682 | 5802.6206
145 | 0.63549 | 26 | 0.19444 | 0.044096 | 0.99394 | 0.78899 | 0.15459 | 103 | 0.79774 | 1.117 | 0.48046 | 0.84688 | 0.14603 | 0.45589 | 0.80871 | 112.1229 | 0.34267 | 5.756 | 6146.7048
146 | 0.36984 | 24 | 0.66927 | 0.10039 | 0.55287 | 0.70543 | 0.27489 | 105 | 0.43587 | 1.0278 | 0.94836 | 1.0887 | 0.75005 | 0.65877 | 0.88966 | 121.2334 | 0.6748 | 8.498 | 6804.6035
147 | 0.96374 | 29 | 0.31849 | 0.057013 | 0.86497 | 0.74803 | 0.25696 | 104 | 0.75222 | 1.1028 | 0.5048 | 0.85525 | 0.97813 | 0.77231 | 0.82497 | 113.768 | 0.87459 | 10.9623 | 7451.5796
148 | 0.69224 | 26 | 0.15983 | 0.039979 | 0.36163 | 0.68505 | 0.27349 | 105 | 0.86653 | 1.1419 | 0.9698 | 1.1149 | 0.70858 | 0.64591 | 0.033722 | 59.1817 | 0.57924 | 7.6041 | 6971.3281
149 | 0.26471 | 24 | 0.058795 | 0.024248 | 0.53071 | 0.70312 | 0.92127 | 112 | 0.49917 | 1.0407 | 0.66791 | 0.91769 | 0.73835 | 0.65504 | 0.64174 | 98.1641 | 0.04363 | 3.3044 | 6360.4035
150 | 0.61697 | 26 | 0.25245 | 0.050245 | 0.36357 | 0.68527 | 0.90346 | 111 | 0.37583 | 1.0163 | 0.97413 | 1.1212 | 0.9988 | 0.80881 | 0.06978 | 63.208 | 0.86783 | 10.8549 | 7232.6248
151 | 0.096725 | 22 | 0.5232 | 0.080401 | 0.35773 | 0.68459 | 0.70846 | 108 | 0.23674 | 0.99103 | 0.084058 | 0.70043 | 0.99511 | 0.79745 | 0.5465 | 91.68 | 0.47969 | 6.7756 | 6014.7357
152 | 0.56619 | 25 | 0.98979 | 0.1825 | 0.071962 | 0.63794 | 0.36664 | 105 | 0.31168 | 1.0046 | 0.63985 | 0.906 | 0.27133 | 0.51248 | 0.42149 | 84.1304 | 0.12781 | 4.2327 | 6383.0093
153 | 0.91503 | 28 | 0.76655 | 0.11631 | 0.055095 | 0.63319 | 0.55672 | 107 | 0.98258 | 1.211 | 0.40014 | 0.82057 | 0.24981 | 0.50388 | 0.90264 | 122.9779 | 0.87982 | 11.0474 | 7236.5211
154 | 0.2446 | 23 | 0.13393 | 0.036596 | 0.045717 | 0.63024 | 0.23976 | 104 | 0.72318 | 1.0944 | 0.52688 | 0.86303 | 0.33099 | 0.53468 | 0.30686 | 77.899 | 0.67802 | 8.5303 | 5952.7015
155 | 0.68066 | 26 | 0.41982 | 0.06807 | 0.64452 | 0.71568 | 0.32215 | 105 | 0.94177 | 1.1786 | 0.079357 | 0.69758 | 0.62617 | 0.62283 | 0.23143 | 74.0534 | 0.73097 | 9.0861 | 6459.3679
156 | 0.16859 | 23 | 0.45592 | 0.07224 | 0.39241 | 0.68859 | 0.11166 | 103 | 0.043861 | 0.93918 | 0.0086404 | 0.6322 | 0.14108 | 0.45322 | 0.98607 | 139.7802 | 0.98781 | 13.7411 | 5559.5347
157 | 0.30377 | 24 | 0.84206 | 0.13117 | 0.57291 | 0.70758 | 0.39348 | 105 | 0.79415 | 1.1158 | 0.61071 | 0.89434 | 0.011251 | 0.34327 | 0.487 | 87.9718 | 0.8609 | 10.7476 | 5932.6745
158 | 0.46243 | 25 | 0.81641 | 0.12579 | 0.48277 | 0.69826 | 0.061741 | 102 | 0.34963 | 1.0114 | 0.38158 | 0.81475 | 0.52901 | 0.59669 | 0.54846 | 91.8058 | 0.52675 | 7.1564 | 6266.2692
159 | 0.75427 | 26 | 0.70176 | 0.10541 | 0.27599 | 0.6743 | 0.98721 | 114 | 0.67055 | 1.0802 | 0.83329 | 0.99997 | 0.16588 | 0.46614 | 0.57153 | 93.312 | 0.79747 | 9.8689 | 6657.3148
160 | 0.52875 | 25 | 0.079885 | 0.028264 | 0.32222 | 0.68028 | 0.51185 | 106 | 0.78617 | 1.1132 | 0.60271 | 0.89121 | 0.31313 | 0.52827 | 0.93804 | 128.4437 | 0.64823 | 8.2376 | 6483.5125
161 | 0.24533 | 24 | 0.27865 | 0.052893 | 0.014125 | 0.61681 | 0.35924 | 105 | 0.43287 | 1.0272 | 0.58393 | 0.884 | 0.61044 | 0.61871 | 0.56487 | 92.8733 | 0.092435 | 3.8987 | 6278.1885
162 | 0.034031 | 21 | 0.52505 | 0.080633 | 0.85465 | 0.74608 | 0.4021 | 106 | 0.088028 | 0.95551 | 0.55014 | 0.87142 | 0.25959 | 0.50783 | 0.15423 | 69.6364 | 0.76844 | 9.5133 | 5344.584
163 | 0.1853 | 23 | 0.81272 | 0.12504 | 0.39322 | 0.68868 | 0.0093166 | 101 | 0.056231 | 0.94436 | 0.57261 | 0.87973 | 0.59448 | 0.61452 | 0.026819 | 58.1882 | 0.051985 | 3.4239 | 5803.9796
164 | 0.48071 | 25 | 0.14661 | 0.038289 | 0.26572 | 0.6729 | 0.33573 | 105 | 0.94032 | 1.1777 | 0.96992 | 1.115 | 0.21395 | 0.48868 | 0.2926 | 77.1612 | 0.60845 | 7.8655 | 6582.2101
165 | 0.14934 | 23 | 0.21185 | 0.046027 | 0.41954 | 0.6916 | 0.75936 | 109 | 0.025304 | 0.92976 | 0.07404 | 0.69426 | 0.85829 | 0.6986 | 0.43253 | 84.7618 | 0.3478 | 5.7921 | 5723.6053
166 | 0.52578 | 25 | 0.33051 | 0.05828 | 0.018291 | 0.61913 | 0.77039 | 109 | 0.35708 | 1.0128 | 0.40499 | 0.82211 | 0.56824 | 0.6075 | 0.28799 | 76.9244 | 0.66188 | 8.3701 | 6269.8901
167 | 0.070127 | 22 | 0.30995 | 0.05612 | 0.4861 | 0.6986 | 0.0041619 | 101 | 0.25253 | 0.99401 | 0.3287 | 0.7986 | 0.80028 | 0.67588 | 0.57072 | 93.2587 | 0.25795 | 5.1782 | 5792.5009
168 | 0.8089 | 27 | 0.35684 | 0.061094 | 0.45872 | 0.69578 | 0.87915 | 111 | 0.27763 | 0.99857 | 0.54107 | 0.86812 | 0.23285 | 0.49684 | 0.96874 | 134.6882 | 0.39948 | 6.1644 | 6532.4997
169 | 0.19411 | 23 | 0.25512 | 0.050512 | 0.72534 | 0.72588 | 0.8093 | 110 | 0.57217 | 1.0565 | 0.7742 | 0.96721 | 0.6379 | 0.62594 | 0.67668 | 100.7564 | 0.60619 | 7.8449 | 6291.0223
170 | 0.35975 | 24 | 0.043945 | 0.020963 | 0.41412 | 0.69101 | 0.47722 | 106 | 0.94533 | 1.1808 | 0.71252 | 0.93733 | 0.38289 | 0.55241 | 0.11413 | 66.8918 | 0.8012 | 9.9163 | 6263.6318
171 | 0.58182 | 25 | 0.70768 | 0.10635 | 0.95235 | 0.76913 | 0.13266 | 103 | 0.097264 | 0.95835 | 0.61947 | 0.8978 | 0.10528 | 0.43236 | 0.3039 | 77.7451 | 0.41969 | 6.3143 | 5742.3184
172 | 0.020079 | 21 | 0.90515 | 0.14666 | 0.50094 | 0.70009 | 0.15729 | 103 | 0.76839 | 1.1076 | 0.048149 | 0.67601 | 0.86676 | 0.70228 | 0.83083 | 114.3797 | 0.11118 | 4.0823 | 6079.6322
173 | 0.54152 | 25 | 0.055155 | 0.023485 | 0.30347 | 0.67791 | 0.94273 | 112 | 0.10525 | 0.9607 | 0.16514 | 0.74077 | 0.44158 | 0.57107 | 0.28497 | 76.7694 | 0.080217 | 3.7688 | 5820.2292
174 | 0.26421 | 24 | 0.39664 | 0.06546 | 0.27449 | 0.67409 | 0.38737 | 105 | 0.41926 | 1.0246 | 0.23816 | 0.76905 | 0.1014 | 0.42989 | 0.65086 | 98.8279 | 0.67197 | 8.4698 | 5739.9138
175 | 0.48436 | 25 | 0.84261 | 0.13129 | 0.078947 | 0.63974 | 0.21147 | 104 | 0.068957 | 0.94913 | 0.43969 | 0.83329 | 0.74242 | 0.65633 | 0.96234 | 133.1931 | 0.23078 | 5.0001 | 6588.8863
176 | 0.23346 | 23 | 0.53484 | 0.08187 | 0.63282 | 0.71431 | 0.91871 | 112 | 0.025765 | 0.93003 | 0.33897 | 0.80169 | 0.94924 | 0.74735 | 0.66063 | 99.549 | 0.012109 | 2.6872 | 6107.1124
177 | 0.50643 | 25 | 0.14004 | 0.037422 | 0.044572 | 0.62986 | 0.01018 | 101 | 0.43322 | 1.0273 | 0.27353 | 0.78117 | 0.39964 | 0.55788 | 0.19782 | 72.2387 | 0.1497 | 4.4162 | 5950.3527
178 | 0.081995 | 22 | 0.25775 | 0.050777 | 0.34692 | 0.6833 | 0.010681 | 101 | 0.066562 | 0.94827 | 0.35201 | 0.80564 | 0.36527 | 0.54654 | 0.65857 | 99.396 | 0.19091 | 4.7286 | 5523.3935
179 | 0.32412 | 24 | 0.028876 | 0.016993 | 0.68081 | 0.7201 | 0.8217 | 110 | 0.037483 | 0.93622 | 0.42911 | 0.82985 | 0.781 | 0.66908 | 0.23288 | 74.1288 | 0.73713 | 9.1543 | 5883.9704
180 | 0.91169 | 28 | 0.050322 | 0.022432 | 0.71108 | 0.72398 | 0.77568 | 109 | 0.50057 | 1.041 | 0.047494 | 0.67549 | 0.71011 | 0.64637 | 0.15033 | 69.3861 | 0.41861 | 6.3063 | 6334.38
181 | 0.64628 | 26 | 0.77971 | 0.11871 | 0.14974 | 0.65473 | 0.95612 | 112 | 0.15803 | 0.97437 | 0.25511 | 0.77497 | 0.076525 | 0.41284 | 0.88414 | 120.5225 | 0.84859 | 10.5633 | 6175.826
182 | 0.23726 | 23 | 0.55608 | 0.084599 | 0.054787 | 0.6331 | 0.044557 | 102 | 0.63075 | 1.0703 | 0.87302 | 1.0254 | 0.4763 | 0.58153 | 0.77673 | 109.0786 | 0.57586 | 7.5745 | 6445.724
183 | 0.77178 | 27 | 0.8427 | 0.13131 | 0.96034 | 0.77184 | 0.53695 | 107 | 0.57878 | 1.058 | 0.14454 | 0.7317 | 0.3084 | 0.52653 | 0.039046 | 59.8801 | 0.89563 | 11.3165 | 6185.4948
184 | 0.036404 | 21 | 0.42664 | 0.068848 | 0.10855 | 0.64659 | 0.25545 | 104 | 0.59142 | 1.0609 | 0.62191 | 0.89877 | 0.54088 | 0.6 | 0.28906 | 76.9792 | 0.58307 | 7.6378 | 5819.2471
185 | 0.56934 | 25 | 0.24631 | 0.04963 | 0.24463 | 0.66995 | 0.23709 | 104 | 0.24451 | 0.99251 | 0.18915 | 0.75066 | 0.32084 | 0.53106 | 0.7942 | 110.7127 | 0.26236 | 5.2075 | 5980.6357
186 | 0.11668 | 22 | 0.51056 | 0.078826 | 0.83641 | 0.7428 | 0.5852 | 107 | 0.43354 | 1.0274 | 0.67714 | 0.92164 | 0.39921 | 0.55774 | 0.17175 | 70.7213 | 0.69467 | 8.6998 | 5758.849
187 | 0.29116 | 24 | 0.40687 | 0.066606 | 0.34283 | 0.6828 | 0.8612 | 110 | 0.5892 | 1.0604 | 0.52784 | 0.86337 | 0.016596 | 0.35255 | 0.028019 | 58.3694 | 0.43992 | 6.4671 | 5587.0088
188 | 0.62396 | 26 | 0.037355 | 0.019327 | 0.80383 | 0.73736 | 0.59711 | 107 | 0.49159 | 1.0391 | 0.35848 | 0.80762 | 0.21233 | 0.48797 | 0.25201 | 75.1005 | 0.38765 | 6.0778 | 5895.7039
189 | 0.10865 | 22 | 0.001399 | 0.0037403 | 0.43408 | 0.69318 | 0.14013 | 103 | 0.64407 | 1.0735 | 0.74526 | 0.95274 | 0.18092 | 0.47351 | 0.77273 | 108.7139 | 0.21812 | 4.9166 | 5734.1251
190 | 0.79493 | 27 | 0.31262 | 0.056399 | 0.85115 | 0.74544 | 0.26605 | 104 | 0.0081653 | 0.91691 | 0.47131 | 0.84379 | 0.84032 | 0.69113 | 0.58498 | 94.2089 | 0.57001 | 7.5235 | 6378.2298
191 | 0.88193 | 28 | 0.016955 | 0.013021 | 0.81771 | 0.73962 | 0.84308 | 110 | 0.99193 | 1.2234 | 0.51965 | 0.86046 | 0.90639 | 0.72133 | 0.84245 | 115.6255 | 0.84761 | 10.5491 | 7517.5165
192 | 0.012856 | 21 | 0.52387 | 0.080485 | 0.31938 | 0.67992 | 0.78073 | 109 | 0.42447 | 1.0256 | 0.37069 | 0.81137 | 0.79654 | 0.67454 | 0.25655 | 75.3284 | 0.36486 | 5.9133 | 5802.156
193 | 0.0009309 | 20 | 0.31438 | 0.056583 | 0.90663 | 0.75679 | 0.53326 | 107 | 0.73077 | 1.0965 | 0.1487 | 0.73358 | 0.04215 | 0.38375 | 0.42561 | 84.365 | 0.7596 | 9.4097 | 5108.4748
194 | 0.78015 | 27 | 0.93662 | 0.15639 | 0.95307 | 0.76936 | 0.18934 | 104 | 0.038749 | 0.93683 | 0.076063 | 0.69554 | 0.02986 | 0.37049 | 0.58495 | 94.2071 | 0.62753 | 8.0414 | 5743.2595
195 | 0.88889 | 28 | 0.2845 | 0.05349 | 0.58155 | 0.70852 | 0.27376 | 105 | 0.96649 | 1.1959 | 0.64749 | 0.90914 | 0.78608 | 0.67084 | 0.37045 | 81.2859 | 0.33921 | 5.7317 | 7257.6018
196 | 0.48559 | 25 | 0.12523 | 0.035388 | 0.70783 | 0.72356 | 0.79743 | 109 | 0.59734 | 1.0623 | 0.97735 | 1.1263 | 0.0087122 | 0.33808 | 0.28939 | 76.9959 | 0.019249 | 2.8664 | 5943.5994
197 | 0.2056 | 23 | 0.42301 | 0.068433 | 0.22152 | 0.66656 | 0.66699 | 108 | 0.54212 | 1.0498 | 0.9078 | 1.0512 | 0.1413 | 0.45334 | 0.58984 | 94.5367 | 0.40724 | 6.2217 | 6059.9236
198 | 0.1776 | 23 | 0.77146 | 0.1172 | 0.7091 | 0.72372 | 0.86245 | 110 | 0.71504 | 1.0921 | 0.29844 | 0.78924 | 0.62076 | 0.6214 | 0.63131 | 97.4151 | 0.53615 | 7.2347 | 6246.6192
199 | 0.83187 | 27 | 0.44346 | 0.070786 | 0.7277 | 0.7262 | 0.86537 | 111 | 0.94104 | 1.1782 | 0.78919 | 0.97507 | 0.76067 | 0.66223 | 0.046479 | 60.7795 | 0.59714 | 7.7632 | 7147.8922
200 | 0.90648 | 28 | 0.14154 | 0.037622 | 0.78275 | 0.73408 | 0.5234 | 107 | 0.70287 | 1.0888 | 0.48214 | 0.84746 | 0.51783 | 0.59354 | 0.0065214 | 54.0378 | 0.66148 | 8.3662 | 6526.1677
201 | 0.37628 | 24 | 0.14657 | 0.038284 | 0.14158 | 0.65321 | 0.34129 | 105 | 0.091276 | 0.95652 | 0.28458 | 0.78479 | 0.96688 | 0.76131 | 0.29118 | 77.088 | 0.029437 | 3.0715 | 6102.0367
202 | 0.33023 | 24 | 0.85852 | 0.13485 | 0.67015 | 0.71878 | 0.64525 | 108 | 0.50335 | 1.0415 | 0.73581 | 0.9482 | 0.096754 | 0.42689 | 0.59569 | 94.9332 | 0.89483 | 11.3024 | 6110.5817
203 | 0.69612 | 26 | 0.67085 | 0.10063 | 0.80207 | 0.73708 | 0.80788 | 110 | 0.73484 | 1.0977 | 0.49771 | 0.8528 | 0.43461 | 0.56892 | 0.31575 | 78.3631 | 0.20426 | 4.8224 | 6495.4553
204 | 0.33423 | 24 | 0.804 | 0.12332 | 0.32672 | 0.68084 | 0.76634 | 109 | 0.97852 | 1.2066 | 0.71208 | 0.93713 | 0.46232 | 0.57736 | 0.0041866 | 53.2352 | 0.19161 | 4.7337 | 6559.8961
205 | 0.54492 | 25 | 0.87948 | 0.13987 | 0.55324 | 0.70547 | 0.54776 | 107 | 0.99059 | 1.2213 | 0.30844 | 0.79239 | 0.66767 | 0.63409 | 0.67676 | 100.7625 | 0.42568 | 6.3593 | 6896.8943
206 | 0.44523 | 25 | 0.047612 | 0.02182 | 0.6342 | 0.71447 | 0.41352 | 106 | 0.6718 | 1.0805 | 0.32318 | 0.79693 | 0.9438 | 0.74355 | 0.26583 | 75.7956 | 0.89127 | 11.2403 | 6442.192
207 | 0.7675 | 27 | 0.57567 | 0.087173 | 0.7402 | 0.72792 | 0.11797 | 103 | 0.72592 | 1.0951 | 0.39614 | 0.81931 | 0.8757 | 0.7063 | 0.12089 | 67.3849 | 0.23232 | 5.0101 | 6731.3277
208 | 0.021757 | 21 | 0.0068759 | 0.0082921 | 0.51779 | 0.7018 | 0.15783 | 103 | 0.98747 | 1.2169 | 0.66006 | 0.91437 | 0.263 | 0.5092 | 0.47265 | 87.1105 | 0.5138 | 7.0498 | 5768.4124
209 | 0.9455 | 28 | 0.075957 | 0.02756 | 0.15817 | 0.65624 | 0.12149 | 103 | 0.058036 | 0.94507 | 0.65175 | 0.9109 | 0.102 | 0.43028 | 0.035158 | 59.3752 | 0.46521 | 6.662 | 5958.2968
210 | 0.61327 | 26 | 0.37123 | 0.062657 | 0.0024115 | 0.60694 | 0.51723 | 106 | 0.59181 | 1.061 | 0.47795 | 0.84604 | 0.82991 | 0.687 | 0.051957 | 61.397 | 0.71028 | 8.8629 | 6667.2245
211 | 0.852 | 27 | 0.71187 | 0.10703 | 0.24051 | 0.66936 | 0.4524 | 106 | 0.26087 | 0.99555 | 0.19447 | 0.75276 | 0.87191 | 0.70458 | 0.10464 | 66.1739 | 0.10604 | 4.0336 | 6541.675
212 | 0.14879 | 23 | 0.18431 | 0.042931 | 0.49027 | 0.69902 | 0.29325 | 105 | 0.62083 | 1.0679 | 0.9706 | 1.116 | 0.21496 | 0.48913 | 0.61722 | 96.4199 | 0.10531 | 4.0266 | 6124.6174
213 | 0.99431 | 29 | 0.079362 | 0.028171 | 0.45997 | 0.69591 | 0.78394 | 109 | 0.84322 | 1.1329 | 0.29545 | 0.78829 | 0.36461 | 0.54632 | 0.88669 | 120.8483 | 0.82036 | 10.1675 | 6971.1815
214 | 0.87861 | 28 | 0.28429 | 0.053469 | 0.22979 | 0.66779 | 0.10324 | 103 | 0.85547 | 1.1375 | 0.99813 | 1.1788 | 0.96306 | 0.75801 | 0.14002 | 68.7094 | 0.74497 | 9.2421 | 7811.9626
215 | 0.49946 | 25 | 0.58752 | 0.08876 | 0.57322 | 0.70761 | 0.54724 | 107 | 0.15862 | 0.97451 | 0.91213 | 1.0548 | 0.58284 | 0.61142 | 0.18213 | 71.3382 | 0.65493 | 8.3023 | 6429.7825
216 | 0.053728 | 22 | 0.25948 | 0.050951 | 0.79473 | 0.73593 | 0.049342 | 102 | 0.14622 | 0.97154 | 0.14113 | 0.73014 | 0.08397 | 0.41821 | 0.0032389 | 52.8456 | 0.817 | 10.1225 | 5002.7657
217 | 0.59295 | 25 | 0.93845 | 0.15703 | 0.73091 | 0.72664 | 0.20194 | 104 | 0.23714 | 0.9911 | 0.17049 | 0.74303 | 0.76872 | 0.66491 | 0.054835 | 61.7084 | 0.46476 | 6.6585 | 6156.1047
218 | 0.77032 | 27 | 0.22623 | 0.047564 | 0.97721 | 0.77865 | 0.25503 | 104 | 0.10427 | 0.96041 | 0.14166 | 0.73038 | 0.41866 | 0.56394 | 0.14776 | 69.2199 | 0.18414 | 4.6798 | 5832.1197
219 | 0.82925 | 27 | 0.41925 | 0.068005 | 0.4034 | 0.68982 | 0.72391 | 109 | 0.60958 | 1.0652 | 0.35556 | 0.80672 | 0.29803 | 0.52269 | 0.37716 | 81.6532 | 0.41618 | 6.2881 | 6388.5552
220 | 0.32881 | 24 | 0.30765 | 0.05588 | 0.28133 | 0.67501 | 0.1797 | 104 | 0.88324 | 1.1489 | 0.7904 | 0.97571 | 0.35005 | 0.54135 | 0.78551 | 109.8919 | 0.12551 | 4.2124 | 6486.0402
221 | 0.2628 | 24 | 0.47997 | 0.075097 | 0.41941 | 0.69159 | 0.50665 | 106 | 0.38458 | 1.0179 | 0.30932 | 0.79266 | 0.41689 | 0.56338 | 0.51879 | 89.9244 | 0.11783 | 4.1437 | 5968.6482
222 | 0.14519 | 23 | 0.66318 | 0.099479 | 0.57565 | 0.70788 | 0.84383 | 110 | 0.13847 | 0.96962 | 0.86517 | 1.0201 | 0.3002 | 0.5235 | 0.8805 | 120.0625 | 0.74082 | 9.1954 | 6205.1877
223 | 0.24536 | 24 | 0.27184 | 0.0522 | 0.96047 | 0.77188 | 0.99897 | 115 | 0.3819 | 1.0174 | 0.44609 | 0.83539 | 0.93498 | 0.73777 | 0.10342 | 66.0793 | 0.83962 | 10.4339 | 6253.0468
224 | 0.54281 | 25 | 0.36972 | 0.062492 | 0.60263 | 0.71085 | 0.18406 | 104 | 0.56275 | 1.0544 | 0.76135 | 0.96068 | 0.051907 | 0.39294 | 0.62816 | 97.1912 | 0.62653 | 8.0321 | 6003.9198
225 | 0.36176 | 24 | 0.44376 | 0.070821 | 0.99331 | 0.78843 | 0.77071 | 109 | 0.28821 | 1.0004 | 0.88721 | 1.0355 | 0.3897 | 0.55465 | 0.45227 | 85.9064 | 0.90542 | 11.4936 | 6163.8116
226 | 0.5859 | 25 | 0.67325 | 0.10099 | 0.03529 | 0.62657 | 0.88256 | 111 | 0.87575 | 1.1457 | 0.73838 | 0.94942 | 0.86871 | 0.70315 | 0.1913 | 71.8689 | 0.96195 | 12.7759 | 7101.991
227 | 0.62845 | 26 | 0.48281 | 0.075437 | 0.56679 | 0.70692 | 0.81384 | 110 | 0.30783 | 1.0039 | 0.5029 | 0.8546 | 0.36829 | 0.54756 | 0.74086 | 105.9141 | 0.86893 | 10.8721 | 6395.0785
228 | 0.30022 | 24 | 0.56243 | 0.085427 | 0.43851 | 0.69365 | 0.0084243 | 101 | 0.62185 | 1.0681 | 0.76708 | 0.96357 | 0.091029 | 0.42307 | 0.94805 | 130.2617 | 0.34867 | 5.7982 | 6166.0714
229 | 0.63437 | 26 | 0.51234 | 0.079046 | 0.74057 | 0.72797 | 0.81046 | 110 | 0.46348 | 1.0333 | 0.45041 | 0.83682 | 0.033628 | 0.3748 | 0.40163 | 83.0092 | 0.12179 | 4.1794 | 5881.3137
230 | 0.27397 | 24 | 0.37653 | 0.063237 | 0.50824 | 0.70083 | 0.1546 | 103 | 0.23648 | 0.99098 | 0.90223 | 1.0468 | 0.94766 | 0.74622 | 0.8241 | 113.6789 | 0.27951 | 5.322 | 6703.0774
231 | 0.69741 | 26 | 0.29237 | 0.054299 | 0.75327 | 0.72975 | 0.61981 | 107 | 0.59025 | 1.0606 | 0.45632 | 0.83878 | 0.77546 | 0.66719 | 0.53563 | 90.9852 | 0.82064 | 10.1713 | 6572.7703
232 | 0.57134 | 25 | 0.14041 | 0.037471 | 0.069771 | 0.63736 | 0.69416 | 108 | 0.30737 | 1.0038 | 0.051013 | 0.67824 | 0.18335 | 0.47467 | 0.068133 | 63.0512 | 0.91847 | 11.7444 | 5641.8531
233 | 0.38763 | 24 | 0.52208 | 0.08026 | 0.61165 | 0.71187 | 0.64046 | 108 | 0.65858 | 1.0772 | 0.89098 | 1.0382 | 0.35633 | 0.5435 | 0.39221 | 82.4838 | 0.69253 | 8.6777 | 6366.0428
234 | 0.10624 | 22 | 0.37333 | 0.062886 | 0.90605 | 0.75665 | 0.91656 | 111 | 0.54356 | 1.0502 | 0.38375 | 0.81542 | 0.63283 | 0.62459 | 0.51159 | 89.4767 | 0.40184 | 6.1818 | 5871.3609
235 | 0.10036 | 22 | 0.0737 | 0.027148 | 0.94784 | 0.7677 | 0.0015178 | 100 | 0.84384 | 1.1331 | 0.098014 | 0.70845 | 0.78199 | 0.66942 | 0.18782 | 71.669 | 0.37972 | 6.0202 | 5650.2767
236 | 0.18671 | 23 | 0.049883 | 0.022335 | 0.37315 | 0.68639 | 0.70958 | 108 | 0.022418 | 0.92801 | 0.21872 | 0.76201 | 0.5731 | 0.60881 | 0.65814 | 99.3643 | 0.59864 | 7.7767 | 5679.0992
237 | 0.066267 | 22 | 0.52281 | 0.080352 | 0.27682 | 0.67441 | 0.8186 | 110 | 0.44684 | 1.03 | 0.64927 | 0.90987 | 2.7959e-05 | 0.30216 | 0.89292 | 121.6616 | 0.65188 | 8.2727 | 5606.8157
238 | 0.72099 | 26 | 0.72537 | 0.10923 | 0.42275 | 0.69195 | 0.58869 | 107 | 0.52568 | 1.0463 | 0.18403 | 0.74861 | 0.9343 | 0.73734 | 0.1746 | 70.8926 | 0.94462 | 12.3168 | 6639.7699
239 | 0.6448 | 26 | 0.89109 | 0.14284 | 0.64445 | 0.71567 | 0.43332 | 106 | 0.22774 | 0.98928 | 0.9879 | 1.1461 | 0.49407 | 0.58673 | 0.80769 | 112.0224 | 0.4521 | 6.5604 | 6975.381
240 | 0.47824 | 25 | 0.19752 | 0.044443 | 0.13023 | 0.65104 | 0.14789 | 103 | 0.40846 | 1.0225 | 0.39519 | 0.81901 | 0.67475 | 0.63608 | 0.61571 | 96.3141 | 0.97174 | 13.0834 | 6330.4465
241 | 0.49377 | 25 | 0.86217 | 0.1357 | 0.71721 | 0.7248 | 0.23939 | 104 | 0.71144 | 1.0911 | 0.68749 | 0.92614 | 0.40951 | 0.56104 | 0.029815 | 58.6335 | 0.1701 | 4.5756 | 6341.7759
242 | 0.53317 | 25 | 0.2687 | 0.051882 | 0.19069 | 0.66176 | 0.46572 | 106 | 0.74156 | 1.0996 | 0.64533 | 0.90824 | 0.13228 | 0.44836 | 0.72242 | 104.3725 | 0.024226 | 2.972 | 6223.1562
243 | 0.78897 | 27 | 0.16943 | 0.041161 | 0.80969 | 0.73831 | 0.13353 | 103 | 0.30656 | 1.0037 | 0.61204 | 0.89486 | 0.68009 | 0.6376 | 0.6477 | 98.5969 | 0.069549 | 3.6469 | 6511.583
244 | 0.40578 | 25 | 0.28851 | 0.053902 | 0.81561 | 0.73927 | 0.42313 | 106 | 0.45838 | 1.0323 | 0.39179 | 0.81794 | 0.32407 | 0.53222 | 0.12836 | 67.9135 | 0.99919 | 14.6748 | 5932.4706
245 | 0.48767 | 25 | 0.88403 | 0.14102 | 0.69871 | 0.72237 | 0.15369 | 103 | 0.55725 | 1.0532 | 0.96938 | 1.1143 | 0.80715 | 0.67838 | 0.92115 | 125.6811 | 0.44506 | 6.5064 | 7151.6015
246 | 0.54647 | 25 | 0.60896 | 0.091689 | 0.10697 | 0.64625 | 0.54117 | 107 | 0.20232 | 0.98415 | 0.010869 | 0.63611 | 0.45913 | 0.5764 | 0.89366 | 121.7587 | 0.71139 | 8.8747 | 6121.732
247 | 0.10708 | 22 | 0.43939 | 0.070315 | 0.70534 | 0.72323 | 0.0077664 | 101 | 0.95805 | 1.1894 | 0.96597 | 1.1096 | 0.039273 | 0.38084 | 0.089618 | 64.9681 | 0.56169 | 7.4514 | 5787.4213
248 | 0.37882 | 24 | 0.80957 | 0.12442 | 0.6176 | 0.71255 | 0.82297 | 110 | 0.15464 | 0.97357 | 0.14285 | 0.73093 | 0.40639 | 0.56005 | 0.64779 | 98.6037 | 0.63147 | 8.0784 | 5979.0859
249 | 0.81114 | 27 | 0.67681 | 0.10153 | 0.17338 | 0.65889 | 0.65043 | 108 | 0.43658 | 1.028 | 0.50774 | 0.85628 | 0.98296 | 0.7779 | 0.65522 | 99.1488 | 0.71837 | 8.9492 | 7187.37
250 | 0.059926 | 22 | 0.98548 | 0.17913 | 0.27569 | 0.67426 | 0.63813 | 108 | 0.59434 | 1.0616 | 0.75888 | 0.95944 | 0.0057679 | 0.33098 | 0.012482 | 55.5862 | 0.048321 | 3.3728 | 5612.5925
251 | 0.32957 | 24 | 0.52267 | 0.080334 | 0.84141 | 0.74368 | 0.49212 | 106 | 0.51642 | 1.0443 | 0.34353 | 0.80307 | 0.18196 | 0.47401 | 0.74379 | 106.1639 | 0.40015 | 6.1693 | 5892.8159
252 | 0.17553 | 23 | 0.10468 | 0.032355 | 0.27222 | 0.67379 | 0.61255 | 107 | 0.093785 | 0.95729 | 0.90797 | 1.0514 | 0.16449 | 0.46544 | 0.97655 | 136.7381 | 0.95949 | 12.7052 | 6060.7357
253 | 0.78173 | 27 | 0.89583 | 0.1441 | 0.27708 | 0.67444 | 0.52376 | 107 | 0.60667 | 1.0645 | 0.075435 | 0.69514 | 0.49063 | 0.58573 | 0.51927 | 89.9544 | 0.68813 | 8.6327 | 6582.8338
254 | 0.6393 | 26 | 0.68983 | 0.10354 | 0.26413 | 0.67268 | 0.23973 | 104 | 0.7958 | 1.1163 | 0.70941 | 0.93591 | 0.64571 | 0.62805 | 0.5811 | 93.9488 | 0.471 | 6.7072 | 6910.737
255 | 0.61741 | 26 | 0.60862 | 0.091642 | 0.57161 | 0.70744 | 0.61631 | 107 | 0.64765 | 1.0744 | 0.4286 | 0.82968 | 0.090878 | 0.42297 | 0.81157 | 112.4075 | 0.068448 | 3.6339 | 6224.3581
256 | 0.48816 | 25 | 0.051237 | 0.022636 | 0.28617 | 0.67565 | 0.33177 | 105 | 0.90269 | 1.1577 | 0.76282 | 0.96141 | 0.87449 | 0.70575 | 0.72098 | 104.2547 | 0.98863 | 13.7843 | 6992.8605
257 | 0.52646 | 25 | 0.61952 | 0.093162 | 0.45598 | 0.6955 | 0.83371 | 110 | 0.09397 | 0.95735 | 0.74022 | 0.95031 | 0.015426 | 0.35066 | 0.52947 | 90.5949 | 0.92851 | 11.9514 | 5849.2859
258 | 0.72668 | 26 | 0.24572 | 0.04957 | 0.89995 | 0.75527 | 0.91002 | 111 | 0.78604 | 1.1132 | 0.46167 | 0.84056 | 0.022505 | 0.3612 | 0.13976 | 68.6924 | 0.13528 | 4.2969 | 5851.9851
259 | 0.20938 | 23 | 0.94249 | 0.15846 | 0.93307 | 0.76341 | 0.87338 | 111 | 0.71854 | 1.0931 | 0.61749 | 0.89701 | 0.55208 | 0.60309 | 0.07887 | 64.0419 | 0.73325 | 9.1113 | 6249.5298
260 | 0.88586 | 28 | 0.33748 | 0.059019 | 0.10154 | 0.64506 | 0.56496 | 107 | 0.60237 | 1.0635 | 0.93214 | 1.0724 | 0.59003 | 0.61334 | 0.48371 | 87.7734 | 0.9613 | 12.7571 | 7253.0705
261 | 0.47935 | 25 | 0.62757 | 0.094298 | 0.17076 | 0.65844 | 0.14755 | 103 | 0.045906 | 0.94008 | 0.082766 | 0.69966 | 0.69355 | 0.64148 | 0.83058 | 114.3535 | 0.39429 | 6.1263 | 6137.3896
262 | 0.68441 | 26 | 0.38947 | 0.064664 | 0.90082 | 0.75546 | 0.65062 | 108 | 0.15354 | 0.97331 | 0.00077166 | 0.60962 | 0.52831 | 0.5965 | 0.52784 | 90.4918 | 0.43142 | 6.4026 | 5861.9353
263 | 0.85308 | 27 | 0.25978 | 0.050981 | 0.86079 | 0.74723 | 0.41872 | 106 | 0.029699 | 0.93224 | 0.22182 | 0.76315 | 0.98171 | 0.77638 | 0.66324 | 99.7439 | 0.75054 | 9.3053 | 6506.9977
264 | 0.11355 | 22 | 0.79212 | 0.12103 | 0.1476 | 0.65433 | 0.39752 | 105 | 0.97446 | 1.2027 | 0.05864 | 0.68389 | 0.24319 | 0.50116 | 0.65277 | 98.9684 | 0.031572 | 3.1096 | 5975.3087
265 | 0.43752 | 25 | 0.23753 | 0.048737 | 0.87352 | 0.7497 | 0.81693 | 110 | 0.85499 | 1.1374 | 0.4722 | 0.84409 | 0.0469 | 0.38834 | 0.86918 | 118.6762 | 0.82144 | 10.1821 | 6112.1399
266 | 0.46194 | 25 | 0.8355 | 0.12975 | 0.2199 | 0.66632 | 0.62482 | 107 | 0.66756 | 1.0794 | 0.60675 | 0.89279 | 0.7587 | 0.66158 | 0.87605 | 119.5105 | 0.56477 | 7.478 | 6925.659
267 | 0.8454 | 27 | 0.26715 | 0.051725 | 0.55592 | 0.70576 | 0.83661 | 110 | 0.46606 | 1.0339 | 0.9041 | 1.0483 | 0.41089 | 0.56148 | 0.9506 | 130.7512 | 0.90831 | 11.5474 | 6997.2677
268 | 0.86752 | 27 | 0.92891 | 0.15382 | 0.84471 | 0.74427 | 0.80759 | 110 | 0.75991 | 1.1051 | 0.089337 | 0.70354 | 0.92223 | 0.73007 | 0.4431 | 85.3725 | 0.80537 | 9.9699 | 6962.5897
269 | 0.69463 | 26 | 0.24769 | 0.049769 | 0.28962 | 0.67611 | 0.5859 | 107 | 0.82564 | 1.1265 | 0.72998 | 0.94543 | 0.82965 | 0.6869 | 0.10712 | 66.3645 | 0.74978 | 9.2966 | 6886.4208
270 | 0.66211 | 26 | 0.10878 | 0.032981 | 0.4218 | 0.69185 | 0.97192 | 113 | 0.32424 | 1.0068 | 0.67215 | 0.91949 | 0.73444 | 0.65381 | 0.89824 | 122.3741 | 0.95828 | 12.6713 | 6793.7132
271 | 0.08202 | 22 | 0.31804 | 0.056965 | 0.88232 | 0.75149 | 0.93599 | 112 | 0.28564 | 0.99999 | 0.061795 | 0.68611 | 0.5545 | 0.60376 | 0.28031 | 76.5309 | 0.89162 | 11.2464 | 5538.7007
272 | 0.41717 | 25 | 0.021336 | 0.014607 | 0.9268 | 0.76174 | 0.67844 | 108 | 0.2896 | 1.0007 | 0.78511 | 0.9729 | 0.53792 | 0.59918 | 0.8754 | 119.4298 | 0.93809 | 12.163 | 6380.9959
273 | 0.46333 | 25 | 0.44127 | 0.070532 | 0.92241 | 0.76061 | 0.37623 | 105 | 0.12684 | 0.96663 | 0.30512 | 0.79135 | 0.60423 | 0.61709 | 0.65295 | 98.9819 | 0.89516 | 11.3083 | 6066.8245
274 | 0.59939 | 26 | 0.07227 | 0.026883 | 0.79075 | 0.73531 | 0.16039 | 103 | 0.40277 | 1.0214 | 0.98164 | 1.1336 | 0.99546 | 0.79826 | 0.49236 | 88.2967 | 0.022472 | 2.9362 | 7084.0105
275 | 0.78199 | 27 | 0.23457 | 0.048433 | 0.2467 | 0.67024 | 0.69948 | 108 | 0.90631 | 1.1595 | 0.049995 | 0.67746 | 0.9898 | 0.78743 | 0.23666 | 74.3238 | 0.82655 | 10.2515 | 7002.1988
276 | 0.47822 | 25 | 0.59022 | 0.089124 | 0.3965 | 0.68905 | 0.62979 | 108 | 0.93529 | 1.1748 | 0.75709 | 0.95855 | 0.73397 | 0.65367 | 0.79801 | 111.0776 | 0.043773 | 3.3066 | 7048.3209
277 | 0.36656 | 24 | 0.043943 | 0.020963 | 0.22484 | 0.66706 | 0.73904 | 109 | 0.86931 | 1.1431 | 0.19267 | 0.75205 | 0.78575 | 0.67073 | 0.010826 | 55.2023 | 0.52833 | 7.1694 | 6195.5638
278 | 0.98104 | 29 | 0.44089 | 0.070488 | 0.9165 | 0.75913 | 0.64494 | 108 | 0.22431 | 0.98861 | 0.045569 | 0.67395 | 0.45192 | 0.57423 | 0.37375 | 81.466 | 0.1419 | 4.3525 | 6258.613
279 | 0.058622 | 22 | 0.73558 | 0.11094 | 0.87228 | 0.74946 | 0.55332 | 107 | 0.73399 | 1.0974 | 0.98607 | 1.1422 | 0.9996 | 0.81359 | 0.6193 | 96.5653 | 0.52407 | 7.1342 | 6893.8074
280 | 0.36979 | 24 | 0.029096 | 0.017057 | 0.72337 | 0.72562 | 0.80391 | 110 | 0.96828 | 1.1973 | 0.8264 | 0.99588 | 0.77968 | 0.66863 | 0.53744 | 91.1004 | 0.5426 | 7.2888 | 6757.7226
281 | 0.85096 | 27 | 0.50529 | 0.078175 | 0.72579 | 0.72594 | 0.3408 | 105 | 0.21537 | 0.98682 | 0.50739 | 0.85616 | 0.17939 | 0.47277 | 0.43406 | 84.8499 | 0.16409 | 4.5297 | 6105.9954
282 | 0.6418 | 26 | 0.12581 | 0.03547 | 0.64804 | 0.7161 | 0.065941 | 102 | 0.86914 | 1.143 | 0.080961 | 0.69857 | 0.81982 | 0.68311 | 0.58241 | 94.0362 | 0.30787 | 5.5144 | 6480.1197
283 | 0.92929 | 28 | 0.81705 | 0.12592 | 0.99189 | 0.78726 | 0.34807 | 105 | 0.48912 | 1.0386 | 0.20404 | 0.75648 | 0.38996 | 0.55473 | 0.982 | 138.3797 | 0.078099 | 3.7452 | 6658.1973
284 | 0.37203 | 24 | 0.87275 | 0.13821 | 0.24055 | 0.66936 | 0.15561 | 103 | 0.52372 | 1.0459 | 0.55095 | 0.87171 | 0.5146 | 0.59263 | 0.39929 | 82.8782 | 0.67024 | 8.4526 | 6313.8456
285 | 0.061688 | 22 | 0.41303 | 0.067301 | 0.44718 | 0.69457 | 0.71024 | 108 | 0.57329 | 1.0568 | 0.74807 | 0.95411 | 0.29538 | 0.5217 | 0.035082 | 59.3651 | 0.60487 | 7.8329 | 5759.6992
286 | 0.8733 | 27 | 0.49401 | 0.076794 | 0.007606 | 0.61233 | 0.81292 | 110 | 0.84815 | 1.1347 | 0.3962 | 0.81933 | 0.21116 | 0.48745 | 0.13095 | 68.0934 | 0.80462 | 9.9603 | 6570.7024
287 | 0.59362 | 25 | 0.097491 | 0.031224 | 0.79521 | 0.736 | 0.38341 | 105 | 0.85484 | 1.1373 | 0.090445 | 0.70418 | 0.47281 | 0.58049 | 0.10576 | 66.2604 | 0.82319 | 10.2057 | 6002.266
288 | 0.83091 | 27 | 0.29868 | 0.054949 | 0.75274 | 0.72968 | 0.45616 | 106 | 0.64776 | 1.0744 | 0.036768 | 0.66642 | 0.81038 | 0.67957 | 0.31791 | 78.4758 | 0.57855 | 7.5981 | 6411.8508
289 | 0.6505 | 26 | 0.8239 | 0.12732 | 0.8861 | 0.75227 | 0.17473 | 104 | 0.33114 | 1.0081 | 0.026253 | 0.65613 | 0.19687 | 0.48099 | 0.87278 | 119.1104 | 0.053015 | 3.4379 | 5998.3286
290 | 0.69224 | 26 | 0.59697 | 0.090041 | 0.56953 | 0.70721 | 0.30208 | 105 | 0.36058 | 1.0135 | 0.27808 | 0.78267 | 0.53705 | 0.59894 | 0.90306 | 123.0362 | 0.44818 | 6.5302 | 6458.339
291 | 0.15923 | 23 | 0.90137 | 0.14561 | 0.63529 | 0.71459 | 0.23001 | 104 | 0.37633 | 1.0164 | 0.052054 | 0.67903 | 0.76447 | 0.66349 | 0.40413 | 83.1495 | 0.23884 | 5.0526 | 5945.3896
292 | 0.32267 | 24 | 0.27203 | 0.05222 | 0.89088 | 0.75328 | 0.44286 | 106 | 0.85763 | 1.1384 | 0.67737 | 0.92173 | 0.87674 | 0.70678 | 0.80302 | 111.564 | 0.27772 | 5.31 | 6681.3401
293 | 0.90689 | 28 | 0.82028 | 0.12657 | 0.54447 | 0.70455 | 0.055906 | 102 | 0.86963 | 1.1432 | 0.58139 | 0.88303 | 0.075721 | 0.41225 | 0.69771 | 102.3848 | 0.14173 | 4.351 | 6637.936
294 | 0.21862 | 23 | 0.78817 | 0.12028 | 0.97206 | 0.77636 | 0.0093835 | 101 | 0.63614 | 1.0716 | 0.72496 | 0.94308 | 0.042926 | 0.38452 | 0.90831 | 123.7759 | 0.66188 | 8.3701 | 5897.5427
295 | 0.60922 | 26 | 0.62649 | 0.094145 | 0.96615 | 0.77398 | 0.45572 | 106 | 0.051889 | 0.94262 | 0.84462 | 1.0069 | 0.053345 | 0.39422 | 0.35824 | 80.623 | 0.62212 | 7.9911 | 5913.1931
296 | 0.26354 | 24 | 0.77846 | 0.11848 | 0.6455 | 0.7158 | 0.23309 | 104 | 0.37197 | 1.0156 | 0.75077 | 0.95543 | 0.85419 | 0.69686 | 0.24604 | 74.8014 | 0.71557 | 8.9192 | 6453.3468
297 | 0.38798 | 24 | 0.56029 | 0.085147 | 0.043406 | 0.62946 | 0.79978 | 110 | 0.15085 | 0.97266 | 0.53047 | 0.86431 | 0.88697 | 0.71158 | 0.98279 | 138.6396 | 0.99225 | 13.9961 | 6708.0821
298 | 0.88064 | 28 | 0.05172 | 0.022742 | 0.27088 | 0.6736 | 0.80707 | 110 | 0.46942 | 1.0345 | 0.23904 | 0.76936 | 0.81387 | 0.68087 | 0.58908 | 94.4852 | 0.015356 | 2.7739 | 6752.9822
299 | 0.57862 | 25 | 0.73815 | 0.11137 | 0.23238 | 0.66817 | 0.17368 | 104 | 0.61232 | 1.0658 | 0.95989 | 1.1019 | 0.96911 | 0.76332 | 0.69016 | 101.7944 | 0.7566 | 9.3749 | 7292.4488
300 | 0.45219 | 25 | 0.061671 | 0.024834 | 0.79979 | 0.73672 | 0.43718 | 106 | 0.40617 | 1.0221 | 0.7977 | 0.97965 | 0.29442 | 0.52134 | 0.57958 | 93.8473 | 0.95777 | 12.6568 | 6167.3607
301 | 0.8209 | 27 | 0.14712 | 0.038356 | 0.40022 | 0.68947 | 0.74062 | 109 | 0.050894 | 0.94221 | 0.61387 | 0.89558 | 0.2628 | 0.50912 | 0.35463 | 80.4281 | 0.80678 | 9.9882 | 6156.6175
302 | 0.88411 | 28 | 0.20885 | 0.0457 | 0.56886 | 0.70714 | 0.44865 | 106 | 0.54587 | 1.0507 | 0.23873 | 0.76926 | 0.47711 | 0.58177 | 0.30555 | 77.8308 | 0.39202 | 6.1097 | 6436.3771
303 | 0.1689 | 23 | 0.45984 | 0.072702 | 0.93322 | 0.76345 | 0.70797 | 108 | 0.13346 | 0.96835 | 0.75201 | 0.95604 | 0.70486 | 0.6448 | 0.10074 | 65.8694 | 0.73605 | 9.1422 | 5949.1482
304 | 0.66721 | 26 | 0.82314 | 0.12716 | 0.59978 | 0.71053 | 0.86613 | 111 | 0.61737 | 1.067 | 0.88747 | 1.0357 | 0.42294 | 0.56529 | 0.40084 | 82.9648 | 0.43373 | 6.4201 | 6823.1346
305 | 0.95279 | 28 | 0.15862 | 0.039827 | 0.043975 | 0.62966 | 0.63493 | 108 | 0.84148 | 1.1322 | 0.53467 | 0.86582 | 0.66772 | 0.6341 | 0.086833 | 64.7337 | 0.64377 | 8.1948 | 7008.6601
306 | 0.86764 | 27 | 0.018418 | 0.013571 | 0.87515 | 0.75003 | 0.6662 | 108 | 0.88508 | 1.1497 | 0.36066 | 0.80828 | 0.97216 | 0.76619 | 0.50435 | 89.0296 | 0.056214 | 3.4807 | 6970.8434
307 | 0.06045 | 22 | 0.24595 | 0.049594 | 0.61756 | 0.71254 | 0.58553 | 107 | 0.98489 | 1.2136 | 0.15694 | 0.73723 | 0.315 | 0.52894 | 0.10888 | 66.4983 | 0.4018 | 6.1815 | 5755.9742
308 | 0.20427 | 23 | 0.53944 | 0.082456 | 0.31078 | 0.67884 | 0.5916 | 107 | 0.092913 | 0.95703 | 0.81955 | 0.99189 | 0.26022 | 0.50809 | 0.97931 | 137.5423 | 0.59231 | 7.7199 | 6159.063
309 | 0.012174 | 21 | 0.96089 | 0.16575 | 0.049527 | 0.63147 | 0.35154 | 105 | 0.18599 | 0.98068 | 0.38433 | 0.8156 | 0.65004 | 0.62922 | 0.5979 | 95.084 | 0.42831 | 6.3791 | 5945.1729
310 | 0.31139 | 24 | 0.38678 | 0.064366 | 0.85784 | 0.74668 | 0.97609 | 113 | 0.73096 | 1.0966 | 0.8879 | 1.036 | 0.94473 | 0.74418 | 0.94688 | 130.0402 | 0.88352 | 11.1087 | 7101.2199
311 | 0.41208 | 25 | 0.79938 | 0.12242 | 0.78611 | 0.7346 | 0.32548 | 105 | 0.39854 | 1.0206 | 0.88879 | 1.0366 | 0.75238 | 0.65952 | 0.61869 | 96.5225 | 0.80091 | 9.9126 | 6759.821
312 | 0.84591 | 27 | 0.46084 | 0.07282 | 0.10565 | 0.64597 | 0.63613 | 108 | 0.1877 | 0.98105 | 0.57519 | 0.8807 | 0.60264 | 0.61667 | 0.28933 | 76.9929 | 0.46397 | 6.6523 | 6560.1876
313 | 0.42522 | 25 | 0.73926 | 0.11156 | 0.90399 | 0.75618 | 0.83508 | 110 | 0.70423 | 1.0891 | 0.9592 | 1.101 | 0.47841 | 0.58215 | 0.68073 | 101.0658 | 0.1804 | 4.6525 | 6827.2259
314 | 0.27468 | 24 | 0.19759 | 0.044452 | 0.26028 | 0.67215 | 0.64806 | 108 | 0.015011 | 0.92292 | 0.028725 | 0.65871 | 0.81051 | 0.67962 | 0.83726 | 115.0636 | 0.92392 | 11.855 | 5942.6451
315 | 0.078797 | 22 | 0.53144 | 0.081438 | 0.72352 | 0.72564 | 0.38307 | 105 | 0.73372 | 1.0974 | 0.92913 | 1.0696 | 0.89258 | 0.7143 | 0.4866 | 87.9476 | 0.47783 | 6.7609 | 6477.9857
316 | 0.192 | 23 | 0.88038 | 0.1401 | 0.82318 | 0.74053 | 0.57808 | 107 | 0.84806 | 1.1347 | 0.27894 | 0.78296 | 0.89237 | 0.7142 | 0.78349 | 109.703 | 0.756 | 9.3679 | 6573.7148
317 | 0.2338 | 23 | 0.97674 | 0.17358 | 0.57223 | 0.7075 | 0.2775 | 105 | 0.55411 | 1.0525 | 0.96147 | 1.1038 | 0.55452 | 0.60376 | 0.25585 | 75.2931 | 0.13448 | 4.2901 | 6506.4862
318 | 0.70523 | 26 | 0.17215 | 0.041491 | 0.492 | 0.6992 | 0.015045 | 101 | 0.58026 | 1.0584 | 0.41875 | 0.8265 | 0.72941 | 0.65225 | 0.41852 | 83.9613 | 0.40586 | 6.2115 | 6397.7576
319 | 0.43957 | 25 | 0.078033 | 0.027934 | 0.83072 | 0.74181 | 0.22258 | 104 | 0.087769 | 0.95542 | 0.57237 | 0.87964 | 0.21907 | 0.49093 | 0.59299 | 94.7501 | 0.77564 | 9.5994 | 5803.8923
320 | 0.98164 | 29 | 0.49431 | 0.076831 | 0.41663 | 0.69128 | 0.94709 | 112 | 0.83596 | 1.1302 | 0.24709 | 0.7722 | 0.91152 | 0.72407 | 0.71365 | 103.6573 | 0.82953 | 10.2925 | 7479.9335
321 | 0.89071 | 28 | 0.21854 | 0.046748 | 0.08931 | 0.64226 | 0.51277 | 106 | 0.19346 | 0.98229 | 0.023658 | 0.65328 | 0.85322 | 0.69645 | 0.775 | 108.9204 | 0.51653 | 7.0721 | 6596.9332
322 | 0.17709 | 23 | 0.83277 | 0.12917 | 0.46486 | 0.69642 | 0.27805 | 105 | 0.19937 | 0.98353 | 0.85096 | 1.0109 | 0.49855 | 0.58803 | 0.77019 | 108.4838 | 0.49124 | 6.8674 | 6310.6153
323 | 0.93404 | 28 | 0.62585 | 0.094054 | 0.57553 | 0.70786 | 0.95237 | 112 | 0.82017 | 1.1246 | 0.55693 | 0.87391 | 0.54868 | 0.60216 | 0.85172 | 116.6513 | 0.90837 | 11.5487 | 7245.556
324 | 0.28636 | 24 | 0.85354 | 0.13371 | 0.14459 | 0.65378 | 0.66066 | 108 | 0.1714 | 0.97745 | 0.45144 | 0.83716 | 0.39158 | 0.55526 | 0.27486 | 76.2536 | 0.2698 | 5.257 | 6060.9684
325 | 0.56692 | 25 | 0.97334 | 0.17172 | 0.77138 | 0.73238 | 0.99143 | 114 | 0.07736 | 0.95203 | 0.80969 | 0.98628 | 0.47564 | 0.58133 | 0.9825 | 138.5428 | 0.037152 | 3.2037 | 6760.4201
326 | 0.80768 | 27 | 0.45243 | 0.071831 | 0.96993 | 0.77548 | 0.18149 | 104 | 0.31282 | 1.0048 | 0.64068 | 0.90634 | 0.89434 | 0.71517 | 0.92377 | 126.0898 | 0.91107 | 11.5998 | 6909.6368
327 | 0.34261 | 24 | 0.81204 | 0.12491 | 0.82703 | 0.74118 | 0.39972 | 106 | 0.080275 | 0.95301 | 0.78129 | 0.97089 | 0.25195 | 0.50475 | 0.53165 | 90.7328 | 0.22167 | 4.9403 | 6014.8338
328 | 0.62339 | 26 | 0.12254 | 0.035005 | 0.33964 | 0.68242 | 0.67564 | 108 | 0.88303 | 1.1488 | 0.63956 | 0.90588 | 0.70987 | 0.64629 | 0.96884 | 134.7129 | 0.51516 | 7.0609 | 7079.6574
329 | 0.71196 | 26 | 0.26569 | 0.051577 | 0.27358 | 0.67397 | 0.24459 | 104 | 0.23092 | 0.9899 | 0.32698 | 0.79808 | 0.46355 | 0.57773 | 0.7707 | 108.53 | 0.92194 | 11.8145 | 6286.7705
330 | 0.75162 | 26 | 0.33799 | 0.059073 | 0.67957 | 0.71995 | 0.47064 | 106 | 0.10612 | 0.96094 | 0.30635 | 0.79173 | 0.85613 | 0.69768 | 0.18007 | 71.217 | 0.55538 | 7.3973 | 6231.2233
331 | 0.80834 | 27 | 0.15876 | 0.039845 | 0.84904 | 0.74505 | 0.52399 | 107 | 0.042928 | 0.93876 | 0.41784 | 0.82621 | 0.547 | 0.6017 | 0.69775 | 102.3884 | 0.54031 | 7.2696 | 6254.1605
332 | 0.30379 | 24 | 0.94236 | 0.15842 | 0.33681 | 0.68207 | 0.43514 | 106 | 0.49987 | 1.0408 | 0.1845 | 0.7488 | 0.79954 | 0.67561 | 0.89496 | 121.9321 | 0.36634 | 5.9239 | 6545.9071
333 | 0.022198 | 21 | 0.022599 | 0.015033 | 0.1486 | 0.65452 | 0.6036 | 107 | 0.1422 | 0.97055 | 0.3318 | 0.79954 | 0.1034 | 0.43117 | 0.26779 | 75.895 | 0.51485 | 7.0584 | 5131.0375
334 | 0.31418 | 24 | 0.11436 | 0.033817 | 0.01001 | 0.61415 | 0.42623 | 106 | 0.081925 | 0.95355 | 0.19148 | 0.75158 | 0.54309 | 0.60062 | 0.013745 | 55.862 | 0.8015 | 9.9201 | 5713.7992
335 | 0.77424 | 27 | 0.76037 | 0.11521 | 0.97749 | 0.77878 | 0.35242 | 105 | 0.10342 | 0.96016 | 0.31124 | 0.79326 | 0.48658 | 0.58455 | 0.32866 | 79.0418 | 0.5305 | 7.1875 | 6192.7038
336 | 0.96106 | 29 | 0.80252 | 0.12303 | 0.98396 | 0.78209 | 0.77422 | 109 | 0.6909 | 1.0855 | 0.058378 | 0.6837 | 0.30709 | 0.52605 | 0.73609 | 105.5107 | 0.10189 | 3.9935 | 6607.9852
337 | 0.82347 | 27 | 0.78797 | 0.12025 | 0.045715 | 0.63024 | 0.28845 | 105 | 0.67365 | 1.081 | 0.58354 | 0.88385 | 0.75825 | 0.66144 | 0.37399 | 81.4796 | 0.26407 | 5.2189 | 7028.3267
338 | 0.34169 | 24 | 0.004649 | 0.0068184 | 0.6241 | 0.71329 | 0.35432 | 105 | 0.92251 | 1.1677 | 0.21733 | 0.76149 | 0.18956 | 0.4776 | 0.37178 | 81.3588 | 0.65972 | 8.3489 | 5831.5852
339 | 0.53693 | 25 | 0.88093 | 0.14023 | 0.37024 | 0.68605 | 0.98696 | 114 | 0.052696 | 0.94295 | 0.26663 | 0.77887 | 0.9825 | 0.77734 | 0.33219 | 79.2287 | 0.076579 | 3.7282 | 6534.249
340 | 0.86188 | 27 | 0.20473 | 0.045247 | 0.39589 | 0.68898 | 0.97148 | 113 | 0.54113 | 1.0496 | 0.075293 | 0.69505 | 0.43636 | 0.56946 | 0.68256 | 101.2068 | 0.81065 | 10.0386 | 6412.7063
341 | 0.98042 | 29 | 0.70088 | 0.10527 | 0.2151 | 0.66559 | 0.33752 | 105 | 0.84969 | 1.1353 | 0.44198 | 0.83404 | 0.80255 | 0.6767 | 0.18487 | 71.4985 | 0.20409 | 4.8212 | 7286.7808
342 | 0.47955 | 25 | 0.3591 | 0.061339 | 0.54056 | 0.70414 | 0.8697 | 111 | 0.5289 | 1.047 | 0.33327 | 0.79998 | 0.074889 | 0.41163 | 0.72126 | 104.2779 | 0.75615 | 9.3697 | 5953.7279
343 | 0.42594 | 25 | 0.78891 | 0.12042 | 0.043791 | 0.62959 | 0.91009 | 111 | 0.60793 | 1.0648 | 0.9658 | 1.1094 | 0.92693 | 0.73283 | 0.083168 | 64.4194 | 0.046167 | 3.3418 | 7174.8738
344 | 0.090894 | 22 | 0.14767 | 0.038428 | 0.93763 | 0.76468 | 0.63558 | 108 | 0.68024 | 1.0827 | 0.88099 | 1.031 | 0.61476 | 0.61984 | 0.44068 | 85.2321 | 0.36764 | 5.9332 | 6075.9986
345 | 0.65488 | 26 | 0.0056249 | 0.0074999 | 0.61576 | 0.71234 | 0.26914 | 104 | 0.5064 | 1.0422 | 0.83139 | 0.99884 | 0.11942 | 0.44097 | 0.6446 | 98.3716 | 0.588 | 7.6815 | 6150.0337
346 | 0.17215 | 23 | 0.73528 | 0.11088 | 0.46821 | 0.69677 | 0.66401 | 108 | 0.14632 | 0.97156 | 0.54005 | 0.86775 | 0.9066 | 0.72144 | 0.93379 | 127.7166 | 0.23461 | 5.025 | 6435.8621
347 | 0.92096 | 28 | 0.48499 | 0.075701 | 0.13037 | 0.65106 | 0.83759 | 110 | 0.38608 | 1.0182 | 0.10257 | 0.71094 | 0.17976 | 0.47295 | 0.93723 | 128.3034 | 0.38593 | 6.0653 | 6464.2017
348 | 0.23733 | 23 | 0.0027203 | 0.0052157 | 0.9708 | 0.77583 | 0.67416 | 108 | 0.39539 | 1.02 | 0.40193 | 0.82114 | 0.00039431 | 0.3081 | 0.48793 | 88.0277 | 0.79656 | 9.8573 | 5181.8545
349 | 0.038679 | 21 | 0.57304 | 0.086824 | 0.31803 | 0.67975 | 0.54489 | 107 | 0.74068 | 1.0994 | 0.82308 | 0.99394 | 0.95387 | 0.75074 | 0.1986 | 72.2821 | 0.90878 | 11.5564 | 6333.6405
350 | 0.27455 | 24 | 0.51803 | 0.079753 | 0.6327 | 0.71429 | 0.073568 | 102 | 0.68494 | 1.084 | 0.83775 | 1.0027 | 0.33529 | 0.5362 | 0.037099 | 59.6306 | 0.83907 | 10.426 | 6135.1294
351 | 0.23001 | 23 | 0.52142 | 0.080177 | 0.36109 | 0.68498 | 0.82081 | 110 | 0.63686 | 1.0717 | 0.7675 | 0.96378 | 0.6891 | 0.64018 | 0.10355 | 66.0897 | 0.97293 | 13.1242 | 6317.6914
352 | 0.9121 | 28 | 0.90109 | 0.14553 | 0.39195 | 0.68854 | 0.26425 | 104 | 0.49815 | 1.0404 | 0.4176 | 0.82613 | 0.60128 | 0.61631 | 0.70819 | 103.2179 | 0.41143 | 6.2528 | 6933.5463
353 | 0.26067 | 24 | 0.93584 | 0.15613 | 0.032405 | 0.62546 | 0.69931 | 108 | 0.046164 | 0.9402 | 0.58113 | 0.88294 | 0.060404 | 0.40026 | 0.014057 | 55.9281 | 0.36535 | 5.9168 | 5710.4192
354 | 0.87071 | 27 | 0.32476 | 0.057672 | 0.88164 | 0.75135 | 0.31017 | 105 | 0.46191 | 1.033 | 0.94469 | 1.0848 | 0.16591 | 0.46615 | 0.77773 | 109.1708 | 0.57277 | 7.5475 | 6567.485
355 | 0.83936 | 27 | 0.5497 | 0.083772 | 0.34163 | 0.68266 | 0.71953 | 109 | 0.96655 | 1.1959 | 0.16625 | 0.74124 | 0.9308 | 0.73516 | 0.93716 | 128.2906 | 0.97541 | 13.2122 | 7434.6051
356 | 0.17754 | 23 | 0.38038 | 0.06366 | 0.21425 | 0.66546 | 0.04524 | 102 | 0.4259 | 1.0259 | 0.89848 | 1.0439 | 0.029623 | 0.37021 | 0.38554 | 82.1144 | 0.37357 | 5.9758 | 5699.8564
357 | 0.90569 | 28 | 0.39016 | 0.06474 | 0.31188 | 0.67898 | 0.81673 | 110 | 0.076009 | 0.95158 | 0.75651 | 0.95826 | 0.33828 | 0.53726 | 0.11824 | 67.1927 | 0.97454 | 13.1807 | 6500.8783
358 | 0.33226 | 24 | 0.058063 | 0.024096 | 0.55879 | 0.70606 | 0.46611 | 106 | 0.95077 | 1.1844 | 0.6021 | 0.89098 | 0.55166 | 0.60298 | 0.11312 | 66.8165 | 0.29036 | 5.3951 | 6287.1215
359 | 0.39073 | 24 | 0.8333 | 0.12928 | 0.084315 | 0.64106 | 0.48991 | 106 | 0.86849 | 1.1427 | 0.24033 | 0.76982 | 0.58655 | 0.61241 | 0.38947 | 82.3317 | 0.432 | 6.407 | 6463.4912
360 | 0.11967 | 22 | 0.8789 | 0.13973 | 0.28445 | 0.67542 | 0.24618 | 104 | 0.076618 | 0.95178 | 0.45869 | 0.83956 | 0.69811 | 0.64281 | 0.19639 | 72.158 | 0.94434 | 12.3101 | 5877.2588
361 | 0.060098 | 22 | 0.75713 | 0.11464 | 0.53119 | 0.70317 | 0.93661 | 112 | 0.11555 | 0.96359 | 0.87673 | 1.028 | 0.12832 | 0.44612 | 0.63841 | 97.9237 | 0.84154 | 10.4612 | 5865.9834
362 | 0.17335 | 23 | 0.43323 | 0.069604 | 0.68786 | 0.72099 | 0.81303 | 110 | 0.80079 | 1.118 | 0.61913 | 0.89766 | 0.87047 | 0.70394 | 0.47681 | 87.3589 | 0.86162 | 10.7585 | 6485.8896
363 | 0.67592 | 26 | 0.60671 | 0.091378 | 0.27412 | 0.67404 | 0.08021 | 102 | 0.18958 | 0.98146 | 0.55462 | 0.87306 | 0.39011 | 0.55478 | 0.85158 | 116.6362 | 0.93684 | 12.1346 | 6434.5807
364 | 0.38683 | 24 | 0.21631 | 0.04651 | 0.63125 | 0.71412 | 0.25551 | 104 | 0.29111 | 1.0009 | 0.068214 | 0.69047 | 0.50051 | 0.58859 | 0.42227 | 84.1746 | 0.084389 | 3.8142 | 5700.8379
365 | 0.5211 | 25 | 0.81738 | 0.12598 | 0.3778 | 0.68693 | 0.53074 | 107 | 0.45094 | 1.0308 | 0.49018 | 0.8502 | 0.90843 | 0.72241 | 0.46453 | 86.628 | 0.02 | 2.8832 | 6658.2412
366 | 0.6413 | 26 | 0.77657 | 0.11813 | 0.97961 | 0.7798 | 0.026505 | 101 | 0.20597 | 0.98491 | 0.086048 | 0.70162 | 0.62321 | 0.62205 | 0.95173 | 130.9728 | 0.42335 | 6.3418 | 6267.5795
367 | 0.67324 | 26 | 0.44935 | 0.071472 | 0.58944 | 0.70938 | 0.37728 | 105 | 0.20858 | 0.98544 | 0.24835 | 0.77263 | 0.13302 | 0.44878 | 0.6761 | 100.7123 | 0.54285 | 7.2909 | 5916.6017
368 | 0.67616 | 26 | 0.2938 | 0.054446 | 0.55794 | 0.70597 | 0.46276 | 106 | 0.68337 | 1.0836 | 0.30007 | 0.78976 | 0.89896 | 0.71749 | 0.50691 | 89.1875 | 0.3949 | 6.1307 | 6656.6176
369 | 0.98814 | 29 | 0.028207 | 0.016795 | 0.51424 | 0.70143 | 0.13676 | 103 | 0.50632 | 1.0422 | 0.91642 | 1.0584 | 0.15431 | 0.46024 | 0.83489 | 114.81 | 0.75262 | 9.329 | 6797.5557
370 | 0.57841 | 25 | 0.38928 | 0.064642 | 0.89439 | 0.75404 | 0.45616 | 106 | 0.42606 | 1.0259 | 0.44051 | 0.83356 | 0.6843 | 0.6388 | 0.32924 | 79.0727 | 0.38966 | 6.0924 | 6180.2301
371 | 0.33219 | 24 | 0.64567 | 0.096898 | 0.74864 | 0.7291 | 0.21431 | 104 | 0.37269 | 1.0157 | 0.90268 | 1.0472 | 0.48223 | 0.58327 | 0.76108 | 107.6695 | 0.86977 | 10.8854 | 6448.0571
372 | 0.22133 | 23 | 0.59662 | 0.089994 | 0.32038 | 0.68005 | 0.9224 | 112 | 0.66805 | 1.0796 | 0.82519 | 0.99517 | 0.21055 | 0.48718 | 0.92012 | 125.5235 | 0.47749 | 6.7583 | 6353.6824
373 | 0.059702 | 22 | 0.46888 | 0.073772 | 0.082653 | 0.64066 | 0.5359 | 107 | 0.31762 | 1.0056 | 0.24785 | 0.77246 | 0.2613 | 0.50852 | 0.9621 | 133.1397 | 0.38618 | 6.0671 | 5848.2971
374 | 0.60475 | 26 | 0.81541 | 0.12559 | 0.14379 | 0.65363 | 0.36386 | 105 | 0.27568 | 0.99823 | 0.51741 | 0.85967 | 0.13633 | 0.45062 | 0.73303 | 105.2529 | 0.57061 | 7.5287 | 6276.0697
375 | 0.8097 | 27 | 0.40357 | 0.066236 | 0.25357 | 0.67121 | 0.93692 | 112 | 0.27605 | 0.99829 | 0.05948 | 0.68448 | 0.363 | 0.54577 | 0.72732 | 104.7773 | 0.50614 | 6.9874 | 6281.8615
376 | 0.17886 | 23 | 0.56403 | 0.085635 | 0.57878 | 0.70822 | 0.30475 | 105 | 0.68922 | 1.0851 | 0.65975 | 0.91424 | 0.15443 | 0.4603 | 0.35257 | 80.3167 | 0.92641 | 11.907 | 5891.3968
377 | 0.8143 | 27 | 0.095593 | 0.030918 | 0.417 | 0.69132 | 0.2479 | 104 | 0.88609 | 1.1502 | 0.62294 | 0.89918 | 0.026729 | 0.36669 | 0.39798 | 82.8049 | 0.10929 | 4.0645 | 6164.4957
378 | 0.049826 | 22 | 0.8702 | 0.1376 | 0.034676 | 0.62633 | 0.69942 | 108 | 0.9241 | 1.1685 | 0.82603 | 0.99567 | 0.8554 | 0.69737 | 0.63556 | 97.7193 | 0.37901 | 6.0151 | 6831.2932
379 | 0.24015 | 23 | 0.72635 | 0.10939 | 0.52142 | 0.70217 | 0.28202 | 105 | 0.45591 | 1.0318 | 0.45887 | 0.83962 | 0.85377 | 0.69668 | 0.31564 | 78.3573 | 0.97625 | 13.2427 | 6226.1414
380 | 0.019489 | 21 | 0.67504 | 0.10126 | 0.72388 | 0.72569 | 0.7084 | 108 | 0.66619 | 1.0791 | 0.46164 | 0.84055 | 0.20929 | 0.48662 | 0.41396 | 83.7031 | 0.17848 | 4.6383 | 5610.8096
381 | 0.82247 | 27 | 0.23885 | 0.048872 | 0.71666 | 0.72472 | 0.94704 | 112 | 0.66027 | 1.0776 | 0.04308 | 0.6719 | 0.33065 | 0.53456 | 0.73443 | 105.3707 | 0.084238 | 3.8125 | 6301.0842
382 | 0.92582 | 28 | 0.15829 | 0.039785 | 0.0099361 | 0.6141 | 0.57858 | 107 | 0.084681 | 0.95444 | 0.41773 | 0.82618 | 0.2317 | 0.49635 | 0.67653 | 100.7457 | 0.19606 | 4.7652 | 6331.4416
383 | 0.70095 | 26 | 0.41263 | 0.067255 | 0.047412 | 0.63079 | 0.16361 | 104 | 0.049536 | 0.94164 | 0.54859 | 0.87085 | 0.43317 | 0.56848 | 0.61416 | 96.2056 | 0.043338 | 3.3001 | 6252.1491
384 | 0.48749 | 25 | 0.89177 | 0.14302 | 0.89742 | 0.75471 | 0.61598 | 107 | 0.85499 | 1.1374 | 0.79472 | 0.97804 | 0.23071 | 0.49593 | 0.56778 | 93.0644 | 0.95917 | 12.6961 | 6580.8733
385 | 0.90329 | 28 | 0.93275 | 0.15508 | 0.49872 | 0.69987 | 0.69014 | 108 | 0.97454 | 1.2028 | 0.30574 | 0.79154 | 0.65593 | 0.63084 | 0.64225 | 98.2012 | 0.59245 | 7.7211 | 7357.0982
386 | 0.81491 | 27 | 0.53452 | 0.081829 | 0.38648 | 0.68792 | 0.016921 | 101 | 0.413 | 1.0234 | 0.67449 | 0.9205 | 0.12883 | 0.44642 | 0.1929 | 71.96 | 0.96517 | 12.8722 | 6202.2869
387 | 0.18717 | 23 | 0.61072 | 0.091933 | 0.24592 | 0.67013 | 0.93492 | 112 | 0.92638 | 1.1697 | 0.46361 | 0.84121 | 0.91114 | 0.72387 | 0.37701 | 81.6449 | 0.45566 | 6.5878 | 6659.7827
388 | 0.14557 | 23 | 0.9218 | 0.15156 | 0.63396 | 0.71444 | 0.47151 | 106 | 0.49384 | 1.0395 | 0.62752 | 0.90101 | 0.13762 | 0.45133 | 0.6203 | 96.6358 | 0.94727 | 12.3817 | 6007.8726
389 | 0.21357 | 23 | 0.87299 | 0.13827 | 0.029719 | 0.62438 | 0.41403 | 106 | 0.06599 | 0.94806 | 0.30948 | 0.79271 | 0.7006 | 0.64354 | 0.29369 | 77.2174 | 0.51138 | 7.03 | 6017.8491
390 | 0.096683 | 22 | 0.55269 | 0.084158 | 0.081789 | 0.64044 | 0.7811 | 109 | 0.15497 | 0.97365 | 0.25907 | 0.77632 | 0.62298 | 0.62198 | 0.5548 | 92.2158 | 0.79917 | 9.8904 | 5854.9866
391 | 0.69175 | 26 | 0.37785 | 0.063382 | 0.42086 | 0.69174 | 0.054574 | 102 | 0.43208 | 1.0271 | 0.41834 | 0.82637 | 0.77366 | 0.66657 | 0.76068 | 107.6333 | 0.28094 | 5.3316 | 6544.5541
392 | 0.96403 | 29 | 0.8058 | 0.12367 | 0.52911 | 0.70295 | 0.87042 | 111 | 0.43675 | 1.028 | 0.6504 | 0.91034 | 0.49018 | 0.5856 | 0.95777 | 132.2041 | 0.80163 | 9.9219 | 7291.8215
393 | 0.057741 | 22 | 0.48035 | 0.075142 | 0.78717 | 0.73476 | 0.42197 | 106 | 0.6561 | 1.0765 | 0.87566 | 1.0273 | 0.64874 | 0.62887 | 0.37093 | 81.3121 | 0.94028 | 12.2138 | 6184.1214
394 | 0.29033 | 24 | 0.91026 | 0.14811 | 0.95139 | 0.76882 | 0.90585 | 111 | 0.12373 | 0.96581 | 0.76358 | 0.9618 | 0.42031 | 0.56446 | 0.16749 | 70.4628 | 0.45943 | 6.617 | 6132.6001
395 | 0.37155 | 24 | 0.86835 | 0.13715 | 0.41852 | 0.69149 | 0.0029625 | 100 | 0.14742 | 0.97183 | 0.93875 | 1.0788 | 0.011406 | 0.34357 | 0.25924 | 75.4634 | 0.64146 | 8.1728 | 5806.669
396 | 0.65507 | 26 | 0.73634 | 0.11106 | 0.38887 | 0.68819 | 0.81488 | 110 | 0.33671 | 1.0091 | 0.93427 | 1.0744 | 0.59805 | 0.61546 | 0.29885 | 77.4837 | 0.049016 | 3.3826 | 6810.9292
397 | 0.10965 | 22 | 0.047963 | 0.0219 | 0.7852 | 0.73446 | 0.70599 | 108 | 0.81153 | 1.1216 | 0.86066 | 1.0171 | 0.71634 | 0.64824 | 0.013569 | 55.8244 | 0.18333 | 4.674 | 6040.2292
398 | 0.53723 | 25 | 0.20034 | 0.044759 | 0.48771 | 0.69876 | 0.94998 | 112 | 0.58741 | 1.06 | 0.73351 | 0.9471 | 0.23131 | 0.49619 | 0.29006 | 77.0303 | 0.031062 | 3.1007 | 6173.6516
399 | 0.53365 | 25 | 0.079489 | 0.028194 | 0.17342 | 0.65889 | 0.5566 | 107 | 0.41141 | 1.0231 | 0.0031732 | 0.61951 | 0.88617 | 0.71119 | 0.31559 | 78.3544 | 0.58098 | 7.6194 | 6070.9577
400 | 0.57621 | 25 | 0.70863 | 0.10651 | 0.94684 | 0.76739 | 0.19774 | 104 | 0.88044 | 1.1477 | 0.78186 | 0.97119 | 0.97912 | 0.7734 | 0.72776 | 104.8136 | 0.36046 | 5.8819 | 7124.9189
401 | 0.83932 | 27 | 0.4765 | 0.07468 | 0.90135 | 0.75558 | 0.21961 | 104 | 0.80771 | 1.1203 | 0.48496 | 0.84842 | 0.73613 | 0.65434 | 0.74738 | 106.4726 | 0.30943 | 5.5251 | 6854.1719
402 | 0.97407 | 29 | 0.054374 | 0.023318 | 0.38925 | 0.68823 | 0.38137 | 105 | 0.99413 | 1.2273 | 0.079253 | 0.69752 | 0.88583 | 0.71103 | 0.33447 | 79.3495 | 0.60257 | 7.8121 | 7215.3168
403 | 0.34317 | 24 | 0.5288 | 0.081105 | 0.2505 | 0.67078 | 0.45266 | 106 | 0.7901 | 1.1145 | 0.4381 | 0.83277 | 0.20633 | 0.48529 | 0.12132 | 67.4155 | 0.20851 | 4.8517 | 5981.2666
404 | 0.81102 | 27 | 0.89017 | 0.1426 | 0.38668 | 0.68794 | 0.33142 | 105 | 0.16278 | 0.97548 | 0.91298 | 1.0555 | 0.28022 | 0.51594 | 0.27144 | 76.0797 | 0.29622 | 5.4349 | 6621.5982
405 | 0.96987 | 29 | 0.11881 | 0.034469 | 0.29644 | 0.677 | 0.18136 | 104 | 0.15532 | 0.97373 | 0.2391 | 0.76939 | 0.36138 | 0.54522 | 0.13662 | 68.4814 | 0.32995 | 5.6669 | 6240.0502
406 | 0.7976 | 27 | 0.17758 | 0.04214 | 0.2517 | 0.67095 | 0.71458 | 108 | 0.11338 | 0.963 | 0.24603 | 0.77182 | 0.90275 | 0.71943 | 0.071683 | 63.3868 | 0.63172 | 8.0807 | 6408.9922
407 | 0.42403 | 25 | 0.73033 | 0.11005 | 0.44674 | 0.69452 | 0.032343 | 102 | 0.77374 | 1.1093 | 0.34235 | 0.80271 | 0.31729 | 0.52978 | 0.97451 | 136.1747 | 0.39139 | 6.1051 | 6497.1474
408 | 0.013788 | 21 | 0.31877 | 0.057043 | 0.11274 | 0.64749 | 0.3928 | 105 | 0.4347 | 1.0276 | 0.10966 | 0.71471 | 0.72818 | 0.65186 | 0.34741 | 80.0397 | 0.9346 | 12.0842 | 5646.5883
409 | 0.62812 | 26 | 0.39465 | 0.065239 | 0.020406 | 0.6202 | 0.32003 | 105 | 0.8719 | 1.1441 | 0.61238 | 0.89499 | 0.097844 | 0.4276 | 0.33964 | 79.6248 | 0.73274 | 9.1056 | 6364.8929
410 | 0.76885 | 27 | 0.47641 | 0.07467 | 0.46703 | 0.69665 | 0.15913 | 103 | 0.42866 | 1.0264 | 0.98376 | 1.1376 | 0.95975 | 0.7553 | 0.14855 | 69.2712 | 0.52476 | 7.1399 | 7257.8804
411 | 0.032356 | 21 | 0.19965 | 0.044682 | 0.73128 | 0.72669 | 0.47893 | 106 | 0.67517 | 1.0814 | 0.64625 | 0.90863 | 0.73688 | 0.65458 | 0.19894 | 72.3014 | 0.32012 | 5.5987 | 5809.1231
412 | 0.57014 | 25 | 0.74591 | 0.11269 | 0.040077 | 0.62831 | 0.34613 | 105 | 0.40725 | 1.0223 | 0.45149 | 0.83717 | 0.70427 | 0.64462 | 0.066652 | 62.9085 | 0.57785 | 7.592 | 6385.0085
413 | 0.040224 | 21 | 0.26873 | 0.051885 | 0.71151 | 0.72404 | 0.42231 | 106 | 0.70327 | 1.0889 | 0.8013 | 0.98162 | 0.33841 | 0.5373 | 0.17339 | 70.8199 | 0.79824 | 9.8786 | 5717.5825
414 | 0.75202 | 26 | 0.35799 | 0.061218 | 0.12152 | 0.6493 | 0.49321 | 106 | 0.4787 | 1.0364 | 0.95883 | 1.1006 | 0.11368 | 0.43753 | 0.010019 | 55.0049 | 0.28277 | 5.3439 | 6259.0685
415 | 0.61185 | 26 | 0.59607 | 0.089918 | 0.65129 | 0.71649 | 0.8771 | 111 | 0.38192 | 1.0174 | 0.21568 | 0.76088 | 0.07237 | 0.40974 | 0.067547 | 62.9949 | 0.28243 | 5.3416 | 5782.6645
416 | 0.14318 | 23 | 0.75357 | 0.11402 | 0.019718 | 0.61986 | 0.91693 | 111 | 0.080708 | 0.95315 | 0.85529 | 1.0136 | 0.7734 | 0.66649 | 0.13451 | 68.3377 | 0.9524 | 12.5124 | 6356.151
417 | 0.44995 | 25 | 0.35823 | 0.061244 | 0.648 | 0.7161 | 0.58675 | 107 | 0.33195 | 1.0082 | 0.21648 | 0.76118 | 0.9413 | 0.74186 | 0.085979 | 64.6611 | 0.3857 | 6.0636 | 6230.4466
418 | 0.21986 | 23 | 0.21645 | 0.046524 | 0.31223 | 0.67902 | 0.72307 | 109 | 0.028421 | 0.93154 | 0.50692 | 0.856 | 0.50961 | 0.5912 | 0.47884 | 87.4801 | 0.025467 | 2.9966 | 5764.7398
419 | 0.067588 | 22 | 0.27833 | 0.05286 | 0.29777 | 0.67717 | 0.51791 | 106 | 0.34246 | 1.0101 | 0.50904 | 0.85674 | 0.45261 | 0.57443 | 0.77577 | 108.9912 | 0.49121 | 6.8672 | 5868.9282
420 | 0.054332 | 22 | 0.86351 | 0.13601 | 0.32714 | 0.68089 | 0.76539 | 109 | 0.84823 | 1.1348 | 0.12117 | 0.72059 | 0.6626 | 0.63268 | 0.25137 | 75.0687 | 0.60907 | 7.8711 | 6097.6383
421 | 0.82756 | 27 | 0.66818 | 0.10023 | 0.17046 | 0.65839 | 0.35087 | 105 | 0.89731 | 1.1552 | 0.98594 | 1.1419 | 0.2395 | 0.49963 | 0.96325 | 133.399 | 0.64481 | 8.2048 | 7353.5458
422 | 0.87523 | 28 | 0.67549 | 0.10133 | 0.049963 | 0.63161 | 0.20751 | 104 | 0.91304 | 1.1628 | 0.88119 | 1.0311 | 0.79188 | 0.67288 | 0.94296 | 129.3168 | 0.84342 | 10.4883 | 7878.4129
423 | 0.31035 | 24 | 0.18874 | 0.043444 | 0.11218 | 0.64737 | 0.64647 | 108 | 0.30047 | 1.0026 | 0.73484 | 0.94773 | 0.50409 | 0.58962 | 0.38303 | 81.9759 | 0.43242 | 6.4101 | 6178.5677
424 | 0.49644 | 25 | 0.86822 | 0.13712 | 0.72934 | 0.72643 | 0.42244 | 106 | 0.5269 | 1.0465 | 0.66212 | 0.91523 | 0.16438 | 0.46539 | 0.28052 | 76.5419 | 0.36467 | 5.9119 | 6146.0223
425 | 0.91469 | 28 | 0.86195 | 0.13565 | 0.54604 | 0.70472 | 0.92076 | 112 | 0.94992 | 1.1838 | 0.1149 | 0.71742 | 0.39743 | 0.55716 | 0.42263 | 84.1953 | 0.90942 | 11.5684 | 6962.0285
426 | 0.26955 | 24 | 0.67288 | 0.10094 | 0.42858 | 0.69258 | 0.16454 | 104 | 0.38462 | 1.018 | 0.13422 | 0.72691 | 0.024872 | 0.36433 | 0.66611 | 99.9581 | 0.82689 | 10.2561 | 5610.2721
427 | 0.76149 | 27 | 0.37447 | 0.063011 | 0.29374 | 0.67665 | 0.93129 | 112 | 0.59158 | 1.061 | 0.67815 | 0.92207 | 0.25827 | 0.50731 | 0.37163 | 81.3502 | 0.47465 | 6.7359 | 6554.3083
428 | 0.6636 | 26 | 0.96234 | 0.16639 | 0.76249 | 0.73108 | 0.084998 | 103 | 0.33019 | 1.0079 | 0.57553 | 0.88082 | 0.92 | 0.72878 | 0.24228 | 74.6111 | 0.064461 | 3.5856 | 6726.9074
429 | 0.16108 | 23 | 0.49124 | 0.076457 | 0.34681 | 0.68328 | 0.27263 | 105 | 0.80259 | 1.1186 | 0.98711 | 1.1444 | 0.4676 | 0.57894 | 0.077789 | 63.9454 | 0.29251 | 5.4097 | 6400.6482
430 | 0.16342 | 23 | 0.93897 | 0.15721 | 0.6581 | 0.71731 | 0.90797 | 111 | 0.31495 | 1.0052 | 0.90744 | 1.051 | 0.99248 | 0.79204 | 0.18246 | 71.3574 | 0.22077 | 4.9343 | 6746.7996
431 | 0.5049 | 25 | 0.35265 | 0.060643 | 0.73382 | 0.72704 | 0.21676 | 104 | 0.77191 | 1.1087 | 0.43309 | 0.83114 | 0.4453 | 0.57221 | 0.37533 | 81.5528 | 0.17202 | 4.5901 | 6216.5763
432 | 0.015304 | 21 | 0.50422 | 0.078044 | 0.88303 | 0.75163 | 0.54165 | 107 | 0.088198 | 0.95556 | 0.66958 | 0.9184 | 0.61349 | 0.61951 | 0.3762 | 81.6004 | 0.077469 | 3.7382 | 5621.5738
433 | 0.027699 | 21 | 0.92428 | 0.15234 | 0.072385 | 0.63805 | 0.9114 | 111 | 0.71497 | 1.0921 | 0.29142 | 0.787 | 0.15784 | 0.46206 | 0.27929 | 76.4789 | 0.8091 | 10.0183 | 5752.3146
434 | 0.7558 | 27 | 0.55455 | 0.084399 | 0.89829 | 0.7549 | 0.67275 | 108 | 0.4875 | 1.0382 | 0.52304 | 0.86167 | 0.97085 | 0.76494 | 0.88727 | 120.9225 | 0.79686 | 9.8612 | 7116.5497
435 | 0.25672 | 24 | 0.52139 | 0.080173 | 0.71293 | 0.72423 | 0.73104 | 109 | 0.57976 | 1.0582 | 0.66392 | 0.91599 | 0.24993 | 0.50393 | 0.49496 | 88.4548 | 0.66736 | 8.4241 | 6105.9152
436 | 0.04131 | 21 | 0.14851 | 0.038537 | 0.82106 | 0.74018 | 0.08253 | 102 | 0.35157 | 1.0118 | 0.36925 | 0.81092 | 0.31301 | 0.52822 | 0.85036 | 116.4997 | 0.61211 | 7.8989 | 5504.866
437 | 0.76291 | 27 | 0.56092 | 0.085228 | 0.25382 | 0.67125 | 0.60223 | 107 | 0.42435 | 1.0256 | 0.91799 | 1.0597 | 0.009211 | 0.33915 | 0.65719 | 99.2941 | 0.57293 | 7.5489 | 6335.264
438 | 0.72387 | 26 | 0.18929 | 0.043508 | 0.77516 | 0.73294 | 0.64337 | 108 | 0.99045 | 1.2211 | 0.23343 | 0.76737 | 0.34233 | 0.53867 | 0.94057 | 128.8873 | 0.7369 | 9.1516 | 6694.7758
439 | 0.36358 | 24 | 0.43103 | 0.069351 | 0.84265 | 0.7439 | 0.68683 | 108 | 0.16517 | 0.97603 | 0.54326 | 0.86892 | 0.27538 | 0.51406 | 0.9018 | 122.861 | 0.057781 | 3.5012 | 5995.7231
440 | 0.6699 | 26 | 0.61086 | 0.091953 | 0.50394 | 0.70039 | 0.0091487 | 101 | 0.42206 | 1.0251 | 0.033229 | 0.66315 | 0.30463 | 0.52515 | 0.24088 | 74.5399 | 0.0041037 | 2.4001 | 5859.4845
441 | 0.32807 | 24 | 0.53191 | 0.081498 | 0.34834 | 0.68347 | 0.174 | 104 | 0.5019 | 1.0412 | 0.026953 | 0.65687 | 0.43213 | 0.56816 | 0.40089 | 82.968 | 0.10171 | 3.9916 | 5810.2833
442 | 0.22703 | 23 | 0.25451 | 0.050452 | 0.99488 | 0.78988 | 0.95226 | 112 | 0.006542 | 0.91513 | 0.65576 | 0.91257 | 0.319 | 0.53039 | 0.87887 | 119.8587 | 0.90876 | 11.556 | 5820.7624
443 | 0.76953 | 27 | 0.79402 | 0.12139 | 0.50855 | 0.70086 | 0.7998 | 110 | 0.69287 | 1.0861 | 0.32963 | 0.79889 | 0.17076 | 0.46856 | 0.91396 | 124.5969 | 0.21244 | 4.8784 | 6617.9128
444 | 0.70579 | 26 | 0.48136 | 0.075264 | 0.67719 | 0.71965 | 0.46113 | 106 | 0.60057 | 1.0631 | 0.41577 | 0.82555 | 0.12507 | 0.44426 | 0.19003 | 71.7963 | 0.82571 | 10.24 | 6010.445
445 | 0.1874 | 23 | 0.39574 | 0.06536 | 0.72905 | 0.72639 | 0.77374 | 109 | 0.85699 | 1.1381 | 0.55509 | 0.87323 | 0.074358 | 0.41123 | 0.56447 | 92.8471 | 0.26007 | 5.1923 | 5840.5165
446 | 0.67614 | 26 | 0.095518 | 0.030906 | 0.78007 | 0.73368 | 0.62527 | 108 | 0.70576 | 1.0895 | 0.62755 | 0.90102 | 0.405 | 0.5596 | 0.61392 | 96.1893 | 0.65489 | 8.3019 | 6456.4708
447 | 0.35939 | 24 | 0.96084 | 0.16572 | 0.54186 | 0.70428 | 0.62822 | 108 | 0.71505 | 1.0921 | 0.85559 | 1.0138 | 0.53116 | 0.5973 | 0.85601 | 117.1375 | 0.34353 | 5.7619 | 6843.7667
448 | 0.36487 | 24 | 0.025004 | 0.015813 | 0.21385 | 0.6654 | 0.33944 | 105 | 0.1854 | 0.98056 | 0.25 | 0.7732 | 0.016948 | 0.3531 | 0.95611 | 131.856 | 0.8089 | 10.0157 | 5586.017
449 | 0.22971 | 23 | 0.89877 | 0.14489 | 0.89063 | 0.75323 | 0.62104 | 107 | 0.38968 | 1.0189 | 0.55469 | 0.87308 | 0.54748 | 0.60183 | 0.41444 | 83.7303 | 0.42769 | 6.3745 | 6088.9048
450 | 0.60838 | 26 | 0.64017 | 0.096101 | 0.57495 | 0.7078 | 0.096957 | 103 | 0.37963 | 1.017 | 0.55509 | 0.87323 | 0.72488 | 0.65085 | 0.92836 | 126.821 | 0.40937 | 6.2375 | 6720.0591
451 | 0.050437 | 22 | 0.84696 | 0.13224 | 0.64228 | 0.71542 | 0.94162 | 112 | 0.66234 | 1.0781 | 0.65753 | 0.91331 | 0.44728 | 0.57281 | 0.53971 | 91.2445 | 0.63474 | 8.1092 | 6176.2697
452 | 0.3213 | 24 | 0.52836 | 0.081049 | 0.74598 | 0.72872 | 0.86967 | 111 | 0.83861 | 1.1312 | 0.41489 | 0.82527 | 0.020383 | 0.35824 | 0.8667 | 118.3816 | 0.22188 | 4.9416 | 5965.9801
453 | 0.054497 | 22 | 0.74448 | 0.11245 | 0.89677 | 0.75456 | 0.24788 | 104 | 0.40508 | 1.0218 | 0.64036 | 0.90621 | 0.50605 | 0.59018 | 0.11155 | 66.6998 | 0.022656 | 2.94 | 5769.348
454 | 0.20344 | 23 | 0.95454 | 0.16307 | 0.84555 | 0.74442 | 0.3211 | 105 | 0.084195 | 0.95428 | 0.4101 | 0.82374 | 0.73792 | 0.6549 | 0.13828 | 68.593 | 0.99824 | 14.5217 | 5988.9532
455 | 0.34392 | 24 | 0.15545 | 0.039427 | 0.98085 | 0.78043 | 0.69095 | 108 | 0.89226 | 1.1529 | 0.090561 | 0.70425 | 0.39467 | 0.55627 | 0.080822 | 64.2146 | 0.69285 | 8.681 | 5828.049
456 | 0.73792 | 26 | 0.032532 | 0.018037 | 0.29364 | 0.67663 | 0.33252 | 105 | 0.64993 | 1.075 | 0.79944 | 0.9806 | 0.28845 | 0.51908 | 0.39793 | 82.8024 | 0.073656 | 3.6949 | 6365.9945
457 | 0.73732 | 26 | 0.93479 | 0.15577 | 0.29959 | 0.67741 | 0.79437 | 109 | 0.53096 | 1.0474 | 0.27294 | 0.78098 | 0.20249 | 0.48356 | 0.40834 | 83.3857 | 0.29027 | 5.3945 | 6306.1192
458 | 0.5075 | 25 | 0.87896 | 0.13974 | 0.26903 | 0.67335 | 0.066201 | 102 | 0.20002 | 0.98367 | 0.99191 | 1.1559 | 0.51011 | 0.59135 | 0.83974 | 115.331 | 0.43381 | 6.4207 | 6859.0477
459 | 0.21722 | 23 | 0.55881 | 0.084954 | 0.49861 | 0.69986 | 0.053727 | 102 | 0.60807 | 1.0648 | 0.43513 | 0.8318 | 0.8137 | 0.68081 | 0.9551 | 131.6497 | 0.64713 | 8.227 | 6407.4517
460 | 0.97656 | 29 | 0.25936 | 0.050939 | 0.293 | 0.67655 | 0.44637 | 106 | 0.45051 | 1.0307 | 0.98925 | 1.1492 | 0.91861 | 0.728 | 0.93468 | 127.8667 | 0.56929 | 7.5172 | 7870.7259
461 | 0.18953 | 23 | 0.0039486 | 0.0062838 | 0.18231 | 0.66038 | 0.12993 | 103 | 0.71905 | 1.0932 | 0.66397 | 0.91602 | 0.071121 | 0.40879 | 0.074067 | 63.6076 | 0.21888 | 4.9217 | 5544.0957
462 | 0.17625 | 23 | 0.57548 | 0.087148 | 0.70925 | 0.72374 | 0.85712 | 110 | 0.79823 | 1.1171 | 0.97323 | 1.1199 | 0.53475 | 0.5983 | 0.58833 | 94.4342 | 0.77108 | 9.5448 | 6613.9674
463 | 0.13424 | 23 | 0.73772 | 0.1113 | 0.47679 | 0.69765 | 0.94528 | 112 | 0.99754 | 1.2353 | 0.0059663 | 0.62676 | 0.56467 | 0.60653 | 0.93946 | 128.6912 | 0.042986 | 3.2948 | 6477.9775
464 | 0.64556 | 26 | 0.81367 | 0.12523 | 0.5876 | 0.70918 | 0.034859 | 102 | 0.85823 | 1.1386 | 0.40921 | 0.82345 | 0.79602 | 0.67435 | 0.29895 | 77.4891 | 0.46184 | 6.6357 | 6776.9111
465 | 0.17556 | 23 | 0.52077 | 0.080096 | 0.51323 | 0.70133 | 0.45126 | 106 | 0.78302 | 1.1122 | 0.37886 | 0.8139 | 0.12728 | 0.44553 | 0.63069 | 97.3707 | 0.86057 | 10.7425 | 5876.3905
466 | 0.3068 | 24 | 0.77632 | 0.11808 | 0.58575 | 0.70898 | 0.017729 | 101 | 0.44066 | 1.0288 | 0.39722 | 0.81965 | 0.65092 | 0.62946 | 0.22613 | 73.7766 | 0.67212 | 8.4713 | 6114.7695
467 | 0.31713 | 24 | 0.4663 | 0.073465 | 0.14896 | 0.65458 | 0.39208 | 105 | 0.558 | 1.0533 | 0.771 | 0.96556 | 0.46601 | 0.57847 | 0.94832 | 130.3122 | 0.74059 | 9.1929 | 6566.4575
468 | 0.017124 | 21 | 0.0027888 | 0.0052809 | 0.27242 | 0.67381 | 0.84606 | 110 | 0.06619 | 0.94813 | 0.22072 | 0.76275 | 0.33666 | 0.53669 | 0.78609 | 109.9458 | 0.070186 | 3.6545 | 5369.8018
469 | 0.48581 | 25 | 0.2443 | 0.049427 | 0.76472 | 0.7314 | 0.88129 | 111 | 0.72992 | 1.0963 | 0.07773 | 0.69658 | 0.1514 | 0.45872 | 0.56387 | 92.8076 | 0.44277 | 6.4889 | 5888.9896
470 | 0.069069 | 22 | 0.94199 | 0.15828 | 0.56229 | 0.70644 | 0.40782 | 106 | 0.95183 | 1.1851 | 0.40097 | 0.82083 | 0.74517 | 0.6572 | 0.11723 | 67.1198 | 0.93952 | 12.196 | 6335.357
471 | 0.36542 | 24 | 0.94564 | 0.15962 | 0.11983 | 0.64896 | 0.64395 | 108 | 0.94761 | 1.1823 | 0.98215 | 1.1346 | 0.079064 | 0.4147 | 0.19881 | 72.2941 | 0.27086 | 5.2641 | 6568.7199
472 | 0.96268 | 29 | 0.69895 | 0.10497 | 0.80795 | 0.73802 | 0.20493 | 104 | 0.16645 | 0.97633 | 0.69552 | 0.92968 | 0.84102 | 0.69142 | 0.45739 | 86.2065 | 0.32031 | 5.6 | 7012.083
473 | 0.74667 | 26 | 0.44096 | 0.070496 | 0.40573 | 0.69008 | 0.97666 | 113 | 0.58333 | 1.0591 | 0.22538 | 0.76445 | 0.20112 | 0.48294 | 0.53818 | 91.1472 | 0.28063 | 5.3295 | 6188.4046
474 | 0.37326 | 24 | 0.10466 | 0.032352 | 0.14987 | 0.65475 | 0.12091 | 103 | 0.00083341 | 0.9054 | 0.060006 | 0.68486 | 0.75542 | 0.66051 | 0.28832 | 76.941 | 0.41673 | 6.2922 | 5632.7278
475 | 0.71396 | 26 | 0.28578 | 0.053621 | 0.28024 | 0.67487 | 0.61491 | 107 | 0.42339 | 1.0254 | 0.90433 | 1.0485 | 0.45294 | 0.57453 | 0.68679 | 101.5325 | 0.64017 | 8.1605 | 6709.5849
476 | 0.68041 | 26 | 0.11971 | 0.034599 | 0.17362 | 0.65893 | 0.8781 | 111 | 0.36288 | 1.0139 | 0.11594 | 0.71795 | 0.09394 | 0.42503 | 0.3661 | 81.0488 | 0.20798 | 4.848 | 5784.4366
477 | 0.51015 | 25 | 0.8737 | 0.13844 | 0.24331 | 0.66976 | 0.45902 | 106 | 0.81059 | 1.1213 | 0.96447 | 1.1077 | 0.11255 | 0.43685 | 0.099893 | 65.8029 | 0.9976 | 14.4415 | 6539.0207
478 | 0.34408 | 24 | 0.71562 | 0.10763 | 0.67362 | 0.71921 | 0.76539 | 109 | 0.93222 | 1.173 | 0.5842 | 0.8841 | 0.1677 | 0.46705 | 0.27226 | 76.1212 | 0.50052 | 6.942 | 6202.7592
479 | 0.32327 | 24 | 0.29847 | 0.054928 | 0.43756 | 0.69355 | 0.23841 | 104 | 0.31931 | 1.0059 | 0.29163 | 0.78707 | 0.97732 | 0.77143 | 0.36459 | 80.9667 | 0.13329 | 4.28 | 6233.5088
480 | 0.73845 | 26 | 0.034369 | 0.018539 | 0.36512 | 0.68545 | 0.2554 | 104 | 0.49299 | 1.0394 | 0.98175 | 1.1338 | 0.80027 | 0.67587 | 0.8134 | 112.5896 | 0.65193 | 8.2733 | 7047.4496
481 | 0.74018 | 26 | 0.26322 | 0.051328 | 0.57318 | 0.70761 | 0.38218 | 105 | 0.15544 | 0.97376 | 0.27418 | 0.78139 | 0.372 | 0.5488 | 0.85327 | 116.8265 | 0.16501 | 4.5368 | 6137.3066
482 | 0.19881 | 23 | 0.49351 | 0.076733 | 0.27394 | 0.67402 | 0.51148 | 106 | 0.15197 | 0.97293 | 0.1146 | 0.71727 | 0.62542 | 0.62263 | 0.12235 | 67.4892 | 0.47503 | 6.7389 | 5685.786
483 | 0.4644 | 25 | 0.21419 | 0.04628 | 0.64494 | 0.71573 | 0.54034 | 107 | 0.66115 | 1.0778 | 0.29484 | 0.7881 | 0.78779 | 0.67144 | 0.13966 | 68.6854 | 0.84594 | 10.5247 | 6293.695
484 | 0.3624 | 24 | 0.033075 | 0.018187 | 0.71458 | 0.72445 | 0.95672 | 112 | 0.093809 | 0.9573 | 0.64453 | 0.90792 | 0.10429 | 0.43174 | 0.080544 | 64.1901 | 0.25228 | 5.1408 | 5508.0114
485 | 0.80725 | 27 | 0.52386 | 0.080484 | 0.87809 | 0.75062 | 0.06328 | 102 | 0.5363 | 1.0486 | 0.059193 | 0.68428 | 0.15918 | 0.46275 | 0.30788 | 77.9521 | 0.28054 | 5.3289 | 5872.2012
486 | 0.14204 | 23 | 0.37728 | 0.06332 | 0.47752 | 0.69773 | 0.20552 | 104 | 0.76644 | 1.107 | 0.70123 | 0.93222 | 0.40505 | 0.55962 | 0.95764 | 132.1767 | 0.0066388 | 2.5088 | 6328.8844
487 | 0.72952 | 26 | 0.32269 | 0.057455 | 0.24944 | 0.67063 | 0.67024 | 108 | 0.68058 | 1.0828 | 0.73071 | 0.94578 | 0.86261 | 0.70047 | 0.87717 | 119.6487 | 0.89968 | 11.3886 | 7130.1136
488 | 0.98748 | 29 | 0.36609 | 0.062097 | 0.83558 | 0.74265 | 0.84413 | 110 | 0.80388 | 1.119 | 0.50261 | 0.85449 | 0.91275 | 0.72474 | 0.097662 | 65.6255 | 0.38243 | 6.0398 | 7231.2918
489 | 0.30423 | 24 | 0.13954 | 0.037356 | 0.21387 | 0.6654 | 0.14334 | 103 | 0.93949 | 1.1772 | 0.18784 | 0.75014 | 0.16631 | 0.46635 | 0.14123 | 68.7906 | 0.29724 | 5.4418 | 5844.1085
490 | 0.9923 | 29 | 0.81573 | 0.12565 | 0.45087 | 0.69496 | 0.29957 | 105 | 0.60907 | 1.065 | 0.4905 | 0.85031 | 0.86411 | 0.70112 | 0.19661 | 72.1701 | 0.42223 | 6.3334 | 7194.7808
491 | 0.38451 | 24 | 0.33594 | 0.058856 | 0.17763 | 0.6596 | 0.16578 | 104 | 0.40293 | 1.0214 | 0.21711 | 0.76141 | 0.56521 | 0.60668 | 0.60231 | 95.3858 | 0.18458 | 4.6831 | 6033.8197
492 | 0.7367 | 26 | 0.52022 | 0.080027 | 0.9316 | 0.76301 | 0.37468 | 105 | 0.42496 | 1.0257 | 0.51034 | 0.85719 | 0.64399 | 0.62758 | 0.46557 | 86.6895 | 0.84397 | 10.4963 | 6394.9517
493 | 0.21613 | 23 | 0.73045 | 0.11008 | 0.63872 | 0.715 | 0.92599 | 112 | 0.36093 | 1.0135 | 0.931 | 1.0713 | 0.63192 | 0.62435 | 0.65168 | 98.8886 | 0.86145 | 10.756 | 6510.6949
494 | 0.74605 | 26 | 0.55206 | 0.084077 | 0.64398 | 0.71562 | 0.01128 | 101 | 0.16273 | 0.97547 | 0.083498 | 0.7001 | 0.84396 | 0.69261 | 0.29748 | 77.413 | 0.31739 | 5.5799 | 6130.1455
495 | 0.38 | 24 | 0.75325 | 0.11396 | 0.69573 | 0.72199 | 0.25382 | 104 | 0.29305 | 1.0013 | 0.2766 | 0.78219 | 0.44343 | 0.57164 | 0.5957 | 94.9345 | 0.030348 | 3.0879 | 5981.8135
496 | 0.52508 | 25 | 0.67199 | 0.1008 | 0.46751 | 0.6967 | 0.085419 | 103 | 0.48875 | 1.0385 | 0.014606 | 0.64187 | 0.3883 | 0.55419 | 0.31068 | 78.0978 | 0.87136 | 10.9106 | 5903.8162
497 | 0.59965 | 26 | 0.46596 | 0.073425 | 0.81412 | 0.73903 | 0.28345 | 105 | 0.52371 | 1.0459 | 0.50447 | 0.85514 | 0.25369 | 0.50546 | 0.052805 | 61.4897 | 0.28679 | 5.371 | 6034.2897
498 | 0.83212 | 27 | 0.4839 | 0.07557 | 0.14867 | 0.65453 | 0.13332 | 103 | 0.68217 | 1.0832 | 0.87014 | 1.0235 | 0.71885 | 0.649 | 0.086075 | 64.6692 | 0.48876 | 6.8477 | 6985.0689
499 | 0.22425 | 23 | 0.010851 | 0.010417 | 0.3177 | 0.67971 | 0.14547 | 103 | 0.38141 | 1.0173 | 0.054655 | 0.68099 | 0.067523 | 0.406 | 0.15167 | 69.4727 | 0.63223 | 8.0856 | 5166.1194
500 | 0.5172 | 25 | 0.17475 | 0.041803 | 0.60508 | 0.71113 | 0.9325 | 112 | 0.9087 | 1.1606 | 0.55716 | 0.87399 | 0.53468 | 0.59828 | 0.59803 | 95.0927 | 0.11801 | 4.1453 | 6602.4553
501 | 0.037196 | 21 | 0.37174 | 0.062713 | 0.22221 | 0.66666 | 0.16112 | 103 | 0.5918 | 1.061 | 0.92988 | 1.0703 | 0.62856 | 0.62345 | 0.044764 | 60.5788 | 0.029783 | 3.0778 | 5919.6762
502 | 0.73783 | 26 | 0.27375 | 0.052394 | 0.73814 | 0.72763 | 0.13064 | 103 | 0.81179 | 1.1217 | 0.14973 | 0.73405 | 0.72569 | 0.6511 | 0.064353 | 62.6839 | 0.047428 | 3.36 | 6281.2101
503 | 0.8242 | 27 | 0.81633 | 0.12577 | 0.43046 | 0.69279 | 0.85665 | 110 | 0.22813 | 0.98936 | 0.9417 | 1.0817 | 0.92012 | 0.72886 | 0.3011 | 77.6002 | 0.4486 | 6.5335 | 7255.2257
504 | 0.35923 | 24 | 0.32014 | 0.057186 | 0.13253 | 0.65148 | 0.34046 | 105 | 0.10703 | 0.9612 | 0.72772 | 0.94437 | 0.39186 | 0.55535 | 0.63077 | 97.3766 | 0.18416 | 4.68 | 6077.6361
505 | 0.23696 | 23 | 0.08052 | 0.028376 | 0.65835 | 0.71734 | 0.97786 | 113 | 0.37751 | 1.0166 | 0.29602 | 0.78847 | 0.028378 | 0.36872 | 0.38819 | 82.261 | 0.63368 | 8.0992 | 5375.7404
506 | 0.12462 | 22 | 0.94119 | 0.158 | 0.18301 | 0.6605 | 0.4159 | 106 | 0.43443 | 1.0275 | 0.54641 | 0.87006 | 0.59428 | 0.61446 | 0.62331 | 96.8474 | 0.17152 | 4.5864 | 6174.4279
507 | 0.24159 | 23 | 0.72005 | 0.10836 | 0.36815 | 0.68581 | 0.25809 | 104 | 0.54204 | 1.0498 | 0.2961 | 0.7885 | 0.47264 | 0.58044 | 0.25675 | 75.3383 | 0.67595 | 8.5095 | 5935.8885
508 | 0.098223 | 22 | 0.34207 | 0.059508 | 0.96696 | 0.7743 | 0.25873 | 104 | 0.85501 | 1.1374 | 0.89631 | 1.0422 | 0.95494 | 0.75154 | 0.79274 | 110.5733 | 0.53754 | 7.2463 | 6582.8213
509 | 0.97648 | 29 | 0.811 | 0.1247 | 0.04401 | 0.62967 | 0.38228 | 105 | 0.038061 | 0.9365 | 0.992 | 1.1562 | 0.32226 | 0.53157 | 0.29859 | 77.4701 | 0.28004 | 5.3255 | 7050.2301
510 | 0.049488 | 22 | 0.092684 | 0.030444 | 0.16029 | 0.65662 | 0.66312 | 108 | 0.74803 | 1.1015 | 0.43561 | 0.83196 | 0.74799 | 0.65811 | 0.85508 | 117.032 | 0.5704 | 7.5269 | 6220.5113
511 | 0.47701 | 25 | 0.36017 | 0.061455 | 0.016944 | 0.61841 | 0.33839 | 105 | 0.7326 | 1.097 | 0.2664 | 0.77879 | 0.71233 | 0.64703 | 0.79787 | 111.0647 | 0.8972 | 11.3444 | 6638.9713
512 | 0.11012 | 22 | 0.56076 | 0.085207 | 0.43988 | 0.6938 | 0.92073 | 112 | 0.97114 | 1.1997 | 0.65417 | 0.9119 | 0.32041 | 0.5309 | 0.031746 | 58.9087 | 0.98924 | 13.8175 | 6105.9816
513 | 0.089634 | 22 | 0.032869 | 0.01813 | 0.60666 | 0.71131 | 0.99804 | 114 | 0.14543 | 0.97134 | 0.76364 | 0.96183 | 0.23772 | 0.49889 | 0.52772 | 90.4847 | 0.89503 | 11.306 | 5672.9535
514 | 0.80274 | 27 | 0.60044 | 0.090516 | 0.59455 | 0.70995 | 0.46987 | 106 | 0.071714 | 0.9501 | 0.54366 | 0.86906 | 0.76439 | 0.66347 | 0.032834 | 59.0601 | 0.049614 | 3.391 | 6392.9643
515 | 0.55006 | 25 | 0.14527 | 0.038114 | 0.99458 | 0.78959 | 0.95679 | 112 | 0.78314 | 1.1122 | 0.5733 | 0.87999 | 0.021996 | 0.3605 | 0.52013 | 90.0084 | 0.40745 | 6.2232 | 5837.7641
516 | 0.42657 | 25 | 0.247 | 0.049699 | 0.566 | 0.70683 | 0.39891 | 106 | 0.99503 | 1.2291 | 0.72285 | 0.94209 | 0.10809 | 0.43411 | 0.32934 | 79.0777 | 0.28733 | 5.3746 | 6305.2185
517 | 0.38484 | 24 | 0.67124 | 0.10069 | 0.5084 | 0.70084 | 0.77675 | 109 | 0.38327 | 1.0177 | 0.11599 | 0.71798 | 0.3177 | 0.52993 | 0.89491 | 121.9258 | 0.83043 | 10.3049 | 6071.7893
518 | 0.53654 | 25 | 0.025682 | 0.016026 | 0.013593 | 0.61649 | 0.45873 | 106 | 0.009594 | 0.91832 | 0.36211 | 0.80873 | 0.94737 | 0.74602 | 0.63638 | 97.778 | 0.65692 | 8.3217 | 6298.6769
519 | 0.23796 | 23 | 0.83635 | 0.12993 | 0.10312 | 0.64541 | 0.97122 | 113 | 0.13065 | 0.96762 | 0.3631 | 0.80903 | 0.74928 | 0.65852 | 0.81303 | 112.553 | 0.1807 | 4.6547 | 6300.7166
520 | 0.084875 | 22 | 0.30222 | 0.055316 | 0.17048 | 0.65839 | 0.92515 | 112 | 0.082556 | 0.95375 | 0.30521 | 0.79138 | 0.8472 | 0.69394 | 0.11579 | 67.0137 | 0.94188 | 12.2512 | 5795.5889
521 | 0.32143 | 24 | 0.68355 | 0.10257 | 0.86259 | 0.74758 | 0.25316 | 104 | 0.66457 | 1.0787 | 0.41366 | 0.82487 | 0.35684 | 0.54368 | 0.07754 | 63.923 | 0.77261 | 9.563 | 5952.8712
522 | 0.87102 | 27 | 0.96927 | 0.16964 | 0.21008 | 0.66482 | 0.033063 | 102 | 0.19926 | 0.98351 | 0.46853 | 0.84286 | 0.99962 | 0.81372 | 0.084081 | 64.4984 | 0.69355 | 8.6882 | 7013.4684
523 | 0.47321 | 25 | 0.87446 | 0.13863 | 0.53188 | 0.70324 | 0.1134 | 103 | 0.96078 | 1.1914 | 0.28553 | 0.7851 | 0.66057 | 0.63212 | 0.49539 | 88.4813 | 0.75474 | 9.3535 | 6713.0879
524 | 0.26489 | 24 | 0.29021 | 0.054076 | 0.45502 | 0.6954 | 0.2543 | 104 | 0.081855 | 0.95353 | 0.46769 | 0.84257 | 0.29838 | 0.52282 | 0.38726 | 82.2097 | 0.3202 | 5.5993 | 5722.5449
525 | 0.15904 | 23 | 0.29975 | 0.055061 | 0.69633 | 0.72207 | 0.90594 | 111 | 0.29107 | 1.0009 | 0.36321 | 0.80907 | 0.84804 | 0.69429 | 0.88299 | 120.3759 | 0.36779 | 5.9343 | 6212.9946
526 | 0.082477 | 22 | 0.44646 | 0.071136 | 0.75753 | 0.73036 | 0.60929 | 107 | 0.53142 | 1.0475 | 0.42821 | 0.82956 | 0.012807 | 0.34616 | 0.7133 | 103.6296 | 0.61618 | 7.9362 | 5443.6407
527 | 0.69935 | 26 | 0.68491 | 0.10277 | 0.76484 | 0.73142 | 0.092404 | 103 | 0.1888 | 0.98129 | 0.96963 | 1.1146 | 0.17565 | 0.47096 | 0.95106 | 130.8423 | 0.0074844 | 2.5403 | 6566.0313
528 | 0.43331 | 25 | 0.96459 | 0.16741 | 0.60087 | 0.71065 | 0.64218 | 108 | 0.92562 | 1.1693 | 0.90507 | 1.0491 | 0.19165 | 0.47858 | 0.13203 | 68.168 | 0.4173 | 6.2965 | 6667.264
529 | 0.72495 | 26 | 0.66948 | 0.10042 | 0.25098 | 0.67085 | 0.77727 | 109 | 0.81856 | 1.124 | 0.93163 | 1.0719 | 0.35616 | 0.54345 | 0.073511 | 63.5565 | 0.31466 | 5.561 | 6816.4469
530 | 0.94581 | 28 | 0.48843 | 0.076116 | 0.23524 | 0.66859 | 0.0098506 | 101 | 0.43313 | 1.0273 | 0.053205 | 0.6799 | 0.85173 | 0.69582 | 0.23376 | 74.1744 | 0.46498 | 6.6601 | 6538.7582
531 | 0.56162 | 25 | 0.12409 | 0.035226 | 0.80755 | 0.73796 | 0.88792 | 111 | 0.56447 | 1.0548 | 0.85816 | 1.0155 | 0.14247 | 0.45397 | 0.78288 | 109.647 | 0.70622 | 8.8201 | 6266.9349
532 | 0.87962 | 28 | 0.46683 | 0.073528 | 0.2762 | 0.67432 | 0.91903 | 112 | 0.39736 | 1.0204 | 0.10075 | 0.70996 | 0.19456 | 0.47993 | 0.97317 | 135.8157 | 0.26119 | 5.1998 | 6505.4835
533 | 0.054527 | 22 | 0.34159 | 0.059457 | 0.83654 | 0.74282 | 0.47241 | 106 | 0.6953 | 1.0867 | 0.5268 | 0.863 | 0.86718 | 0.70247 | 0.56103 | 92.6214 | 0.58263 | 7.634 | 6124.7307
534 | 0.61294 | 26 | 0.5414 | 0.082705 | 0.98287 | 0.78149 | 0.72706 | 109 | 0.085896 | 0.95483 | 0.34659 | 0.804 | 0.95699 | 0.75312 | 0.21571 | 73.222 | 0.11745 | 4.1402 | 6350.9801
535 | 0.4053 | 25 | 0.6723 | 0.10085 | 0.74293 | 0.7283 | 0.76006 | 109 | 0.64837 | 1.0746 | 0.31988 | 0.79592 | 0.58863 | 0.61297 | 0.95589 | 131.8121 | 0.96584 | 12.8927 | 6628.2941
536 | 0.6813 | 26 | 0.88539 | 0.14136 | 0.11285 | 0.64751 | 0.96418 | 113 | 0.85721 | 1.1382 | 0.2073 | 0.75772 | 0.25895 | 0.50758 | 0.82612 | 113.8875 | 0.39304 | 6.1172 | 6739.9363
537 | 0.87092 | 27 | 0.72135 | 0.10857 | 0.27555 | 0.67424 | 0.43246 | 106 | 0.84209 | 1.1325 | 0.23357 | 0.76742 | 0.74098 | 0.65587 | 0.62044 | 96.6457 | 0.34552 | 5.776 | 6950.6947
538 | 0.61578 | 26 | 0.61712 | 0.092826 | 0.34567 | 0.68315 | 0.49387 | 106 | 0.20122 | 0.98392 | 0.68141 | 0.92348 | 0.064575 | 0.40366 | 0.67691 | 100.774 | 0.069347 | 3.6446 | 6086.524
539 | 0.33199 | 24 | 0.38033 | 0.063655 | 0.76087 | 0.73084 | 0.37406 | 105 | 0.6153 | 1.0665 | 0.046317 | 0.67455 | 0.70742 | 0.64556 | 0.42378 | 84.2609 | 0.1103 | 4.0741 | 5950.1438
540 | 0.2584 | 24 | 0.94829 | 0.16061 | 0.99933 | 0.79634 | 0.72063 | 109 | 0.25215 | 0.99394 | 0.6929 | 0.92852 | 0.87365 | 0.70537 | 0.49663 | 88.5566 | 0.099234 | 3.9673 | 6478.8405
541 | 0.54528 | 25 | 0.27737 | 0.052763 | 0.54653 | 0.70477 | 0.01147 | 101 | 0.81777 | 1.1237 | 0.10217 | 0.71073 | 0.44933 | 0.57344 | 0.99183 | 142.1721 | 0.65136 | 8.2678 | 6379.817
542 | 0.99341 | 29 | 0.08274 | 0.028765 | 0.95387 | 0.76963 | 0.35517 | 105 | 0.1206 | 0.96497 | 0.12515 | 0.72255 | 0.98254 | 0.77739 | 0.93239 | 127.4809 | 0.75042 | 9.3039 | 6830.6459
543 | 0.40833 | 25 | 0.95942 | 0.16511 | 0.31684 | 0.6796 | 0.98367 | 113 | 0.79474 | 1.116 | 0.46868 | 0.84291 | 0.70444 | 0.64468 | 0.37477 | 81.5221 | 0.53716 | 7.2431 | 6841.7766
544 | 0.91829 | 28 | 0.11274 | 0.033577 | 0.6069 | 0.71133 | 0.61082 | 107 | 0.79931 | 1.1175 | 0.95974 | 1.1017 | 0.38473 | 0.55302 | 0.44961 | 85.7512 | 0.76289 | 9.4481 | 7077.7483
545 | 0.089446 | 22 | 0.48843 | 0.076117 | 0.76619 | 0.73162 | 0.29684 | 105 | 0.0085083 | 0.91726 | 0.62327 | 0.89931 | 0.67012 | 0.63478 | 0.050041 | 61.185 | 0.67116 | 8.4617 | 5605.5948
546 | 0.97031 | 29 | 0.050093 | 0.022382 | 0.74912 | 0.72916 | 0.51856 | 107 | 0.63925 | 1.0723 | 0.78474 | 0.9727 | 0.98559 | 0.78129 | 0.1966 | 72.1698 | 0.88977 | 11.2145 | 7412.0823
547 | 0.80206 | 27 | 0.71747 | 0.10794 | 0.94314 | 0.76628 | 0.87966 | 111 | 0.7516 | 1.1026 | 0.40709 | 0.82278 | 0.34172 | 0.53846 | 0.45704 | 86.1861 | 0.36766 | 5.9334 | 6562.5085
548 | 0.63793 | 26 | 0.11519 | 0.03394 | 0.72009 | 0.72518 | 0.12231 | 103 | 0.23982 | 0.99162 | 0.092514 | 0.70536 | 0.73694 | 0.6546 | 0.12385 | 67.5963 | 0.67483 | 8.4983 | 5966.2476
549 | 0.25166 | 24 | 0.32682 | 0.057889 | 0.915 | 0.75877 | 0.0056598 | 101 | 0.96455 | 1.1943 | 0.051385 | 0.67853 | 0.57054 | 0.60812 | 0.77768 | 109.1659 | 0.85487 | 10.6564 | 6186.9222
550 | 0.53606 | 25 | 0.87562 | 0.13892 | 0.60231 | 0.71082 | 0.63659 | 108 | 0.8773 | 1.1464 | 0.17551 | 0.74512 | 0.97027 | 0.7644 | 0.32906 | 79.0629 | 0.35875 | 5.8697 | 6844.1974
551 | 0.56715 | 25 | 0.92473 | 0.15248 | 0.26018 | 0.67214 | 0.54694 | 107 | 0.76948 | 1.108 | 0.59786 | 0.88933 | 0.82932 | 0.68677 | 0.46594 | 86.7113 | 0.67558 | 8.5058 | 6927.0873
552 | 0.53067 | 25 | 0.16886 | 0.041092 | 0.69361 | 0.72172 | 0.51829 | 106 | 0.12081 | 0.96502 | 0.17522 | 0.745 | 0.34559 | 0.53981 | 0.68298 | 101.2386 | 0.38866 | 6.0851 | 5828.6728
553 | 0.24004 | 23 | 0.99876 | 0.19391 | 0.27004 | 0.67349 | 0.65573 | 108 | 0.87563 | 1.1457 | 0.6157 | 0.8963 | 0.53799 | 0.5992 | 0.34285 | 79.7958 | 0.14685 | 4.3932 | 6558.471
554 | 0.28786 | 24 | 0.34307 | 0.059615 | 0.64494 | 0.71573 | 0.37261 | 105 | 0.96512 | 1.1948 | 0.36603 | 0.80993 | 0.53892 | 0.59946 | 0.40642 | 83.2781 | 0.54389 | 7.2997 | 6331.3176
555 | 0.62406 | 26 | 0.43708 | 0.070047 | 0.57111 | 0.70738 | 0.24807 | 104 | 0.25961 | 0.99532 | 0.58869 | 0.88581 | 0.97403 | 0.76803 | 0.33056 | 79.1422 | 0.014963 | 2.7639 | 6647.6319
556 | 0.74631 | 26 | 0.21969 | 0.046871 | 0.14647 | 0.65412 | 0.37926 | 105 | 0.79063 | 1.1146 | 0.1593 | 0.73826 | 0.52336 | 0.5951 | 0.45828 | 86.2593 | 0.79897 | 9.8878 | 6428.4883
557 | 0.59779 | 26 | 0.75958 | 0.11507 | 0.87957 | 0.75092 | 0.32403 | 105 | 0.57465 | 1.0571 | 0.54241 | 0.86861 | 0.001135 | 0.31374 | 0.17284 | 70.7872 | 0.5485 | 7.3388 | 5779.2806
558 | 0.58286 | 25 | 0.73043 | 0.11007 | 0.53944 | 0.70402 | 0.88343 | 111 | 0.91892 | 1.1658 | 0.51984 | 0.86053 | 0.36869 | 0.54769 | 0.58997 | 94.5456 | 0.72125 | 8.9802 | 6642.3468
559 | 0.53276 | 25 | 0.097755 | 0.031266 | 0.37529 | 0.68664 | 0.2309 | 104 | 0.49973 | 1.0408 | 0.76464 | 0.96233 | 0.071281 | 0.40891 | 0.65003 | 98.7674 | 0.42903 | 6.3845 | 5977.4365
560 | 0.42391 | 25 | 0.8909 | 0.14279 | 0.98097 | 0.78049 | 0.77597 | 109 | 0.31608 | 1.0054 | 0.28398 | 0.7846 | 0.3636 | 0.54597 | 0.9053 | 123.3494 | 0.6222 | 7.9919 | 6284.9321
561 | 0.7418 | 26 | 0.088327 | 0.02972 | 0.91368 | 0.75845 | 0.84293 | 110 | 0.70902 | 1.0904 | 0.35234 | 0.80574 | 0.54766 | 0.60188 | 0.64148 | 98.1451 | 0.92833 | 11.9477 | 6434.3743
562 | 0.82033 | 27 | 0.10223 | 0.031974 | 0.81109 | 0.73853 | 0.13375 | 103 | 0.81947 | 1.1243 | 0.21284 | 0.75981 | 0.95004 | 0.74792 | 0.83749 | 115.0888 | 0.69192 | 8.6715 | 6916.2244
563 | 0.50914 | 25 | 0.41609 | 0.067647 | 0.22527 | 0.66712 | 0.55999 | 107 | 0.84576 | 1.1338 | 0.50484 | 0.85527 | 0.70031 | 0.64346 | 0.27371 | 76.1951 | 0.055292 | 3.4685 | 6578.4564
564 | 0.33865 | 24 | 0.96526 | 0.16772 | 0.73579 | 0.72731 | 0.19897 | 104 | 0.30302 | 1.003 | 0.80568 | 0.98404 | 0.91744 | 0.72734 | 0.38059 | 81.8417 | 0.68571 | 8.608 | 6658.2084
565 | 0.98188 | 29 | 0.015326 | 0.01238 | 0.78061 | 0.73376 | 0.14568 | 103 | 0.28139 | 0.99924 | 0.27457 | 0.78152 | 0.59958 | 0.61586 | 0.75067 | 106.7569 | 0.1566 | 4.4713 | 6522.2568
566 | 0.45613 | 25 | 0.33806 | 0.059081 | 0.52584 | 0.70262 | 0.0026621 | 100 | 0.26224 | 0.9958 | 0.91237 | 1.055 | 0.69982 | 0.64331 | 0.64756 | 98.5869 | 0.24124 | 5.0683 | 6526.9558
567 | 0.93666 | 28 | 0.63459 | 0.095299 | 0.94036 | 0.76546 | 0.27401 | 105 | 0.47983 | 1.0367 | 0.097923 | 0.7084 | 0.0026951 | 0.32118 | 0.96821 | 134.5601 | 0.27068 | 5.2629 | 6018.8125
568 | 0.56185 | 25 | 0.29053 | 0.054109 | 0.84336 | 0.74403 | 0.65159 | 108 | 0.34688 | 1.0109 | 0.64965 | 0.91003 | 0.65339 | 0.63014 | 0.31401 | 78.2717 | 0.29592 | 5.4328 | 6250.0698
569 | 0.83676 | 27 | 0.47509 | 0.074511 | 0.9101 | 0.7576 | 0.52307 | 107 | 0.10565 | 0.96081 | 0.90947 | 1.0526 | 0.67434 | 0.63597 | 0.5445 | 91.5512 | 0.52368 | 7.131 | 6739.3396
570 | 0.64113 | 26 | 0.63765 | 0.095739 | 0.29197 | 0.67642 | 0.36527 | 105 | 0.36612 | 1.0145 | 0.2091 | 0.7584 | 0.72951 | 0.65228 | 0.43845 | 85.1028 | 0.63917 | 8.1511 | 6413.027
571 | 0.41077 | 25 | 0.90416 | 0.14638 | 0.04971 | 0.63153 | 0.1504 | 103 | 0.58864 | 1.0603 | 0.81854 | 0.99131 | 0.91404 | 0.72545 | 0.62967 | 97.2983 | 0.23568 | 5.032 | 7094.5031
572 | 0.61568 | 26 | 0.77255 | 0.1174 | 0.85501 | 0.74615 | 0.99347 | 114 | 0.12002 | 0.96481 | 0.98111 | 1.1327 | 0.51716 | 0.59335 | 0.52801 | 90.5028 | 0.66235 | 8.3747 | 6822.2379
573 | 0.96767 | 29 | 0.26113 | 0.051117 | 0.64515 | 0.71576 | 0.17293 | 104 | 0.44993 | 1.0306 | 0.90088 | 1.0458 | 0.12463 | 0.44401 | 0.068061 | 63.0443 | 0.84555 | 10.5192 | 6523.6617
574 | 0.64981 | 26 | 0.38372 | 0.064028 | 0.14402 | 0.65367 | 0.93747 | 112 | 0.33246 | 1.0083 | 0.094999 | 0.70677 | 0.58449 | 0.61186 | 0.81443 | 112.6934 | 0.05415 | 3.4532 | 6392.5025
575 | 0.84721 | 27 | 0.82966 | 0.12851 | 0.78845 | 0.73495 | 0.57106 | 107 | 0.17142 | 0.97746 | 0.060037 | 0.68488 | 0.95111 | 0.74869 | 0.47747 | 87.3985 | 0.972 | 13.092 | 6590.8383
576 | 0.45687 | 25 | 0.36373 | 0.06184 | 0.6001 | 0.71057 | 0.28667 | 105 | 0.32103 | 1.0063 | 0.3078 | 0.79219 | 0.18564 | 0.47576 | 0.46323 | 86.5511 | 0.45828 | 6.6081 | 5824.3872
577 | 0.62201 | 26 | 0.94548 | 0.15956 | 0.30153 | 0.67766 | 0.79196 | 109 | 0.93787 | 1.1763 | 0.55503 | 0.87321 | 0.42681 | 0.5665 | 0.40325 | 83.0999 | 0.56519 | 7.4817 | 6934.2831
578 | 0.77747 | 27 | 0.97426 | 0.17221 | 0.47854 | 0.69783 | 0.97299 | 113 | 0.36652 | 1.0146 | 0.84477 | 1.007 | 0.75578 | 0.66063 | 0.35213 | 80.2935 | 0.33145 | 5.6773 | 7170.2393
579 | 0.9901 | 29 | 0.44322 | 0.070759 | 0.74077 | 0.728 | 0.50923 | 106 | 0.33895 | 1.0095 | 0.27128 | 0.78043 | 0.40248 | 0.55879 | 0.15595 | 69.7454 | 0.86093 | 10.7481 | 6437.7561
580 | 0.7185 | 26 | 0.6578 | 0.098679 | 0.27663 | 0.67438 | 0.96243 | 113 | 0.69397 | 1.0864 | 0.5115 | 0.8576 | 0.53359 | 0.59798 | 0.39298 | 82.5267 | 0.0099596 | 2.6232 | 6676.8169
581 | 0.33493 | 24 | 0.38607 | 0.064287 | 0.061579 | 0.63509 | 0.80864 | 110 | 0.32441 | 1.0069 | 0.048189 | 0.67604 | 0.49095 | 0.58582 | 0.66398 | 99.7992 | 0.091153 | 3.8855 | 5968.5198
582 | 0.53681 | 25 | 0.45769 | 0.072449 | 0.66414 | 0.71804 | 0.40364 | 106 | 0.54951 | 1.0515 | 0.81679 | 0.99031 | 0.31164 | 0.52772 | 0.30957 | 78.04 | 0.53816 | 7.2515 | 6278.7014
583 | 0.22957 | 23 | 0.82591 | 0.12773 | 0.48102 | 0.69808 | 0.48877 | 106 | 0.14023 | 0.97006 | 0.90838 | 1.0517 | 0.30818 | 0.52645 | 0.16376 | 70.2338 | 0.76538 | 9.4772 | 6036.9219
584 | 0.61019 | 26 | 0.30033 | 0.055121 | 0.6928 | 0.72162 | 0.4747 | 106 | 0.29682 | 1.002 | 0.46472 | 0.84158 | 0.50883 | 0.59098 | 0.19978 | 72.3486 | 0.56493 | 7.4794 | 6169.8115
585 | 0.98753 | 29 | 0.2901 | 0.054065 | 0.45282 | 0.69516 | 0.013927 | 101 | 0.70705 | 1.0899 | 0.97707 | 1.1258 | 0.64552 | 0.62799 | 0.52232 | 90.1449 | 0.12425 | 4.2013 | 7397.5597
586 | 0.74534 | 26 | 0.97947 | 0.17518 | 0.16404 | 0.65728 | 0.58061 | 107 | 0.14563 | 0.97139 | 0.62585 | 0.90034 | 0.048844 | 0.39015 | 0.89791 | 122.3285 | 0.51631 | 7.0703 | 6347.1547
587 | 0.87863 | 28 | 0.77958 | 0.11868 | 0.18107 | 0.66018 | 0.053896 | 102 | 0.97075 | 1.1994 | 0.77881 | 0.9696 | 0.74122 | 0.65595 | 0.64309 | 98.2617 | 0.16714 | 4.5531 | 7592.2851
588 | 0.5581 | 25 | 0.85128 | 0.13321 | 0.75949 | 0.73065 | 0.21147 | 104 | 0.8552 | 1.1374 | 0.19795 | 0.75412 | 0.66708 | 0.63392 | 0.32034 | 78.6038 | 0.81089 | 10.0417 | 6468.0086
589 | 0.93535 | 28 | 0.7187 | 0.10814 | 0.19228 | 0.66201 | 0.65303 | 108 | 0.57519 | 1.0572 | 0.76192 | 0.96096 | 0.34247 | 0.53872 | 0.078202 | 63.9824 | 0.97677 | 13.262 | 6841.4483
590 | 0.9724 | 29 | 0.72738 | 0.10956 | 0.69064 | 0.72134 | 0.90615 | 111 | 0.35716 | 1.0128 | 0.23757 | 0.76884 | 0.13383 | 0.44923 | 0.81782 | 113.0356 | 0.1937 | 4.7485 | 6514.26
591 | 0.20858 | 23 | 0.38679 | 0.064367 | 0.80738 | 0.73793 | 0.5989 | 107 | 0.99283 | 1.225 | 0.034011 | 0.66388 | 0.072801 | 0.41006 | 0.95014 | 130.6619 | 0.54279 | 7.2904 | 5906.5594
592 | 0.94475 | 28 | 0.70005 | 0.10514 | 0.52715 | 0.70275 | 0.79733 | 109 | 0.8804 | 1.1477 | 0.97122 | 1.1169 | 0.46423 | 0.57794 | 0.016445 | 56.4119 | 0.76664 | 9.4921 | 7297.8568
593 | 0.57223 | 25 | 0.89482 | 0.14383 | 0.57666 | 0.70798 | 0.1047 | 103 | 0.079012 | 0.95259 | 0.20314 | 0.75613 | 0.0609 | 0.40067 | 0.78721 | 110.0508 | 0.44468 | 6.5035 | 5805.8687
594 | 0.091208 | 22 | 0.90936 | 0.14785 | 0.58463 | 0.70886 | 0.71979 | 109 | 0.81446 | 1.1226 | 0.32882 | 0.79864 | 0.083154 | 0.41763 | 0.046325 | 60.7616 | 0.23212 | 5.0088 | 5653.2471
595 | 0.58768 | 25 | 0.31873 | 0.057038 | 0.62913 | 0.71388 | 0.43402 | 106 | 0.65305 | 1.0758 | 0.97769 | 1.1268 | 0.70355 | 0.64441 | 0.73953 | 105.8012 | 0.76472 | 9.4695 | 6920.9771
596 | 0.93141 | 28 | 0.58869 | 0.088917 | 0.78848 | 0.73496 | 0.18017 | 104 | 0.5249 | 1.0461 | 0.14277 | 0.73089 | 0.69278 | 0.64125 | 0.6496 | 98.7358 | 0.70726 | 8.831 | 6641.8434
597 | 0.37042 | 24 | 0.43374 | 0.069663 | 0.98653 | 0.78359 | 0.48449 | 106 | 0.21268 | 0.98628 | 0.71848 | 0.94007 | 0.47896 | 0.58231 | 0.17308 | 70.8013 | 0.12321 | 4.1921 | 5920.2396
598 | 0.1978 | 23 | 0.29027 | 0.054083 | 0.81157 | 0.73861 | 0.83843 | 110 | 0.73997 | 1.0992 | 0.59683 | 0.88894 | 0.090414 | 0.42266 | 0.406 | 83.2544 | 0.76582 | 9.4825 | 5760.0888
599 | 0.36077 | 24 | 0.82755 | 0.12807 | 0.535 | 0.70356 | 0.88097 | 111 | 0.32857 | 1.0076 | 0.97171 | 1.1176 | 0.55959 | 0.60515 | 0.79153 | 110.4581 | 0.97532 | 13.2088 | 6783.1271
600 | 0.37089 | 24 | 0.46794 | 0.07366 | 0.83527 | 0.7426 | 0.66053 | 108 | 0.81201 | 1.1217 | 0.39002 | 0.81738 | 0.38926 | 0.5545 | 0.73 | 105.0001 | 0.93738 | 12.1468 | 6261.796
601 | 0.97611 | 29 | 0.55804 | 0.084853 | 0.78294 | 0.73411 | 0.51378 | 106 | 0.3998 | 1.0208 | 0.20294 | 0.75605 | 0.74139 | 0.656 | 0.52189 | 90.118 | 0.66542 | 8.4049 | 6765.6859
602 | 0.051103 | 22 | 0.48743 | 0.075995 | 0.69018 | 0.72128 | 0.65556 | 108 | 0.20679 | 0.98507 | 0.87947 | 1.0299 | 0.69496 | 0.64189 | 0.44839 | 85.6797 | 0.71188 | 8.8799 | 6083.9327
603 | 0.73554 | 26 | 0.51878 | 0.079847 | 0.98484 | 0.78259 | 0.73891 | 109 | 0.56653 | 1.0552 | 0.55812 | 0.87434 | 0.56285 | 0.60604 | 0.73908 | 105.7631 | 0.79848 | 9.8816 | 6558.008
604 | 0.29771 | 24 | 0.62397 | 0.093788 | 0.14354 | 0.65358 | 0.87929 | 111 | 0.064651 | 0.94757 | 0.95588 | 1.0971 | 0.52885 | 0.59665 | 0.026048 | 58.0697 | 0.35112 | 5.8155 | 6289.8576
605 | 0.014551 | 21 | 0.13276 | 0.036436 | 0.82211 | 0.74035 | 0.90901 | 111 | 0.81132 | 1.1215 | 0.20165 | 0.75556 | 0.44745 | 0.57286 | 0.41022 | 83.4919 | 0.57946 | 7.6061 | 5633.3591
606 | 0.75139 | 26 | 0.72712 | 0.10952 | 0.54607 | 0.70472 | 0.208 | 104 | 0.64941 | 1.0749 | 0.47172 | 0.84393 | 0.64996 | 0.6292 | 0.77501 | 108.9218 | 0.27424 | 5.2866 | 6710.9332
607 | 0.65697 | 26 | 0.76407 | 0.11587 | 0.61298 | 0.71202 | 0.28063 | 105 | 0.28545 | 0.99995 | 0.16294 | 0.73983 | 0.014557 | 0.34922 | 0.60338 | 95.4594 | 0.98189 | 13.4656 | 5794.4635
608 | 0.56448 | 25 | 0.56278 | 0.085472 | 0.0020144 | 0.60635 | 0.50746 | 106 | 0.81003 | 1.1211 | 0.94568 | 1.0858 | 0.2548 | 0.50591 | 0.97035 | 135.0885 | 0.5022 | 6.9555 | 6964.4211
609 | 0.74532 | 26 | 0.45662 | 0.072323 | 0.44512 | 0.69435 | 0.53794 | 107 | 0.93679 | 1.1756 | 0.90845 | 1.0518 | 0.7784 | 0.66819 | 0.18618 | 71.5743 | 0.29063 | 5.3969 | 7147.616
610 | 0.7755 | 27 | 0.16062 | 0.040077 | 0.48284 | 0.69827 | 0.026583 | 101 | 0.92104 | 1.1669 | 0.28386 | 0.78456 | 0.796 | 0.67434 | 0.81911 | 113.1667 | 0.78695 | 9.7372 | 6941.6603
611 | 0.70032 | 26 | 0.75924 | 0.11501 | 0.61059 | 0.71175 | 0.40906 | 106 | 0.87831 | 1.1468 | 0.24314 | 0.77081 | 0.21241 | 0.488 | 0.25457 | 75.2288 | 0.68843 | 8.6357 | 6313.8875
612 | 0.7276 | 26 | 0.39324 | 0.065082 | 0.0083734 | 0.61294 | 0.076554 | 102 | 0.34175 | 1.01 | 0.1394 | 0.72934 | 0.15649 | 0.46137 | 0.98107 | 138.0836 | 0.69177 | 8.67 | 6207.6014
613 | 0.34471 | 24 | 0.51101 | 0.078881 | 0.14246 | 0.65338 | 0.23129 | 104 | 0.85635 | 1.1379 | 0.19855 | 0.75436 | 0.29914 | 0.52311 | 0.53288 | 90.8106 | 0.61322 | 7.9091 | 6137.1678
614 | 0.44653 | 25 | 0.099375 | 0.031524 | 0.76543 | 0.73151 | 0.7589 | 109 | 0.78395 | 1.1125 | 0.65949 | 0.91413 | 0.81285 | 0.68049 | 0.39769 | 82.7889 | 0.95201 | 12.5024 | 6632.7775
615 | 0.53104 | 25 | 0.75953 | 0.11506 | 0.079846 | 0.63996 | 0.84559 | 110 | 0.67812 | 1.0822 | 0.83715 | 1.0023 | 0.74499 | 0.65715 | 0.34123 | 79.7091 | 0.23298 | 5.0144 | 6914.0856
616 | 0.82561 | 27 | 0.065388 | 0.025571 | 0.46099 | 0.69602 | 0.21123 | 104 | 0.91077 | 1.1616 | 0.70454 | 0.93371 | 0.35948 | 0.54458 | 0.19769 | 72.2314 | 0.88899 | 11.2011 | 6655.5341
617 | 0.88519 | 28 | 0.11779 | 0.034321 | 0.98639 | 0.7835 | 0.10414 | 103 | 0.32917 | 1.0077 | 0.40397 | 0.82178 | 0.75906 | 0.6617 | 0.29093 | 77.0753 | 0.022926 | 2.9456 | 6395.6669
618 | 0.91632 | 28 | 0.1563 | 0.039535 | 0.47935 | 0.69791 | 0.3079 | 105 | 0.55011 | 1.0516 | 0.73119 | 0.946 | 0.76558 | 0.66386 | 0.22219 | 73.5686 | 0.29894 | 5.4534 | 6887.6236
619 | 0.77306 | 27 | 0.87221 | 0.13808 | 0.53763 | 0.70384 | 0.8877 | 111 | 0.42123 | 1.025 | 0.83347 | 1.0001 | 0.46994 | 0.57964 | 0.84709 | 116.1348 | 0.087195 | 3.8441 | 7043.1222
620 | 0.085814 | 22 | 0.098394 | 0.031368 | 0.02586 | 0.62274 | 0.069413 | 102 | 0.26351 | 0.99604 | 0.089462 | 0.70361 | 0.34149 | 0.53838 | 0.68405 | 101.3211 | 0.9639 | 12.8337 | 5559.5319
621 | 0.60683 | 26 | 0.80245 | 0.12302 | 0.11426 | 0.6478 | 0.59581 | 107 | 0.65522 | 1.0763 | 0.71372 | 0.93788 | 0.44022 | 0.57065 | 0.64017 | 98.0509 | 0.34853 | 5.7972 | 6815.7503
622 | 0.81769 | 27 | 0.20234 | 0.044983 | 0.51678 | 0.70169 | 0.66862 | 108 | 0.56914 | 1.0558 | 0.20005 | 0.75494 | 0.79223 | 0.673 | 0.4591 | 86.3077 | 0.86308 | 10.7811 | 6600.428
623 | 0.8179 | 27 | 0.40674 | 0.066592 | 0.53227 | 0.70328 | 0.91612 | 111 | 0.92595 | 1.1695 | 0.33525 | 0.80058 | 0.030919 | 0.37173 | 0.0058203 | 53.8146 | 0.39988 | 6.1673 | 6100.8773
624 | 0.90835 | 28 | 0.97844 | 0.17457 | 0.94653 | 0.7673 | 0.74358 | 109 | 0.87521 | 1.1455 | 0.10396 | 0.71169 | 0.31484 | 0.52889 | 0.81027 | 112.2773 | 0.058265 | 3.5074 | 6835.2705
625 | 0.33032 | 24 | 0.87506 | 0.13878 | 0.37521 | 0.68663 | 0.52062 | 107 | 0.95251 | 1.1855 | 0.22223 | 0.7633 | 0.91543 | 0.72621 | 0.71411 | 103.6945 | 0.62182 | 7.9883 | 6878.6271
626 | 0.91503 | 28 | 0.94448 | 0.15919 | 0.88251 | 0.75152 | 0.65642 | 108 | 0.49173 | 1.0391 | 0.88416 | 1.0333 | 0.0012898 | 0.31465 | 0.70596 | 103.0397 | 0.12425 | 4.2013 | 6466.7143
627 | 0.086386 | 22 | 0.29842 | 0.054923 | 0.93316 | 0.76344 | 0.36818 | 105 | 0.17592 | 0.97847 | 0.55945 | 0.87483 | 0.53632 | 0.59874 | 0.40671 | 83.2942 | 0.49918 | 6.9311 | 5644.3387
628 | 0.58685 | 25 | 0.05281 | 0.02298 | 0.24324 | 0.66975 | 0.36536 | 105 | 0.77901 | 1.1109 | 0.52073 | 0.86085 | 0.77498 | 0.66702 | 0.29065 | 77.0607 | 0.40359 | 6.1947 | 6478.8174
629 | 0.33946 | 24 | 0.3389 | 0.05917 | 0.15777 | 0.65617 | 0.93334 | 112 | 0.91745 | 1.165 | 0.27712 | 0.78236 | 0.67227 | 0.63538 | 0.20898 | 72.8569 | 0.34085 | 5.7432 | 6427.5898
630 | 0.9034 | 28 | 0.56181 | 0.085345 | 0.23778 | 0.66896 | 0.020018 | 101 | 0.70158 | 1.0884 | 0.5908 | 0.88662 | 0.83683 | 0.68973 | 0.67527 | 100.6495 | 0.33213 | 5.6821 | 7176.1289
631 | 0.63256 | 26 | 0.58747 | 0.088753 | 0.24646 | 0.67021 | 0.97204 | 113 | 0.54966 | 1.0515 | 0.627 | 0.9008 | 0.072366 | 0.40973 | 0.28929 | 76.9911 | 0.37828 | 6.0098 | 6181.2804
632 | 0.45459 | 25 | 0.40462 | 0.066354 | 0.83525 | 0.7426 | 0.25408 | 104 | 0.96593 | 1.1954 | 0.93978 | 1.0798 | 0.71693 | 0.64842 | 0.98078 | 137.9924 | 0.67187 | 8.4688 | 7225.0545
633 | 0.52979 | 25 | 0.42142 | 0.068252 | 0.72331 | 0.72561 | 0.5393 | 107 | 0.40756 | 1.0223 | 0.4098 | 0.82364 | 0.65177 | 0.6297 | 0.30747 | 77.9307 | 0.051998 | 3.4241 | 6179.646
634 | 0.68144 | 26 | 0.56998 | 0.086419 | 0.58378 | 0.70876 | 0.88134 | 111 | 0.79946 | 1.1175 | 0.71571 | 0.93879 | 0.18943 | 0.47754 | 0.51231 | 89.521 | 0.27694 | 5.3048 | 6518.9111
635 | 0.90594 | 28 | 0.81987 | 0.12649 | 0.72558 | 0.72592 | 0.81669 | 110 | 0.86065 | 1.1396 | 0.38389 | 0.81547 | 0.35731 | 0.54384 | 0.93367 | 127.6953 | 0.2335 | 5.0178 | 7075.8314
636 | 0.14055 | 23 | 0.57088 | 0.086538 | 0.86196 | 0.74746 | 0.41153 | 106 | 0.94705 | 1.1819 | 0.82723 | 0.99637 | 0.46352 | 0.57772 | 0.67131 | 100.3495 | 0.63335 | 8.0961 | 6470.3789
637 | 0.59904 | 26 | 0.59346 | 0.089563 | 0.27419 | 0.67405 | 0.84392 | 110 | 0.14485 | 0.9712 | 0.80284 | 0.98247 | 0.20416 | 0.48432 | 0.73343 | 105.2866 | 0.29469 | 5.4245 | 6400.0667
638 | 0.33583 | 24 | 0.018579 | 0.01363 | 0.88551 | 0.75215 | 0.66634 | 108 | 0.78588 | 1.1131 | 0.80257 | 0.98232 | 0.55943 | 0.6051 | 0.18822 | 71.6921 | 0.3781 | 6.0085 | 6236.0976
639 | 0.52017 | 25 | 0.34989 | 0.060346 | 0.11857 | 0.6487 | 0.21095 | 104 | 0.90814 | 1.1603 | 0.74208 | 0.9512 | 0.86119 | 0.69985 | 0.23767 | 74.3755 | 0.715 | 8.9131 | 6909.2478
640 | 0.67938 | 26 | 0.72736 | 0.10956 | 0.34986 | 0.68365 | 0.50673 | 106 | 0.73281 | 1.0971 | 0.98931 | 1.1493 | 0.42603 | 0.56626 | 0.62889 | 97.2425 | 0.17564 | 4.6173 | 7055.1757
641 | 0.095259 | 22 | 0.55806 | 0.084855 | 0.37827 | 0.68698 | 0.3185 | 105 | 0.24537 | 0.99267 | 0.54524 | 0.86963 | 0.49557 | 0.58716 | 0.80376 | 111.6358 | 0.96773 | 12.9519 | 5968.5807
642 | 0.23189 | 23 | 0.49245 | 0.076604 | 0.47858 | 0.69783 | 0.38062 | 105 | 0.31681 | 1.0055 | 0.49933 | 0.85336 | 0.80913 | 0.67911 | 0.60504 | 95.5738 | 0.87518 | 10.9718 | 6164.298
643 | 0.70639 | 26 | 0.67975 | 0.10198 | 0.60581 | 0.71121 | 0.43347 | 106 | 0.79394 | 1.1157 | 0.15761 | 0.73752 | 0.60584 | 0.61751 | 0.80565 | 111.8214 | 0.35584 | 5.849 | 6634.6226
644 | 0.46376 | 25 | 0.53271 | 0.081599 | 0.0011934 | 0.60489 | 0.31246 | 105 | 0.14665 | 0.97164 | 0.23253 | 0.76704 | 0.55029 | 0.6026 | 0.95237 | 131.0992 | 0.11919 | 4.156 | 6365.2388
645 | 0.38979 | 24 | 0.42893 | 0.06911 | 0.51992 | 0.70201 | 0.43592 | 106 | 0.43108 | 1.0269 | 0.58139 | 0.88304 | 0.47229 | 0.58034 | 0.74333 | 106.1247 | 0.46895 | 6.6912 | 6210.4496
646 | 0.10149 | 22 | 0.49765 | 0.077238 | 0.59256 | 0.70973 | 0.072512 | 102 | 0.76412 | 1.1063 | 0.19259 | 0.75202 | 0.18123 | 0.47366 | 0.54514 | 91.5924 | 0.65502 | 8.3031 | 5621.3285
647 | 0.96328 | 29 | 0.022399 | 0.014966 | 0.46536 | 0.69647 | 0.45055 | 106 | 0.39284 | 1.0195 | 0.94675 | 1.087 | 0.2367 | 0.49846 | 0.52101 | 90.0634 | 0.56137 | 7.4487 | 6801.5982
648 | 0.39992 | 24 | 0.18977 | 0.043563 | 0.55068 | 0.7052 | 0.39303 | 105 | 0.0051737 | 0.91346 | 0.51498 | 0.85882 | 0.075553 | 0.41213 | 0.41384 | 83.6959 | 0.30623 | 5.5032 | 5436.6112
649 | 0.31994 | 24 | 0.35156 | 0.060526 | 0.69142 | 0.72144 | 0.37291 | 105 | 0.53772 | 1.0489 | 0.823 | 0.99389 | 0.66285 | 0.63275 | 0.34955 | 80.1549 | 0.15781 | 4.4809 | 6322.6596
650 | 0.79514 | 27 | 0.20076 | 0.044806 | 0.55087 | 0.70522 | 0.084986 | 103 | 0.70638 | 1.0897 | 0.68499 | 0.92504 | 0.65816 | 0.63145 | 0.68501 | 101.3954 | 0.019934 | 2.8817 | 6813.8024
651 | 0.2136 | 23 | 0.46513 | 0.073326 | 0.0096183 | 0.61387 | 0.45434 | 106 | 0.24512 | 0.99262 | 0.44517 | 0.83509 | 0.29924 | 0.52314 | 0.42524 | 84.344 | 0.53191 | 7.1992 | 5838.0283
652 | 0.102 | 22 | 0.37447 | 0.063011 | 0.44434 | 0.69427 | 0.96821 | 113 | 0.72205 | 1.094 | 0.4774 | 0.84585 | 0.41507 | 0.56281 | 0.052464 | 61.4525 | 0.53294 | 7.2078 | 5832.8427
653 | 0.16658 | 23 | 0.22456 | 0.047388 | 0.62756 | 0.71369 | 0.93262 | 112 | 0.087252 | 0.95526 | 0.46962 | 0.84322 | 0.92287 | 0.73044 | 0.39809 | 82.8111 | 0.37896 | 6.0147 | 6048.2527
654 | 0.34472 | 24 | 0.53813 | 0.082287 | 0.58676 | 0.70909 | 0.61021 | 107 | 0.13992 | 0.96998 | 0.83897 | 1.0034 | 0.8092 | 0.67913 | 0.54212 | 91.3985 | 0.87118 | 10.9078 | 6444.5609
655 | 0.88031 | 28 | 0.67472 | 0.10121 | 0.76952 | 0.73211 | 0.82267 | 110 | 0.77354 | 1.1092 | 0.27891 | 0.78295 | 0.24363 | 0.50135 | 0.2121 | 73.0271 | 0.4222 | 6.3332 | 6518.1133
656 | 0.88164 | 28 | 0.2933 | 0.054395 | 0.31115 | 0.67889 | 0.64801 | 108 | 0.54697 | 1.0509 | 0.89295 | 1.0397 | 0.68446 | 0.63885 | 0.70659 | 103.09 | 0.26905 | 5.252 | 7226.7341
657 | 0.6727 | 26 | 0.41177 | 0.067159 | 0.37086 | 0.68612 | 0.82147 | 110 | 0.65573 | 1.0764 | 0.1695 | 0.74262 | 0.10799 | 0.43405 | 0.3952 | 82.65 | 0.29931 | 5.4559 | 6006.5815
658 | 0.25831 | 24 | 0.70701 | 0.10625 | 0.75405 | 0.72986 | 0.8994 | 111 | 0.58731 | 1.06 | 0.49718 | 0.85261 | 0.72502 | 0.65089 | 0.94937 | 130.5132 | 0.53669 | 7.2392 | 6616.9533
659 | 0.45796 | 25 | 0.65356 | 0.098053 | 0.84111 | 0.74363 | 0.26167 | 104 | 0.60723 | 1.0646 | 0.12593 | 0.72293 | 0.22295 | 0.49261 | 0.39248 | 82.499 | 0.30146 | 5.4706 | 5880.6236
660 | 0.25291 | 24 | 0.074067 | 0.027215 | 0.66131 | 0.7177 | 0.29217 | 105 | 0.36321 | 1.014 | 0.097121 | 0.70796 | 0.54845 | 0.6021 | 0.88699 | 120.8874 | 0.068398 | 3.6333 | 5923.5858
661 | 0.30512 | 24 | 0.19831 | 0.044532 | 0.86958 | 0.74893 | 0.60252 | 107 | 0.20888 | 0.9855 | 0.23911 | 0.76939 | 0.045091 | 0.38662 | 0.25766 | 75.3841 | 0.56684 | 7.4959 | 5353.41
662 | 0.18753 | 23 | 0.90786 | 0.14743 | 0.14933 | 0.65465 | 0.86967 | 111 | 0.18373 | 0.98019 | 0.47002 | 0.84336 | 0.97179 | 0.76584 | 0.72176 | 104.3186 | 0.17763 | 4.632 | 6553.2535
663 | 0.44878 | 25 | 0.59382 | 0.089612 | 0.50576 | 0.70058 | 0.13501 | 103 | 0.12007 | 0.96483 | 0.94093 | 1.0809 | 0.76494 | 0.66365 | 0.99902 | 147.2894 | 0.55112 | 7.361 | 6903.9259
664 | 0.76366 | 27 | 0.035809 | 0.018923 | 0.86238 | 0.74754 | 0.42881 | 106 | 0.025682 | 0.92998 | 0.8913 | 1.0385 | 0.70794 | 0.64572 | 0.26864 | 75.9379 | 0.51435 | 7.0543 | 6468.2182
665 | 0.097758 | 22 | 0.29365 | 0.054431 | 0.50032 | 0.70003 | 0.9249 | 112 | 0.44242 | 1.0291 | 0.5077 | 0.85627 | 0.78723 | 0.67124 | 0.55155 | 92.0053 | 0.12588 | 4.2157 | 6032.3261
666 | 0.84622 | 27 | 0.84669 | 0.13218 | 0.31025 | 0.67877 | 0.12373 | 103 | 0.39423 | 1.0198 | 0.10191 | 0.71058 | 0.46153 | 0.57713 | 0.49626 | 88.5344 | 0.86844 | 10.8644 | 6404.6254
667 | 0.26792 | 24 | 0.92556 | 0.15274 | 0.37084 | 0.68612 | 0.27848 | 105 | 0.27954 | 0.99891 | 0.22293 | 0.76356 | 0.082692 | 0.4173 | 0.50815 | 89.2639 | 0.015626 | 2.7806 | 5762.5802
668 | 0.37558 | 24 | 0.36351 | 0.061816 | 0.96815 | 0.77476 | 0.057542 | 102 | 0.3482 | 1.0112 | 0.415 | 0.8253 | 0.24317 | 0.50116 | 0.049689 | 61.1455 | 0.092176 | 3.896 | 5551.6515
669 | 0.78842 | 27 | 0.533 | 0.081636 | 0.14844 | 0.65449 | 0.67032 | 108 | 0.33251 | 1.0083 | 0.58171 | 0.88316 | 0.94202 | 0.74235 | 0.68366 | 101.2914 | 0.76026 | 9.4173 | 7072.3133
670 | 0.58663 | 25 | 0.37085 | 0.062615 | 0.58934 | 0.70937 | 0.41194 | 106 | 0.54909 | 1.0514 | 0.29531 | 0.78825 | 0.57389 | 0.60902 | 0.74684 | 106.4261 | 0.99951 | 14.7466 | 6344.4286
671 | 0.96178 | 29 | 0.5412 | 0.08268 | 0.17017 | 0.65834 | 0.2866 | 105 | 0.37656 | 1.0164 | 0.79841 | 0.98004 | 0.62884 | 0.62353 | 0.17227 | 70.7526 | 0.57575 | 7.5736 | 7054.8906
672 | 0.40141 | 24 | 0.43416 | 0.069711 | 0.182 | 0.66033 | 0.63626 | 108 | 0.78642 | 1.1133 | 0.81657 | 0.99018 | 0.41328 | 0.56224 | 0.87692 | 119.6169 | 0.14926 | 4.4127 | 6628.2169
673 | 0.54483 | 25 | 0.83181 | 0.12897 | 0.019235 | 0.61961 | 0.099279 | 103 | 0.35513 | 1.0125 | 0.69473 | 0.92933 | 0.12035 | 0.44152 | 0.24008 | 74.4991 | 0.73738 | 9.157 | 6134.2312
674 | 0.79676 | 27 | 0.15369 | 0.039203 | 0.081951 | 0.64048 | 0.24496 | 104 | 0.28199 | 0.99935 | 0.42669 | 0.82906 | 0.048249 | 0.3896 | 0.85598 | 117.1348 | 0.22675 | 4.9738 | 6083.5647
675 | 0.44182 | 25 | 0.93898 | 0.15721 | 0.57642 | 0.70796 | 0.63986 | 108 | 0.65913 | 1.0773 | 0.08731 | 0.70236 | 0.30895 | 0.52674 | 0.83396 | 114.7111 | 0.032921 | 3.1331 | 6324.388
676 | 0.12035 | 22 | 0.72205 | 0.10868 | 0.05492 | 0.63314 | 0.48 | 106 | 0.28806 | 1.0004 | 0.99114 | 1.1539 | 0.30701 | 0.52602 | 0.95139 | 130.9052 | 0.93416 | 12.0744 | 6422.3319
677 | 0.98403 | 29 | 0.51049 | 0.078817 | 0.90376 | 0.75613 | 0.064498 | 102 | 0.070064 | 0.94952 | 0.63857 | 0.90548 | 0.77305 | 0.66637 | 0.088144 | 64.8445 | 0.10827 | 4.0549 | 6612.8647
678 | 0.26567 | 24 | 0.90979 | 0.14798 | 0.61682 | 0.71246 | 0.61195 | 107 | 0.5092 | 1.0428 | 0.095108 | 0.70683 | 0.25443 | 0.50576 | 0.95874 | 132.4089 | 0.2165 | 4.9058 | 6153.1574
679 | 0.26856 | 24 | 0.31642 | 0.056796 | 0.87233 | 0.74947 | 0.42108 | 106 | 0.89537 | 1.1543 | 0.14014 | 0.72968 | 0.43683 | 0.56961 | 0.41588 | 83.8116 | 0.85135 | 10.604 | 6054.0387
680 | 0.93886 | 28 | 0.74096 | 0.11185 | 0.20643 | 0.66425 | 0.18546 | 104 | 0.76026 | 1.1052 | 0.79402 | 0.97766 | 0.69563 | 0.64208 | 0.10956 | 66.5501 | 0.1323 | 4.2715 | 7177.9023
681 | 0.59486 | 25 | 0.52254 | 0.080318 | 0.42301 | 0.69198 | 0.97952 | 113 | 0.036857 | 0.93592 | 0.24838 | 0.77264 | 0.68953 | 0.64031 | 0.79589 | 110.8744 | 0.10913 | 4.063 | 6240.6967
682 | 0.3848 | 24 | 0.49657 | 0.077106 | 0.038328 | 0.62769 | 0.79368 | 109 | 0.98318 | 1.2116 | 0.77246 | 0.96631 | 0.58369 | 0.61165 | 0.0026327 | 52.5655 | 0.83464 | 10.3635 | 6695.359
683 | 0.56482 | 25 | 0.83867 | 0.13043 | 0.3965 | 0.68905 | 0.27646 | 105 | 0.98118 | 1.2094 | 0.58353 | 0.88385 | 0.62497 | 0.62251 | 0.8861 | 120.7731 | 0.74882 | 9.2857 | 7067.6823
684 | 0.34588 | 24 | 0.82058 | 0.12663 | 0.91711 | 0.75928 | 0.9498 | 112 | 0.33383 | 1.0086 | 0.65519 | 0.91233 | 0.65741 | 0.63124 | 0.43005 | 84.6193 | 0.48261 | 6.7988 | 6338.8591
685 | 0.66092 | 26 | 0.60049 | 0.090523 | 0.68958 | 0.72121 | 0.97984 | 113 | 0.25621 | 0.9947 | 0.31814 | 0.79539 | 0.10298 | 0.4309 | 0.91366 | 124.5527 | 0.65015 | 8.256 | 6168.1688
686 | 0.77252 | 27 | 0.25088 | 0.050088 | 0.55023 | 0.70516 | 0.25062 | 104 | 0.63045 | 1.0702 | 0.0093387 | 0.63348 | 0.45407 | 0.57488 | 0.54496 | 91.581 | 0.10747 | 4.0473 | 6171.1727
687 | 0.31922 | 24 | 0.96841 | 0.16922 | 0.66106 | 0.71767 | 0.91908 | 112 | 0.38327 | 1.0177 | 0.84873 | 1.0095 | 0.19651 | 0.48083 | 0.34245 | 79.7743 | 0.40951 | 6.2385 | 6278.0287
688 | 0.7858 | 27 | 0.029165 | 0.017078 | 0.47981 | 0.69796 | 0.98565 | 114 | 0.23653 | 0.99099 | 0.86434 | 1.0196 | 0.74558 | 0.65734 | 0.0079565 | 54.4599 | 0.24546 | 5.096 | 6662.2041
689 | 0.5248 | 25 | 0.1021 | 0.031953 | 0.48621 | 0.69861 | 0.13028 | 103 | 0.90608 | 1.1593 | 0.089769 | 0.70379 | 0.035031 | 0.37635 | 0.29467 | 77.2675 | 0.87162 | 10.9148 | 5695.4077
690 | 0.35516 | 24 | 0.081925 | 0.028623 | 0.081672 | 0.64042 | 0.21376 | 104 | 0.28764 | 1.0003 | 0.3026 | 0.79056 | 0.032647 | 0.37371 | 0.051281 | 61.3226 | 0.42579 | 6.3601 | 5358.2957
691 | 0.43534 | 25 | 0.799 | 0.12235 | 0.28327 | 0.67527 | 0.44118 | 106 | 0.084907 | 0.95451 | 0.39515 | 0.81899 | 0.64101 | 0.62678 | 0.12185 | 67.4532 | 0.069971 | 3.6519 | 6139.6858
692 | 0.13 | 23 | 0.26459 | 0.051466 | 0.66761 | 0.71847 | 0.95938 | 113 | 0.94484 | 1.1805 | 0.19295 | 0.75217 | 0.04958 | 0.39083 | 0.48854 | 88.0651 | 0.98877 | 13.7919 | 5775.4006
693 | 0.99014 | 29 | 0.4733 | 0.074298 | 0.66238 | 0.71783 | 0.2571 | 104 | 0.53926 | 1.0492 | 0.0016058 | 0.61388 | 0.70769 | 0.64564 | 0.74774 | 106.5039 | 0.87293 | 10.9356 | 6639.3475
694 | 0.89373 | 28 | 0.37917 | 0.063527 | 0.32565 | 0.6807 | 0.1739 | 104 | 0.88403 | 1.1493 | 0.0090704 | 0.63299 | 0.55031 | 0.60261 | 0.44109 | 85.2555 | 0.30944 | 5.5252 | 6594.2394
695 | 0.78302 | 27 | 0.012163 | 0.011028 | 0.94909 | 0.76809 | 0.71486 | 108 | 0.97011 | 1.1989 | 0.040101 | 0.66937 | 0.19372 | 0.47954 | 0.56424 | 92.8317 | 0.025782 | 3.0027 | 6165.9007
696 | 0.99275 | 29 | 0.1634 | 0.040423 | 0.038364 | 0.6277 | 0.84653 | 110 | 0.41685 | 1.0241 | 0.26557 | 0.77852 | 0.61451 | 0.61977 | 0.23966 | 74.4775 | 0.49991 | 6.937 | 6761.7646
697 | 0.80333 | 27 | 0.25866 | 0.050868 | 0.50877 | 0.70088 | 0.40859 | 106 | 0.088589 | 0.95568 | 0.16562 | 0.74098 | 0.81568 | 0.68155 | 0.68825 | 101.6456 | 0.89589 | 11.3212 | 6417.5557
698 | 0.0025911 | 20 | 0.70198 | 0.10545 | 0.18785 | 0.66129 | 0.53816 | 107 | 0.97822 | 1.2063 | 0.62963 | 0.90186 | 0.54419 | 0.60092 | 0.15642 | 69.7748 | 0.91206 | 11.6189 | 6013.6728
699 | 0.058784 | 22 | 0.88688 | 0.14174 | 0.17854 | 0.65976 | 0.34305 | 105 | 0.14143 | 0.97036 | 0.69936 | 0.93139 | 0.77602 | 0.66738 | 0.41181 | 83.5814 | 0.66194 | 8.3707 | 6148.8189
700 | 0.78009 | 27 | 0.6153 | 0.092571 | 0.82899 | 0.74152 | 0.96701 | 113 | 0.51263 | 1.0435 | 0.10731 | 0.71348 | 0.43013 | 0.56753 | 0.71268 | 103.5787 | 0.063627 | 3.5753 | 6435.6215
701 | 0.22339 | 23 | 0.51905 | 0.079881 | 0.79005 | 0.7352 | 0.81192 | 110 | 0.75346 | 1.1031 | 0.42742 | 0.8293 | 0.39749 | 0.55718 | 0.86368 | 118.0255 | 0.61377 | 7.9141 | 6200.1178
702 | 0.78371 | 27 | 0.13563 | 0.036828 | 0.37456 | 0.68655 | 0.60423 | 107 | 0.13572 | 0.96892 | 0.69527 | 0.92956 | 0.68525 | 0.63908 | 0.072093 | 63.4251 | 0.75356 | 9.3399 | 6457.8467
703 | 0.24601 | 24 | 0.043384 | 0.020829 | 0.44463 | 0.6943 | 0.48348 | 106 | 0.40122 | 1.0211 | 0.59643 | 0.88878 | 0.74882 | 0.65837 | 0.46841 | 86.8577 | 0.70753 | 8.8339 | 6187.3374
704 | 0.20299 | 23 | 0.35397 | 0.060785 | 0.78293 | 0.73411 | 0.71146 | 108 | 0.87333 | 1.1447 | 0.077729 | 0.69658 | 0.62245 | 0.62185 | 0.2709 | 76.0526 | 0.418 | 6.3017 | 5955.5772
705 | 0.78983 | 27 | 0.58774 | 0.088789 | 0.067008 | 0.63661 | 0.2282 | 104 | 0.66229 | 1.0781 | 0.53735 | 0.86678 | 0.3462 | 0.54002 | 0.8879 | 121.004 | 0.17295 | 4.5971 | 6798.2993
706 | 0.18366 | 23 | 0.24044 | 0.049034 | 0.13047 | 0.65108 | 0.85088 | 110 | 0.25096 | 0.99372 | 0.012861 | 0.63928 | 0.35473 | 0.54295 | 0.60147 | 95.3287 | 0.30313 | 5.482 | 5619.7462
707 | 0.32212 | 24 | 0.60234 | 0.090777 | 0.56583 | 0.70681 | 0.99455 | 114 | 0.46077 | 1.0328 | 0.44463 | 0.83491 | 0.21369 | 0.48857 | 0.61045 | 95.9482 | 0.14929 | 4.4129 | 6035.636
708 | 0.18425 | 23 | 0.66829 | 0.10024 | 0.31006 | 0.67875 | 0.88641 | 111 | 0.70598 | 1.0896 | 0.90057 | 1.0455 | 0.41047 | 0.56135 | 0.98289 | 138.6703 | 0.6845 | 8.5957 | 6690.6923
709 | 0.24928 | 24 | 0.72833 | 0.10972 | 0.69182 | 0.72149 | 0.52176 | 107 | 0.44162 | 1.029 | 0.42722 | 0.82923 | 0.34612 | 0.53999 | 0.040617 | 60.0768 | 0.19755 | 4.7757 | 5896.1746
710 | 0.67421 | 26 | 0.94901 | 0.16089 | 0.68756 | 0.72095 | 0.98133 | 113 | 0.78317 | 1.1123 | 0.8518 | 1.0114 | 0.25237 | 0.50493 | 0.69928 | 102.5086 | 0.53016 | 7.1847 | 6924.5124
711 | 0.72564 | 26 | 0.3843 | 0.064092 | 0.66148 | 0.71772 | 0.70421 | 108 | 0.51589 | 1.0442 | 0.27919 | 0.78304 | 0.13711 | 0.45105 | 0.82846 | 114.1314 | 0.93584 | 12.1119 | 6152.9902
712 | 0.8888 | 28 | 0.14729 | 0.038378 | 0.61738 | 0.71252 | 0.95482 | 112 | 0.68738 | 1.0846 | 0.068689 | 0.69079 | 0.58894 | 0.61305 | 0.65355 | 99.026 | 0.060179 | 3.532 | 6621.4365
713 | 0.99935 | 30 | 0.76414 | 0.11588 | 0.63036 | 0.71402 | 0.34718 | 105 | 0.18468 | 0.9804 | 0.050386 | 0.67776 | 0.62155 | 0.62161 | 0.46205 | 86.4812 | 0.51872 | 7.0901 | 6637.2581
714 | 0.2051 | 23 | 0.77304 | 0.11748 | 0.28386 | 0.67535 | 0.87738 | 111 | 0.76768 | 1.1074 | 0.4468 | 0.83563 | 0.29541 | 0.52171 | 0.33241 | 79.2403 | 0.462 | 6.637 | 6109.1155
715 | 0.97995 | 29 | 0.92001 | 0.15101 | 0.92131 | 0.76033 | 0.37605 | 105 | 0.097916 | 0.95854 | 0.71598 | 0.93892 | 0.0074857 | 0.33529 | 0.15171 | 69.4753 | 0.15465 | 4.4558 | 6116.7931
716 | 0.15798 | 23 | 0.19484 | 0.044141 | 0.88075 | 0.75116 | 0.33558 | 105 | 0.33868 | 1.0094 | 0.25116 | 0.77361 | 0.27445 | 0.5137 | 0.20203 | 72.4739 | 0.41134 | 6.2521 | 5478.3228
717 | 0.21928 | 23 | 0.48009 | 0.075111 | 0.080365 | 0.64009 | 0.95299 | 112 | 0.76148 | 1.1055 | 0.17773 | 0.74604 | 0.0051483 | 0.32927 | 0.60859 | 95.8191 | 0.94906 | 12.4266 | 5665.1834
718 | 0.87124 | 27 | 0.30191 | 0.055284 | 0.73687 | 0.72746 | 0.46981 | 106 | 0.11325 | 0.96296 | 0.48626 | 0.84886 | 0.12344 | 0.44332 | 0.67432 | 100.5776 | 0.12277 | 4.1882 | 6017.0298
719 | 0.60992 | 26 | 0.52596 | 0.080748 | 0.030515 | 0.6247 | 0.17746 | 104 | 0.99982 | 1.246 | 0.7402 | 0.95029 | 0.97285 | 0.76686 | 0.49488 | 88.4502 | 0.25084 | 5.1313 | 7604.4057
720 | 0.87003 | 27 | 0.856 | 0.13427 | 0.041485 | 0.6288 | 0.49587 | 106 | 0.80303 | 1.1187 | 0.48491 | 0.8484 | 0.56425 | 0.60642 | 0.89849 | 122.4082 | 0.59808 | 7.7716 | 7191.6306
721 | 0.20207 | 23 | 0.20448 | 0.04522 | 0.74705 | 0.72887 | 0.37176 | 105 | 0.0066149 | 0.91522 | 0.96635 | 1.1101 | 0.036358 | 0.37778 | 0.15712 | 69.8191 | 0.85992 | 10.7326 | 5485.9718
722 | 0.92993 | 28 | 0.45308 | 0.071908 | 0.44019 | 0.69383 | 0.38188 | 105 | 0.90017 | 1.1565 | 0.77484 | 0.96754 | 0.57221 | 0.60857 | 0.90691 | 123.5764 | 0.7036 | 8.7926 | 7381.6489
723 | 0.49293 | 25 | 0.76601 | 0.11622 | 0.24465 | 0.66995 | 0.68464 | 108 | 0.99425 | 1.2276 | 0.9823 | 1.1348 | 0.83866 | 0.69046 | 0.90994 | 124.0111 | 0.6735 | 8.485 | 7709.2504
724 | 0.30814 | 24 | 0.050861 | 0.022552 | 0.50336 | 0.70034 | 0.0078336 | 101 | 0.65716 | 1.0768 | 0.28994 | 0.78653 | 0.14947 | 0.45771 | 0.25496 | 75.2486 | 0.058845 | 3.5149 | 5603.0909
725 | 0.3987 | 24 | 0.65516 | 0.098288 | 0.64011 | 0.71516 | 0.93942 | 112 | 0.32412 | 1.0068 | 0.31959 | 0.79583 | 0.50786 | 0.5907 | 0.84425 | 115.8218 | 0.59269 | 7.7233 | 6241.926
726 | 0.62597 | 26 | 0.21227 | 0.046072 | 0.18208 | 0.66035 | 0.63851 | 108 | 0.011962 | 0.92046 | 0.89699 | 1.0428 | 0.77284 | 0.6663 | 0.14433 | 68.9952 | 0.11012 | 4.0724 | 6504.3186
727 | 0.3486 | 24 | 0.38596 | 0.064275 | 0.54151 | 0.70424 | 0.45931 | 106 | 0.77422 | 1.1094 | 0.33121 | 0.79936 | 0.20267 | 0.48364 | 0.89298 | 121.6687 | 0.45873 | 6.6116 | 6124.9782
728 | 0.75156 | 26 | 0.58722 | 0.088719 | 0.010969 | 0.61481 | 0.646 | 108 | 0.66647 | 1.0792 | 0.064042 | 0.68766 | 0.872 | 0.70462 | 0.087822 | 64.8174 | 0.62133 | 7.9838 | 6586.6045
729 | 0.22683 | 23 | 0.058579 | 0.024203 | 0.85391 | 0.74595 | 0.37673 | 105 | 0.88883 | 1.1514 | 0.18683 | 0.74973 | 0.49178 | 0.58606 | 0.0963 | 65.5161 | 0.35253 | 5.8255 | 5776.2493
730 | 0.81248 | 27 | 0.69595 | 0.10449 | 0.73706 | 0.72748 | 0.70187 | 108 | 0.99091 | 1.2218 | 0.16483 | 0.74064 | 0.50781 | 0.59069 | 0.11351 | 66.8457 | 0.39218 | 6.1109 | 6746.2766
731 | 0.33167 | 24 | 0.51188 | 0.078989 | 0.5124 | 0.70125 | 0.26921 | 104 | 0.82735 | 1.1271 | 0.23958 | 0.76956 | 0.8284 | 0.68641 | 0.86231 | 117.8642 | 0.21958 | 4.9263 | 6532.6455
732 | 0.7461 | 26 | 0.49034 | 0.076348 | 0.10824 | 0.64653 | 0.92439 | 112 | 0.68447 | 1.0838 | 0.66485 | 0.91639 | 0.6379 | 0.62594 | 0.9867 | 140.012 | 0.69283 | 8.6808 | 7120.9708
733 | 0.30804 | 24 | 0.25679 | 0.050681 | 0.26493 | 0.67279 | 0.68892 | 108 | 0.77619 | 1.1101 | 0.84522 | 1.0073 | 0.19836 | 0.48168 | 0.81418 | 112.6689 | 0.08663 | 3.8381 | 6359.7275
734 | 0.60612 | 26 | 0.59215 | 0.089386 | 0.72296 | 0.72556 | 0.617 | 107 | 0.093085 | 0.95708 | 0.67586 | 0.92109 | 0.6264 | 0.62289 | 0.95884 | 132.4292 | 0.009329 | 2.6032 | 6616.0722
735 | 0.26101 | 24 | 0.92196 | 0.15161 | 0.48939 | 0.69893 | 0.75607 | 109 | 0.51707 | 1.0444 | 0.75355 | 0.95679 | 0.48829 | 0.58505 | 0.95803 | 132.2586 | 0.010099 | 2.6276 | 6686.8624
736 | 0.043203 | 21 | 0.24512 | 0.04951 | 0.42963 | 0.6927 | 0.56324 | 107 | 0.52349 | 1.0458 | 0.26036 | 0.77676 | 0.029137 | 0.36963 | 0.70301 | 102.8048 | 0.069087 | 3.6415 | 5277.6169
737 | 0.89243 | 28 | 0.72438 | 0.10907 | 0.21055 | 0.66489 | 0.10314 | 103 | 0.57913 | 1.0581 | 0.88079 | 1.0309 | 0.036353 | 0.37778 | 0.079566 | 64.1037 | 0.22828 | 4.9838 | 6420.3089
738 | 0.53076 | 25 | 0.96398 | 0.16713 | 0.906 | 0.75664 | 0.11539 | 103 | 0.34755 | 1.0111 | 0.82436 | 0.99469 | 0.37098 | 0.54846 | 0.61631 | 96.3562 | 0.97925 | 13.3577 | 6492.381
739 | 0.20398 | 23 | 0.038955 | 0.019737 | 0.80716 | 0.7379 | 0.44498 | 106 | 0.83877 | 1.1312 | 0.58005 | 0.88253 | 0.78935 | 0.67199 | 0.19545 | 72.1046 | 0.10917 | 4.0634 | 6128.7534
740 | 0.10438 | 22 | 0.82853 | 0.12828 | 0.55382 | 0.70554 | 0.48114 | 106 | 0.68768 | 1.0847 | 0.68678 | 0.92582 | 0.91636 | 0.72673 | 0.80272 | 111.5345 | 0.3664 | 5.9243 | 6540.6342
741 | 0.084568 | 22 | 0.7382 | 0.11138 | 0.15706 | 0.65605 | 0.13042 | 103 | 0.86106 | 1.1397 | 0.64971 | 0.91005 | 0.85628 | 0.69774 | 0.54728 | 91.7296 | 0.63637 | 8.1246 | 6481.1981
742 | 0.01645 | 21 | 0.23405 | 0.048379 | 0.75445 | 0.72992 | 0.041121 | 102 | 0.98628 | 1.2154 | 0.51255 | 0.85797 | 0.94633 | 0.74529 | 0.62294 | 96.8216 | 0.35539 | 5.8458 | 6247.8885
743 | 0.50735 | 25 | 0.085056 | 0.029164 | 0.48735 | 0.69873 | 0.55686 | 107 | 0.83632 | 1.1303 | 0.91367 | 1.0561 | 0.13062 | 0.44743 | 0.22698 | 73.8213 | 0.81232 | 10.0605 | 6267.9442
744 | 0.86145 | 27 | 0.76343 | 0.11576 | 0.096455 | 0.64392 | 0.76535 | 109 | 0.048154 | 0.94105 | 0.4192 | 0.82665 | 0.53882 | 0.59943 | 0.48987 | 88.1453 | 0.39119 | 6.1036 | 6500.4239
745 | 0.14752 | 23 | 0.27698 | 0.052722 | 0.97003 | 0.77552 | 0.98167 | 113 | 0.70138 | 1.0884 | 0.28875 | 0.78615 | 0.49091 | 0.58581 | 0.93872 | 128.5624 | 0.47286 | 6.7218 | 6149.0691
746 | 0.16695 | 23 | 0.10775 | 0.032825 | 0.95701 | 0.77068 | 0.72108 | 109 | 0.82736 | 1.1271 | 0.57971 | 0.8824 | 0.21873 | 0.49078 | 0.59152 | 94.6502 | 0.24567 | 5.0974 | 5883.5392
747 | 0.21233 | 23 | 0.50477 | 0.078111 | 0.58069 | 0.70842 | 0.53501 | 107 | 0.37272 | 1.0157 | 0.74905 | 0.95459 | 0.93268 | 0.73633 | 0.90923 | 123.9088 | 0.21168 | 4.8733 | 6565.674
748 | 0.89046 | 28 | 0.71378 | 0.10734 | 0.67622 | 0.71953 | 0.74094 | 109 | 0.91995 | 1.1663 | 0.076797 | 0.696 | 0.45972 | 0.57658 | 0.111 | 66.6584 | 0.32901 | 5.6603 | 6686.1241
749 | 0.070015 | 22 | 0.75125 | 0.11361 | 0.59402 | 0.70989 | 0.43629 | 106 | 0.63292 | 1.0708 | 0.52293 | 0.86163 | 0.59084 | 0.61355 | 0.46896 | 86.8904 | 0.732 | 9.0975 | 6060.2447
750 | 0.66019 | 26 | 0.54721 | 0.083451 | 0.40793 | 0.69033 | 0.46764 | 106 | 0.27522 | 0.99815 | 0.40835 | 0.82318 | 0.32158 | 0.53133 | 0.30536 | 77.8212 | 0.37474 | 5.9843 | 6129.3937
751 | 0.72125 | 26 | 0.9596 | 0.16519 | 0.54376 | 0.70448 | 0.72607 | 109 | 0.58402 | 1.0592 | 0.93075 | 1.0711 | 0.39436 | 0.55617 | 0.70496 | 102.9596 | 0.45114 | 6.553 | 7001.2664
752 | 0.67317 | 26 | 0.33805 | 0.05908 | 0.55204 | 0.70535 | 0.74388 | 109 | 0.18184 | 0.97978 | 0.16085 | 0.73893 | 0.79215 | 0.67298 | 0.48829 | 88.05 | 0.61411 | 7.9172 | 6286.7686
753 | 0.48199 | 25 | 0.2555 | 0.050551 | 0.83264 | 0.74215 | 0.41218 | 106 | 0.5652 | 1.0549 | 0.19316 | 0.75225 | 0.1241 | 0.4437 | 0.76877 | 108.3562 | 0.96498 | 12.8664 | 5888.2956
754 | 0.6268 | 26 | 0.097471 | 0.03122 | 0.39557 | 0.68895 | 0.25626 | 104 | 0.040483 | 0.93764 | 0.97019 | 1.1154 | 0.18641 | 0.47612 | 0.8221 | 113.4724 | 0.38484 | 6.0574 | 6327.9127
755 | 0.68749 | 26 | 0.86411 | 0.13615 | 0.95813 | 0.77106 | 0.7564 | 109 | 0.83603 | 1.1302 | 0.10413 | 0.71178 | 0.20734 | 0.48575 | 0.34707 | 80.0214 | 0.91194 | 11.6166 | 6235.2634
756 | 0.65536 | 26 | 0.50835 | 0.078553 | 0.62386 | 0.71327 | 0.69617 | 108 | 0.70336 | 1.0889 | 0.82359 | 0.99423 | 0.97599 | 0.77003 | 0.14457 | 69.0115 | 0.29676 | 5.4386 | 7089.8443
757 | 0.59991 | 26 | 0.042783 | 0.020684 | 0.75397 | 0.72985 | 0.12352 | 103 | 0.21833 | 0.98742 | 0.30216 | 0.79042 | 0.51667 | 0.59321 | 0.95141 | 130.9097 | 0.024495 | 2.9774 | 6213.1969
758 | 0.94654 | 28 | 0.47123 | 0.074052 | 0.22394 | 0.66692 | 0.56653 | 107 | 0.60459 | 1.064 | 0.13702 | 0.72823 | 0.056631 | 0.39707 | 0.41615 | 83.8267 | 0.34448 | 5.7687 | 6130.5402
759 | 0.55434 | 25 | 0.48406 | 0.075588 | 0.92281 | 0.76071 | 0.73723 | 109 | 0.3044 | 1.0033 | 0.42177 | 0.82747 | 0.38506 | 0.55313 | 0.53038 | 90.6522 | 0.12808 | 4.235 | 6048.7332
760 | 0.29518 | 24 | 0.20958 | 0.04578 | 0.93636 | 0.76432 | 0.32766 | 105 | 0.26407 | 0.99614 | 0.88481 | 1.0337 | 0.25609 | 0.50643 | 0.11938 | 67.276 | 0.71765 | 8.9415 | 5871.0991
761 | 0.2083 | 23 | 0.066656 | 0.025818 | 0.067884 | 0.63685 | 0.73925 | 109 | 0.70917 | 1.0905 | 0.1724 | 0.74383 | 0.39244 | 0.55554 | 0.87922 | 119.9021 | 0.86337 | 10.7855 | 6077.5343
762 | 0.98714 | 29 | 0.71118 | 0.10692 | 0.63936 | 0.71507 | 0.3509 | 105 | 0.31854 | 1.0058 | 0.86024 | 1.0169 | 0.96899 | 0.76321 | 0.2985 | 77.4655 | 0.38347 | 6.0474 | 7442.5026
763 | 0.48714 | 25 | 0.4257 | 0.06874 | 0.048072 | 0.63101 | 0.48333 | 106 | 0.25693 | 0.99483 | 0.024741 | 0.65449 | 0.74693 | 0.65777 | 0.15886 | 69.9285 | 0.40439 | 6.2006 | 6018.5413
764 | 0.30162 | 24 | 0.55863 | 0.08493 | 0.015153 | 0.61741 | 0.91274 | 111 | 0.093275 | 0.95714 | 0.095074 | 0.70681 | 0.21201 | 0.48782 | 0.91002 | 124.0223 | 0.37188 | 5.9636 | 5918.622
765 | 0.33611 | 24 | 0.01767 | 0.013293 | 0.18363 | 0.6606 | 0.55872 | 107 | 0.32134 | 1.0063 | 0.36945 | 0.81099 | 0.84318 | 0.69229 | 0.16906 | 70.5584 | 0.25988 | 5.1911 | 6053.2183
766 | 0.63583 | 26 | 0.37913 | 0.063523 | 0.073589 | 0.63836 | 0.62354 | 107 | 0.84432 | 1.1333 | 0.42148 | 0.82738 | 0.051404 | 0.39249 | 0.19681 | 72.1817 | 0.7515 | 9.3163 | 6124.5547
767 | 0.50231 | 25 | 0.49733 | 0.077199 | 0.53985 | 0.70407 | 0.22781 | 104 | 0.9643 | 1.1941 | 0.70854 | 0.93552 | 0.90878 | 0.7226 | 0.66536 | 99.9022 | 0.026973 | 3.0256 | 7060.2731
768 | 0.58639 | 25 | 0.76042 | 0.11522 | 0.34712 | 0.68332 | 0.87457 | 111 | 0.94252 | 1.1791 | 0.7866 | 0.97369 | 0.43274 | 0.56834 | 0.22118 | 73.5148 | 0.43675 | 6.443 | 6801.5062
769 | 0.65002 | 26 | 0.87065 | 0.13771 | 0.14153 | 0.6532 | 0.38784 | 105 | 0.8224 | 1.1253 | 0.36114 | 0.80843 | 0.33658 | 0.53666 | 0.67388 | 100.544 | 0.59798 | 7.7707 | 6680.5458
770 | 0.39335 | 24 | 0.32181 | 0.057362 | 0.82818 | 0.74138 | 0.091 | 103 | 0.13176 | 0.96791 | 0.67528 | 0.92083 | 0.90535 | 0.72078 | 0.8623 | 117.8635 | 0.69688 | 8.7226 | 6381.7726
771 | 0.97702 | 29 | 0.702 | 0.10545 | 0.76494 | 0.73143 | 0.57432 | 107 | 0.77521 | 1.1098 | 0.53901 | 0.86738 | 0.86977 | 0.70362 | 0.65929 | 99.4501 | 0.98481 | 13.5948 | 7445.2324
772 | 0.47541 | 25 | 0.41494 | 0.067517 | 0.56018 | 0.70621 | 0.34997 | 105 | 0.32378 | 1.0068 | 0.60443 | 0.89188 | 0.10567 | 0.4326 | 0.22219 | 73.5685 | 0.8178 | 10.1331 | 5834.6713
773 | 0.11705 | 22 | 0.3448 | 0.059801 | 0.63822 | 0.71494 | 0.86063 | 110 | 0.036682 | 0.93583 | 0.92695 | 1.0676 | 0.91031 | 0.72342 | 0.85347 | 116.8498 | 0.048906 | 3.3811 | 6316.3859
774 | 0.0691 | 22 | 0.87881 | 0.1397 | 0.29463 | 0.67676 | 0.019804 | 101 | 0.65766 | 1.0769 | 0.030457 | 0.66046 | 0.76873 | 0.66491 | 0.66179 | 99.6357 | 0.26081 | 5.1972 | 5998.2939
775 | 0.62453 | 26 | 0.12608 | 0.035507 | 0.21326 | 0.66531 | 0.9948 | 114 | 0.77793 | 1.1106 | 0.96685 | 1.1108 | 0.85626 | 0.69773 | 0.49815 | 88.6495 | 0.99968 | 14.7945 | 7354.8238
776 | 0.50399 | 25 | 0.88396 | 0.141 | 0.69827 | 0.72232 | 0.38438 | 105 | 0.5868 | 1.0599 | 0.11968 | 0.71984 | 0.40698 | 0.56024 | 0.076878 | 63.8634 | 0.13108 | 4.261 | 6041.1299
777 | 0.61015 | 26 | 0.65109 | 0.09769 | 0.9516 | 0.76889 | 0.0066343 | 101 | 0.081679 | 0.95347 | 0.31304 | 0.79382 | 0.8281 | 0.68629 | 0.93793 | 128.4238 | 0.35539 | 5.8458 | 6422.5167
778 | 0.66266 | 26 | 0.52026 | 0.080033 | 0.80233 | 0.73712 | 0.91196 | 111 | 0.49111 | 1.039 | 0.28882 | 0.78617 | 0.1553 | 0.46076 | 0.21427 | 73.1448 | 0.61203 | 7.8982 | 5988.6864
779 | 0.77253 | 27 | 0.18188 | 0.042647 | 0.25138 | 0.67091 | 0.45852 | 106 | 0.65194 | 1.0755 | 0.064842 | 0.68821 | 0.19563 | 0.48042 | 0.67694 | 100.7765 | 0.053025 | 3.438 | 6157.7967
780 | 0.42881 | 25 | 0.59606 | 0.089917 | 0.83943 | 0.74333 | 0.41456 | 106 | 0.089795 | 0.95606 | 0.94403 | 1.0841 | 0.94955 | 0.74757 | 0.53247 | 90.7844 | 0.95253 | 12.5159 | 6798.5966
781 | 0.5926 | 25 | 0.084469 | 0.029064 | 0.14789 | 0.65439 | 0.24045 | 104 | 0.66677 | 1.0792 | 0.14581 | 0.73228 | 0.18165 | 0.47386 | 0.74452 | 106.2267 | 0.29613 | 5.4343 | 5969.2324
782 | 0.6428 | 26 | 0.78422 | 0.11954 | 0.18648 | 0.66107 | 0.76875 | 109 | 0.45231 | 1.0311 | 4.5151e-05 | 0.60233 | 0.66412 | 0.6331 | 0.67892 | 100.9274 | 0.13748 | 4.3155 | 6356.9989
783 | 0.70065 | 26 | 0.69306 | 0.10404 | 0.30465 | 0.67806 | 0.84281 | 110 | 0.87693 | 1.1462 | 0.98359 | 1.1373 | 0.37322 | 0.54921 | 0.69555 | 102.2155 | 0.043862 | 3.3079 | 7167.8367
784 | 0.4973 | 25 | 0.34781 | 0.060122 | 0.46946 | 0.6969 | 0.13359 | 103 | 0.74549 | 1.1008 | 0.46628 | 0.8421 | 0.085191 | 0.41906 | 0.035369 | 59.4033 | 0.25049 | 5.129 | 5798.4791
785 | 0.85284 | 27 | 0.059901 | 0.024475 | 0.72286 | 0.72555 | 0.15295 | 103 | 0.26594 | 0.99648 | 0.56672 | 0.87753 | 0.36875 | 0.54771 | 0.46008 | 86.3652 | 0.0051844 | 2.4497 | 6180.8269
786 | 0.0029146 | 20 | 0.88278 | 0.1407 | 0.273 | 0.67389 | 0.97511 | 113 | 0.001918 | 0.90819 | 0.77031 | 0.96521 | 0.24891 | 0.50351 | 0.68754 | 101.5908 | 0.077898 | 3.743 | 5622.5382
787 | 0.21153 | 23 | 0.24089 | 0.049081 | 0.44666 | 0.69452 | 0.076756 | 102 | 0.59184 | 1.061 | 0.80916 | 0.98599 | 0.053543 | 0.39439 | 0.54164 | 91.368 | 0.63215 | 8.0848 | 5736.618
788 | 0.72957 | 26 | 0.59249 | 0.089431 | 0.033519 | 0.62589 | 0.84922 | 110 | 0.81365 | 1.1223 | 0.44267 | 0.83427 | 0.2724 | 0.5129 | 0.16931 | 70.5738 | 0.043137 | 3.2971 | 6473.2123
789 | 0.24201 | 23 | 0.2831 | 0.053348 | 0.7262 | 0.726 | 0.093495 | 103 | 0.77945 | 1.1111 | 0.70497 | 0.9339 | 0.92773 | 0.73331 | 0.25506 | 75.2533 | 0.93218 | 12.0306 | 6394.6325
790 | 0.34962 | 24 | 0.10809 | 0.032877 | 0.45996 | 0.69591 | 0.24079 | 104 | 0.26003 | 0.9954 | 0.36541 | 0.80974 | 0.11179 | 0.43639 | 0.31976 | 78.5732 | 0.34257 | 5.7552 | 5526.6242
791 | 0.81603 | 27 | 0.32883 | 0.058102 | 0.31235 | 0.67904 | 0.99683 | 114 | 0.40993 | 1.0228 | 0.19043 | 0.75117 | 0.60315 | 0.6168 | 0.54119 | 91.3394 | 0.75578 | 9.3655 | 6542.7784
792 | 0.51802 | 25 | 0.52685 | 0.080859 | 0.53833 | 0.70391 | 0.31604 | 105 | 0.54927 | 1.0514 | 0.96914 | 1.1139 | 0.8836 | 0.70997 | 0.5323 | 90.7739 | 0.19491 | 4.7571 | 6961.1012
793 | 0.74382 | 26 | 0.50387 | 0.078 | 0.50659 | 0.70066 | 0.54869 | 107 | 0.5516 | 1.0519 | 0.66922 | 0.91824 | 0.71254 | 0.6471 | 0.34865 | 80.1064 | 0.00086438 | 2.1836 | 6629.3783
794 | 0.93971 | 28 | 0.88579 | 0.14147 | 0.66553 | 0.71821 | 0.45137 | 106 | 0.34516 | 1.0106 | 0.98164 | 1.1336 | 0.31186 | 0.5278 | 0.079297 | 64.0799 | 0.78225 | 9.6796 | 6917.2818
795 | 0.93185 | 28 | 0.072102 | 0.026852 | 0.19601 | 0.66261 | 0.9917 | 114 | 0.82685 | 1.1269 | 0.54397 | 0.86917 | 0.42601 | 0.56625 | 0.75526 | 107.1564 | 0.65983 | 8.35 | 7033.695
796 | 0.93913 | 28 | 0.41222 | 0.067209 | 0.34728 | 0.68334 | 0.8955 | 111 | 0.054084 | 0.94351 | 0.27349 | 0.78116 | 0.39638 | 0.55682 | 0.98193 | 138.3582 | 0.4188 | 6.3077 | 6586.819
797 | 0.60607 | 26 | 0.96897 | 0.16949 | 0.57442 | 0.70774 | 0.68919 | 108 | 0.34593 | 1.0108 | 0.82285 | 0.9938 | 0.61157 | 0.61901 | 0.03308 | 59.094 | 0.14505 | 4.3784 | 6693.1243
798 | 0.46808 | 25 | 0.39111 | 0.064846 | 0.41175 | 0.69075 | 0.2605 | 104 | 0.46351 | 1.0333 | 0.38139 | 0.81469 | 0.43412 | 0.56877 | 0.98007 | 137.7745 | 0.55814 | 7.421 | 6384.8992
799 | 0.50729 | 25 | 0.56582 | 0.085872 | 0.038723 | 0.62783 | 0.040697 | 102 | 0.92637 | 1.1697 | 0.20634 | 0.75736 | 0.73699 | 0.65461 | 0.10274 | 66.0269 | 0.5185 | 7.0883 | 6548.1207
800 | 0.051675 | 22 | 0.51291 | 0.079117 | 0.15993 | 0.65656 | 0.41432 | 106 | 0.52018 | 1.0451 | 0.05073 | 0.67802 | 0.41568 | 0.563 | 0.41115 | 83.5441 | 0.46856 | 6.6881 | 5648.0554
801 | 0.20946 | 23 | 0.32116 | 0.057294 | 0.99762 | 0.79311 | 0.37002 | 105 | 0.64385 | 1.0735 | 0.84058 | 1.0044 | 0.19375 | 0.47956 | 0.97937 | 137.5615 | 0.94783 | 12.3956 | 6142.7893
802 | 0.092618 | 22 | 0.072721 | 0.026967 | 0.73426 | 0.7271 | 0.69814 | 108 | 0.22455 | 0.98865 | 0.94298 | 1.083 | 0.086089 | 0.41969 | 0.74215 | 106.024 | 0.077318 | 3.7365 | 5672.4577
803 | 0.1489 | 23 | 0.040174 | 0.020043 | 0.69553 | 0.72197 | 0.61343 | 107 | 0.073203 | 0.95062 | 0.26535 | 0.77844 | 0.67719 | 0.63677 | 0.76669 | 108.1689 | 0.89088 | 11.2337 | 5802.9815
804 | 0.22495 | 23 | 0.92939 | 0.15397 | 0.14318 | 0.65351 | 0.53994 | 107 | 0.11964 | 0.96471 | 0.72107 | 0.94127 | 0.050047 | 0.39126 | 0.46771 | 86.8165 | 0.32648 | 5.6428 | 5797.1455
805 | 0.8029 | 27 | 0.41845 | 0.067915 | 0.51014 | 0.70102 | 0.95369 | 112 | 0.11912 | 0.96457 | 0.29829 | 0.78919 | 0.5129 | 0.59214 | 0.65416 | 99.0706 | 0.25229 | 5.1409 | 6389.9517
806 | 0.51906 | 25 | 0.49594 | 0.077029 | 0.79184 | 0.73548 | 0.58795 | 107 | 0.080146 | 0.95296 | 0.7868 | 0.9738 | 0.30245 | 0.52434 | 0.27482 | 76.2515 | 0.056398 | 3.4831 | 6020.6783
807 | 0.44975 | 25 | 0.16987 | 0.041215 | 0.0052783 | 0.61027 | 0.50544 | 106 | 0.53187 | 1.0476 | 0.50694 | 0.856 | 0.70081 | 0.6436 | 0.46009 | 86.3658 | 0.40712 | 6.2208 | 6458.7636
808 | 0.055476 | 22 | 0.39734 | 0.065539 | 0.36584 | 0.68554 | 0.078269 | 102 | 0.89116 | 1.1524 | 0.65015 | 0.91023 | 0.46363 | 0.57775 | 0.85393 | 116.9012 | 0.95179 | 12.4966 | 6250.6612
809 | 0.11064 | 22 | 0.50975 | 0.078725 | 0.50021 | 0.70002 | 0.16268 | 103 | 0.58808 | 1.0601 | 0.41861 | 0.82646 | 0.88559 | 0.71092 | 0.38365 | 82.0103 | 0.83196 | 10.3261 | 6063.5229
810 | 0.76158 | 27 | 0.64985 | 0.097508 | 0.38293 | 0.68751 | 0.2646 | 104 | 0.56236 | 1.0543 | 0.48269 | 0.84765 | 0.50666 | 0.59036 | 0.57443 | 93.504 | 0.19667 | 4.7695 | 6640.5099
811 | 0.75403 | 26 | 0.8984 | 0.14479 | 0.87795 | 0.75059 | 0.26426 | 104 | 0.83416 | 1.1295 | 0.54691 | 0.87024 | 0.111 | 0.4359 | 0.0049806 | 53.5287 | 0.6706 | 8.4562 | 6167.0612
812 | 0.12684 | 23 | 0.76688 | 0.11637 | 0.20384 | 0.66385 | 0.66719 | 108 | 0.81892 | 1.1241 | 0.25374 | 0.7745 | 0.98297 | 0.77791 | 0.77526 | 108.9442 | 0.43596 | 6.437 | 6723.9703
813 | 0.85184 | 27 | 0.69644 | 0.10457 | 0.055601 | 0.63335 | 0.97489 | 113 | 0.4714 | 1.0349 | 0.4447 | 0.83493 | 0.7486 | 0.6583 | 0.027754 | 58.3297 | 0.83629 | 10.3868 | 6795.4126
814 | 0.75931 | 27 | 0.49993 | 0.077517 | 0.44064 | 0.69388 | 0.93313 | 112 | 0.79096 | 1.1148 | 0.055263 | 0.68143 | 0.77803 | 0.66806 | 0.88276 | 120.3465 | 0.82647 | 10.2503 | 6925.513
815 | 0.59539 | 26 | 0.050213 | 0.022408 | 0.32321 | 0.6804 | 0.49861 | 106 | 0.51787 | 1.0446 | 0.20028 | 0.75503 | 0.44866 | 0.57323 | 0.71385 | 103.6735 | 0.040774 | 3.261 | 6219.5716
816 | 0.59629 | 26 | 0.62957 | 0.094583 | 0.28134 | 0.67501 | 0.92544 | 112 | 0.42555 | 1.0258 | 0.52473 | 0.86227 | 0.057939 | 0.39819 | 0.24369 | 74.6824 | 0.74892 | 9.2868 | 6052.3798
817 | 0.27586 | 24 | 0.71273 | 0.10717 | 0.17625 | 0.65937 | 0.19475 | 104 | 0.55222 | 1.0521 | 0.05731 | 0.68293 | 0.66312 | 0.63282 | 0.2212 | 73.5162 | 0.53646 | 7.2373 | 6052.08
818 | 0.30345 | 24 | 0.91611 | 0.14983 | 0.96447 | 0.77334 | 0.27304 | 105 | 0.54463 | 1.0504 | 0.9097 | 1.0528 | 0.45566 | 0.57536 | 0.66259 | 99.6948 | 0.55018 | 7.353 | 6519.604
819 | 0.029832 | 21 | 0.17417 | 0.041734 | 0.82701 | 0.74118 | 0.8507 | 110 | 0.43975 | 1.0286 | 0.29713 | 0.78883 | 0.42253 | 0.56516 | 0.9603 | 132.7442 | 0.82693 | 10.2567 | 5752.475
820 | 0.53073 | 25 | 0.92944 | 0.15399 | 0.94929 | 0.76815 | 0.79428 | 109 | 0.57541 | 1.0573 | 0.043604 | 0.67234 | 0.17173 | 0.46904 | 0.15734 | 69.8334 | 0.30379 | 5.4864 | 5842.3574
821 | 0.8346 | 27 | 0.44921 | 0.071456 | 0.49406 | 0.6994 | 0.20218 | 104 | 0.07783 | 0.95219 | 0.083071 | 0.69984 | 0.76904 | 0.66502 | 0.01234 | 55.5543 | 0.25487 | 5.1579 | 6069.5229
822 | 0.013747 | 21 | 0.79709 | 0.12198 | 0.1909 | 0.66179 | 0.053284 | 102 | 0.91322 | 1.1629 | 0.022833 | 0.65234 | 0.37479 | 0.54973 | 0.33682 | 79.4747 | 0.81382 | 10.0802 | 5722.1674
823 | 0.62452 | 26 | 0.50745 | 0.078441 | 0.73531 | 0.72724 | 0.033332 | 102 | 0.56414 | 1.0547 | 0.62922 | 0.90169 | 0.96928 | 0.76348 | 0.039051 | 59.8806 | 0.95443 | 12.5659 | 6717.8549
824 | 0.36022 | 24 | 0.63655 | 0.09558 | 0.47069 | 0.69703 | 0.048262 | 102 | 0.1191 | 0.96456 | 0.45238 | 0.83747 | 0.6966 | 0.64237 | 0.38984 | 82.3524 | 0.86002 | 10.7342 | 6064.9403
825 | 0.33383 | 24 | 0.32446 | 0.057641 | 0.12913 | 0.65082 | 0.77589 | 109 | 0.79766 | 1.1169 | 0.81489 | 0.98922 | 0.83553 | 0.68922 | 0.89942 | 122.5344 | 0.43217 | 6.4082 | 6956.2086
826 | 0.5225 | 25 | 0.4958 | 0.077012 | 0.71713 | 0.72478 | 0.68117 | 108 | 0.32696 | 1.0073 | 0.60467 | 0.89198 | 0.98859 | 0.78556 | 0.083774 | 64.4718 | 0.48464 | 6.8149 | 6563.6767
827 | 0.28847 | 24 | 0.14661 | 0.03829 | 0.26178 | 0.67236 | 0.0892 | 103 | 0.98613 | 1.2152 | 0.61609 | 0.89646 | 0.08535 | 0.41917 | 0.92868 | 126.8717 | 0.34979 | 5.8061 | 6273.7218
828 | 0.38442 | 24 | 0.92658 | 0.15307 | 0.12132 | 0.64926 | 0.89244 | 111 | 0.79989 | 1.1177 | 6.0745e-05 | 0.6027 | 0.94086 | 0.74157 | 0.68025 | 101.0295 | 0.72106 | 8.9782 | 6648.2936
829 | 0.89415 | 28 | 0.75305 | 0.11393 | 0.45815 | 0.69572 | 0.50164 | 106 | 0.798 | 1.1171 | 0.53356 | 0.86542 | 0.28484 | 0.51771 | 0.65477 | 99.1154 | 0.25021 | 5.1272 | 6852.677
830 | 0.74917 | 26 | 0.13018 | 0.036081 | 0.59119 | 0.70958 | 0.13233 | 103 | 0.30172 | 1.0028 | 0.74286 | 0.95158 | 0.54931 | 0.60233 | 0.43563 | 84.9404 | 0.6261 | 8.0282 | 6363.0581
831 | 0.72933 | 26 | 0.30169 | 0.055262 | 0.4921 | 0.69921 | 0.65532 | 108 | 0.24151 | 0.99194 | 0.11284 | 0.71637 | 0.1083 | 0.43424 | 0.39004 | 82.3633 | 0.25874 | 5.1835 | 5731.3334
832 | 0.5735 | 25 | 0.044736 | 0.021151 | 0.31951 | 0.67994 | 0.27189 | 105 | 0.041797 | 0.93825 | 0.34267 | 0.80281 | 0.092791 | 0.42426 | 0.61376 | 96.1782 | 0.33567 | 5.7069 | 5591.3961
833 | 0.46732 | 25 | 0.47244 | 0.074196 | 0.19379 | 0.66226 | 0.62514 | 108 | 0.28042 | 0.99907 | 0.91594 | 1.058 | 0.0046627 | 0.32785 | 0.60957 | 95.8866 | 0.55841 | 7.4233 | 5982.0062
834 | 0.53888 | 25 | 0.73242 | 0.1104 | 0.61024 | 0.71171 | 0.81427 | 110 | 0.93616 | 1.1753 | 0.53363 | 0.86544 | 0.34196 | 0.53854 | 0.26577 | 75.7928 | 0.49393 | 6.889 | 6519.9088
835 | 0.18749 | 23 | 0.067158 | 0.025915 | 0.50837 | 0.70084 | 0.58123 | 107 | 0.65698 | 1.0768 | 0.25541 | 0.77507 | 0.35576 | 0.54331 | 0.075313 | 63.7216 | 0.70602 | 8.818 | 5674.2522
836 | 0.90254 | 28 | 0.41751 | 0.067808 | 0.33922 | 0.68237 | 0.0026279 | 100 | 0.212 | 0.98614 | 0.61795 | 0.89719 | 0.22891 | 0.49517 | 0.26292 | 75.6487 | 0.85567 | 10.6683 | 6302.4604
837 | 0.82079 | 27 | 0.23582 | 0.048561 | 0.45049 | 0.69492 | 0.34221 | 105 | 0.373 | 1.0158 | 0.42021 | 0.82697 | 0.48757 | 0.58484 | 0.77909 | 109.2956 | 0.15579 | 4.4649 | 6478.6982
838 | 0.81442 | 27 | 0.32513 | 0.057711 | 0.95927 | 0.77146 | 0.74775 | 109 | 0.84664 | 1.1342 | 0.58252 | 0.88347 | 0.064055 | 0.40324 | 0.70217 | 102.738 | 0.0014317 | 2.2363 | 6305.6544
839 | 0.99272 | 29 | 0.25463 | 0.050464 | 0.72504 | 0.72584 | 0.39686 | 105 | 0.93728 | 1.1759 | 0.079225 | 0.6975 | 0.52083 | 0.59439 | 0.89618 | 122.0958 | 0.78093 | 9.6634 | 6992.5726
840 | 0.036359 | 21 | 0.50535 | 0.078183 | 0.93747 | 0.76464 | 0.38634 | 105 | 0.27816 | 0.99867 | 0.82005 | 0.99218 | 0.42121 | 0.56474 | 0.068377 | 63.0745 | 0.64696 | 8.2254 | 5582.4316
841 | 0.48973 | 25 | 0.76535 | 0.1161 | 0.63445 | 0.7145 | 0.18059 | 104 | 0.26428 | 0.99618 | 0.80521 | 0.98378 | 0.24195 | 0.50065 | 0.13038 | 68.0541 | 0.18766 | 4.7053 | 6112.8132
842 | 0.40455 | 24 | 0.78696 | 0.12006 | 0.72601 | 0.72597 | 0.055542 | 102 | 0.046252 | 0.94023 | 0.10143 | 0.71033 | 0.80573 | 0.67786 | 0.053668 | 61.5831 | 0.072591 | 3.6826 | 5776.3515
843 | 0.76418 | 27 | 0.20893 | 0.045709 | 0.37408 | 0.6865 | 0.48395 | 106 | 0.031984 | 0.93346 | 0.59697 | 0.88899 | 0.67566 | 0.63634 | 0.39562 | 82.6733 | 0.27769 | 5.3098 | 6385.7557
844 | 0.41398 | 25 | 0.96248 | 0.16645 | 0.48909 | 0.6989 | 0.7374 | 109 | 0.92674 | 1.1699 | 0.33905 | 0.80172 | 0.12806 | 0.44598 | 0.72366 | 104.4749 | 0.030348 | 3.0879 | 6459.1418
845 | 0.86474 | 27 | 0.77719 | 0.11824 | 0.15642 | 0.65593 | 0.66343 | 108 | 0.059974 | 0.94582 | 0.96908 | 1.1139 | 0.072711 | 0.41 | 0.65875 | 99.4095 | 0.91461 | 11.6682 | 6543.2367
846 | 0.3529 | 24 | 0.14918 | 0.038624 | 0.70445 | 0.72312 | 0.27262 | 105 | 0.5836 | 1.0591 | 0.59691 | 0.88897 | 0.42497 | 0.56592 | 0.71281 | 103.5892 | 0.33138 | 5.6768 | 6129.2486
847 | 0.081491 | 22 | 0.070536 | 0.026559 | 0.6051 | 0.71113 | 0.43423 | 106 | 0.77787 | 1.1106 | 0.24124 | 0.77014 | 0.42896 | 0.56717 | 0.67765 | 100.8306 | 0.69447 | 8.6977 | 5806.0807
848 | 0.028045 | 21 | 0.44259 | 0.070685 | 0.95815 | 0.77107 | 0.47762 | 106 | 0.58818 | 1.0602 | 0.6205 | 0.89821 | 0.11896 | 0.4407 | 0.73987 | 105.8304 | 0.18379 | 4.6773 | 5533.7045
849 | 0.23924 | 23 | 0.4875 | 0.076004 | 0.56148 | 0.70635 | 0.32674 | 105 | 0.48368 | 1.0374 | 0.014632 | 0.6419 | 0.51411 | 0.59249 | 0.22856 | 73.9037 | 0.95526 | 12.5883 | 5670.3982
850 | 0.92638 | 28 | 0.75307 | 0.11393 | 0.55211 | 0.70535 | 0.55658 | 107 | 0.88076 | 1.1479 | 0.96252 | 1.1052 | 0.98607 | 0.78193 | 0.89919 | 122.5027 | 0.23538 | 5.03 | 8153.072
851 | 0.68488 | 26 | 0.46104 | 0.072844 | 0.97043 | 0.77568 | 0.11435 | 103 | 0.55995 | 1.0538 | 0.75473 | 0.95738 | 0.30691 | 0.52599 | 0.2382 | 74.4028 | 0.55485 | 7.3928 | 6236.2516
852 | 0.13024 | 23 | 0.29537 | 0.054607 | 0.81928 | 0.73988 | 0.96548 | 113 | 0.56679 | 1.0553 | 0.97693 | 1.1256 | 0.2993 | 0.52317 | 0.48641 | 87.936 | 0.29447 | 5.423 | 6220.0972
853 | 0.53862 | 25 | 0.62143 | 0.09343 | 0.62642 | 0.71356 | 0.47271 | 106 | 0.33159 | 1.0082 | 0.97968 | 1.1302 | 0.42435 | 0.56573 | 0.43057 | 84.6494 | 0.52511 | 7.1428 | 6554.7548
854 | 0.35142 | 24 | 0.43168 | 0.069426 | 0.94552 | 0.76699 | 0.79064 | 109 | 0.2571 | 0.99486 | 0.64765 | 0.9092 | 0.53515 | 0.59841 | 0.8261 | 113.8852 | 0.81179 | 10.0536 | 6228.9671
855 | 0.12116 | 22 | 0.098315 | 0.031355 | 0.89478 | 0.75413 | 0.087262 | 103 | 0.35986 | 1.0133 | 0.4786 | 0.84625 | 0.9247 | 0.73151 | 0.94739 | 130.1357 | 0.15739 | 4.4776 | 6070.4007
856 | 0.45794 | 25 | 0.89426 | 0.14368 | 0.28436 | 0.67541 | 0.32475 | 105 | 0.0001278 | 0.90211 | 0.99273 | 1.1582 | 0.46898 | 0.57935 | 0.91967 | 125.4544 | 0.74672 | 9.2619 | 6762.0015
857 | 0.65202 | 26 | 0.28457 | 0.053498 | 0.30676 | 0.67833 | 0.52655 | 107 | 0.62511 | 1.0689 | 0.80746 | 0.98503 | 0.22904 | 0.49522 | 0.50848 | 89.284 | 0.63599 | 8.121 | 6454.8732
858 | 0.30709 | 24 | 0.44801 | 0.071316 | 0.0013165 | 0.60513 | 0.58025 | 107 | 0.78203 | 1.1119 | 0.50714 | 0.85607 | 0.84845 | 0.69446 | 0.10783 | 66.4187 | 0.88994 | 11.2174 | 6580.0872
859 | 0.58253 | 25 | 0.52346 | 0.080434 | 0.23808 | 0.669 | 0.62064 | 107 | 0.84146 | 1.1322 | 0.22533 | 0.76444 | 0.15091 | 0.45846 | 0.86748 | 118.4736 | 0.66232 | 8.3744 | 6287.4015
860 | 0.7129 | 26 | 0.7325 | 0.11042 | 0.96461 | 0.7734 | 0.20578 | 104 | 0.23508 | 0.99071 | 0.99166 | 1.1553 | 0.64024 | 0.62657 | 0.55703 | 92.3609 | 0.26471 | 5.2231 | 6806.692
861 | 0.90909 | 28 | 0.85625 | 0.13433 | 0.81167 | 0.73863 | 0.16141 | 103 | 0.69517 | 1.0867 | 0.60663 | 0.89274 | 0.15767 | 0.46198 | 0.78224 | 109.5867 | 0.37944 | 6.0182 | 6680.6426
862 | 0.72224 | 26 | 0.089361 | 0.029893 | 0.76395 | 0.73129 | 0.28423 | 105 | 0.080319 | 0.95302 | 0.11712 | 0.71855 | 0.61691 | 0.6204 | 0.46833 | 86.853 | 0.16363 | 4.5262 | 5916.2271
863 | 0.49899 | 25 | 0.81424 | 0.12535 | 0.28794 | 0.67589 | 0.62345 | 107 | 0.2509 | 0.99371 | 0.28487 | 0.78489 | 0.34586 | 0.5399 | 0.0034015 | 52.9161 | 0.84899 | 10.5693 | 5977.0254
864 | 0.65505 | 26 | 0.37045 | 0.062572 | 0.39981 | 0.68942 | 0.89654 | 111 | 0.11377 | 0.9631 | 0.32587 | 0.79775 | 0.44267 | 0.5714 | 0.64461 | 98.3724 | 0.62991 | 8.0637 | 6226.5199
865 | 0.46099 | 25 | 0.092249 | 0.030373 | 0.88707 | 0.75248 | 0.37461 | 105 | 0.29113 | 1.0009 | 0.10959 | 0.71468 | 0.84851 | 0.69448 | 0.23226 | 74.0965 | 0.17889 | 4.6414 | 5942.7879
866 | 0.99149 | 29 | 0.59683 | 0.090023 | 0.63333 | 0.71437 | 0.49838 | 106 | 0.63219 | 1.0706 | 0.57837 | 0.88189 | 0.15258 | 0.45934 | 0.90846 | 123.798 | 0.74621 | 9.256 | 6818.8341
867 | 0.016508 | 21 | 0.97991 | 0.17545 | 0.11295 | 0.64753 | 0.76165 | 109 | 0.14105 | 0.97026 | 0.47073 | 0.84359 | 0.3174 | 0.52982 | 0.26872 | 75.9419 | 0.083512 | 3.8047 | 5712.9018
868 | 0.019332 | 21 | 0.2636 | 0.051366 | 0.43688 | 0.69348 | 0.63496 | 108 | 0.8537 | 1.1369 | 0.97608 | 1.1242 | 0.89693 | 0.71646 | 0.47496 | 87.2481 | 0.94525 | 12.3321 | 6500.6293
869 | 0.83116 | 27 | 0.79071 | 0.12076 | 0.2819 | 0.67509 | 0.24087 | 104 | 0.59081 | 1.0608 | 0.29445 | 0.78797 | 0.34848 | 0.54081 | 0.75775 | 107.3751 | 0.36288 | 5.8991 | 6594.7771
870 | 0.97144 | 29 | 0.46977 | 0.073877 | 0.88505 | 0.75205 | 0.0005895 | 100 | 0.90983 | 1.1612 | 0.55634 | 0.87369 | 0.45424 | 0.57493 | 0.26316 | 75.6608 | 0.35433 | 5.8382 | 6865.6776
871 | 0.035307 | 21 | 0.0019019 | 0.0043611 | 0.58877 | 0.70931 | 0.99039 | 114 | 0.11772 | 0.96419 | 0.058331 | 0.68366 | 0.21772 | 0.49034 | 0.41281 | 83.6381 | 0.83029 | 10.3029 | 5133.4406
872 | 0.0492 | 22 | 0.69327 | 0.10407 | 0.813 | 0.73884 | 0.62229 | 107 | 0.34061 | 1.0098 | 0.35803 | 0.80748 | 0.054953 | 0.39563 | 0.85204 | 116.6876 | 0.64135 | 8.1718 | 5581.0807
873 | 0.21586 | 23 | 0.27047 | 0.052061 | 0.35881 | 0.68471 | 0.32541 | 105 | 0.95261 | 1.1856 | 0.75292 | 0.95649 | 0.79095 | 0.67255 | 0.17841 | 71.1195 | 0.17648 | 4.6235 | 6477.4817
874 | 0.0014935 | 20 | 0.87025 | 0.13761 | 0.93783 | 0.76474 | 0.90829 | 111 | 0.25797 | 0.99502 | 0.21517 | 0.76069 | 0.976 | 0.77004 | 0.011683 | 55.4043 | 0.93716 | 12.1418 | 5683.4495
875 | 0.65871 | 26 | 0.096871 | 0.031124 | 0.51786 | 0.7018 | 0.74896 | 109 | 0.75159 | 1.1026 | 0.50925 | 0.85681 | 0.63911 | 0.62627 | 0.57866 | 93.786 | 0.36233 | 5.8952 | 6613.6685
876 | 0.64502 | 26 | 0.67737 | 0.10162 | 0.8895 | 0.75299 | 0.4583 | 106 | 0.27421 | 0.99797 | 0.54853 | 0.87083 | 0.34546 | 0.53976 | 0.65281 | 98.9712 | 0.78295 | 9.688 | 6297.2422
877 | 0.42349 | 25 | 0.51221 | 0.07903 | 0.87813 | 0.75063 | 0.97002 | 113 | 0.5857 | 1.0596 | 0.55803 | 0.87431 | 0.040525 | 0.38212 | 0.097046 | 65.5761 | 0.10005 | 3.9753 | 5794.55
878 | 0.80885 | 27 | 0.84938 | 0.13278 | 0.05044 | 0.63176 | 0.715 | 108 | 0.77863 | 1.1108 | 0.65725 | 0.91319 | 0.67037 | 0.63485 | 0.82323 | 113.589 | 0.53984 | 7.2656 | 7316.673
879 | 0.51223 | 25 | 0.11711 | 0.034222 | 0.67737 | 0.71967 | 0.28233 | 105 | 0.97681 | 1.205 | 0.6965 | 0.93011 | 0.72706 | 0.65152 | 0.36296 | 80.8786 | 0.74297 | 9.2196 | 6733.8982
880 | 0.99873 | 30 | 0.70261 | 0.10554 | 0.61957 | 0.71277 | 0.044877 | 102 | 0.71258 | 1.0914 | 0.42392 | 0.82817 | 0.24835 | 0.50329 | 0.99759 | 145.746 | 0.32377 | 5.624 | 7099.0679
881 | 0.6821 | 26 | 0.50368 | 0.077977 | 0.36419 | 0.68534 | 0.035379 | 102 | 0.24716 | 0.99301 | 0.35053 | 0.80519 | 0.37342 | 0.54927 | 0.72754 | 104.7956 | 0.99424 | 14.1344 | 6255.8039
882 | 0.32552 | 24 | 0.14983 | 0.038708 | 0.030876 | 0.62485 | 0.63148 | 108 | 0.32114 | 1.0063 | 0.14745 | 0.73302 | 0.7239 | 0.65055 | 0.64872 | 98.672 | 0.28675 | 5.3707 | 6112.0566
883 | 0.56811 | 25 | 0.48261 | 0.075413 | 0.18746 | 0.66123 | 0.19741 | 104 | 0.30836 | 1.004 | 0.20253 | 0.7559 | 0.8906 | 0.71334 | 0.38401 | 82.0297 | 0.11107 | 4.0813 | 6303.8313
884 | 0.40899 | 25 | 0.47403 | 0.074385 | 0.71009 | 0.72385 | 0.46987 | 106 | 0.19309 | 0.98221 | 0.64238 | 0.90703 | 0.76941 | 0.66514 | 0.72581 | 104.6521 | 0.59449 | 7.7394 | 6447.289
885 | 0.73803 | 26 | 0.35156 | 0.060526 | 0.83048 | 0.74177 | 0.65634 | 108 | 0.90199 | 1.1574 | 0.6022 | 0.89102 | 0.068731 | 0.40694 | 0.38897 | 82.3043 | 0.32143 | 5.6078 | 6188.6345
886 | 0.48919 | 25 | 0.21087 | 0.045921 | 0.059932 | 0.63462 | 0.022234 | 101 | 0.5787 | 1.058 | 0.15389 | 0.73589 | 0.19755 | 0.48131 | 0.96769 | 134.4323 | 0.88227 | 11.0879 | 6148.1294
887 | 0.86868 | 27 | 0.91427 | 0.14928 | 0.58022 | 0.70837 | 0.30259 | 105 | 0.22273 | 0.98829 | 0.52324 | 0.86174 | 0.65325 | 0.6301 | 0.063397 | 62.5894 | 0.61351 | 7.9117 | 6556.8075
888 | 0.13182 | 23 | 0.7247 | 0.10912 | 0.21473 | 0.66553 | 0.37191 | 105 | 0.68355 | 1.0836 | 0.68322 | 0.92427 | 0.42735 | 0.56667 | 0.10784 | 66.4196 | 0.94797 | 12.3991 | 6163.1006
889 | 0.5902 | 25 | 0.64726 | 0.09713 | 0.72366 | 0.72566 | 0.50676 | 106 | 0.64094 | 1.0727 | 0.064489 | 0.68797 | 0.63633 | 0.62552 | 0.35679 | 80.5443 | 0.34989 | 5.8069 | 6159.144
890 | 0.4629 | 25 | 0.39322 | 0.06508 | 0.94001 | 0.76536 | 0.77068 | 109 | 0.51888 | 1.0448 | 0.22751 | 0.76523 | 0.73857 | 0.65511 | 0.46067 | 86.3999 | 0.44299 | 6.4905 | 6219.0795
891 | 0.30398 | 24 | 0.80047 | 0.12263 | 0.035178 | 0.62652 | 0.37223 | 105 | 0.26426 | 0.99617 | 0.84663 | 1.0081 | 0.55289 | 0.60332 | 0.7744 | 108.8657 | 0.18161 | 4.6613 | 6572.7178
892 | 0.30117 | 24 | 0.091743 | 0.030289 | 0.41276 | 0.69086 | 0.26278 | 104 | 0.82433 | 1.126 | 0.72719 | 0.94412 | 0.66769 | 0.6341 | 0.69953 | 102.5283 | 0.90325 | 11.4536 | 6528.7957
893 | 0.94771 | 28 | 0.75864 | 0.11491 | 0.32688 | 0.68086 | 0.86248 | 110 | 0.03338 | 0.93418 | 0.93929 | 1.0793 | 0.4685 | 0.57921 | 0.63011 | 97.3296 | 0.50226 | 6.956 | 6978.772
894 | 0.661 | 26 | 0.77964 | 0.11869 | 0.85137 | 0.74548 | 0.67849 | 108 | 0.068434 | 0.94894 | 0.75855 | 0.95928 | 0.74429 | 0.65692 | 0.41597 | 83.8167 | 0.72655 | 9.0377 | 6570.1647
895 | 0.056856 | 22 | 0.32607 | 0.05781 | 0.56757 | 0.707 | 0.77652 | 109 | 0.114 | 0.96317 | 0.93733 | 1.0774 | 0.39031 | 0.55485 | 0.55053 | 91.9395 | 0.81753 | 10.1295 | 5951.7503
896 | 0.025684 | 21 | 0.69189 | 0.10386 | 0.19764 | 0.66287 | 0.73385 | 109 | 0.30743 | 1.0038 | 0.95927 | 1.1011 | 0.82717 | 0.68593 | 0.24778 | 74.8888 | 0.55478 | 7.3922 | 6221.4689
897 | 0.54647 | 25 | 0.2931 | 0.054374 | 0.65653 | 0.71712 | 0.69588 | 108 | 0.56075 | 1.054 | 0.9247 | 1.0656 | 0.34227 | 0.53865 | 0.61623 | 96.3506 | 0.22144 | 4.9387 | 6477.6748
898 | 0.55935 | 25 | 0.21751 | 0.046638 | 0.017881 | 0.61891 | 0.33771 | 105 | 0.73202 | 1.0969 | 0.2663 | 0.77876 | 0.70199 | 0.64395 | 0.46016 | 86.3697 | 0.42385 | 6.3456 | 6449.8102
899 | 0.65773 | 26 | 0.73957 | 0.11161 | 0.92394 | 0.761 | 0.69349 | 108 | 0.6426 | 1.0732 | 0.17302 | 0.74409 | 0.010151 | 0.3411 | 0.46996 | 86.95 | 0.12217 | 4.1828 | 5795.1997
900 | 0.92905 | 28 | 0.053346 | 0.023097 | 0.381 | 0.68729 | 0.41636 | 106 | 0.27333 | 0.99781 | 0.086966 | 0.70216 | 0.36305 | 0.54579 | 0.16794 | 70.4901 | 0.15017 | 4.42 | 6058.6565
901 | 0.99095 | 29 | 0.93438 | 0.15563 | 0.76304 | 0.73116 | 0.94818 | 112 | 0.19417 | 0.98244 | 0.62539 | 0.90016 | 0.68073 | 0.63778 | 0.77067 | 108.5275 | 0.019957 | 2.8822 | 7180.4109
902 | 0.65485 | 26 | 0.66839 | 0.10026 | 0.033486 | 0.62588 | 0.12106 | 103 | 0.11288 | 0.96286 | 0.055893 | 0.6819 | 0.16737 | 0.46689 | 0.45225 | 85.9051 | 0.17102 | 4.5826 | 5843.7145
903 | 0.70605 | 26 | 0.28914 | 0.053967 | 0.77235 | 0.73252 | 0.049273 | 102 | 0.20446 | 0.98459 | 0.84656 | 1.0081 | 0.80893 | 0.67904 | 0.090368 | 65.0306 | 0.40501 | 6.2052 | 6466.175
904 | 0.75957 | 27 | 0.95155 | 0.16187 | 0.42931 | 0.69266 | 0.87131 | 111 | 0.78459 | 1.1127 | 0.48059 | 0.84693 | 0.76028 | 0.66211 | 0.045541 | 60.6702 | 0.62696 | 8.0361 | 7034.8157
905 | 0.75172 | 26 | 0.61094 | 0.091964 | 0.9693 | 0.77522 | 0.56873 | 107 | 0.79458 | 1.1159 | 0.11505 | 0.7175 | 0.41111 | 0.56155 | 0.71623 | 103.8666 | 0.7226 | 8.9948 | 6353.945
906 | 0.080024 | 22 | 0.82375 | 0.12728 | 0.10533 | 0.6459 | 0.57149 | 107 | 0.76314 | 1.106 | 0.037502 | 0.66708 | 0.55253 | 0.60322 | 0.31177 | 78.1547 | 0.84474 | 10.5074 | 5948.3364
907 | 0.12664 | 23 | 0.93266 | 0.15505 | 0.37818 | 0.68697 | 0.27667 | 105 | 0.11237 | 0.96271 | 0.56741 | 0.87779 | 0.3399 | 0.53782 | 0.016819 | 56.4843 | 0.1469 | 4.3935 | 5795.7272
908 | 0.11416 | 22 | 0.7855 | 0.11978 | 0.75603 | 0.73015 | 0.98325 | 113 | 0.20755 | 0.98523 | 0.5941 | 0.88788 | 0.90719 | 0.72176 | 0.54096 | 91.3245 | 0.030626 | 3.0929 | 6191.969
909 | 0.24006 | 23 | 0.1448 | 0.038053 | 0.97505 | 0.77766 | 0.087392 | 103 | 0.80596 | 1.1197 | 0.43694 | 0.8324 | 0.53668 | 0.59884 | 0.71777 | 103.9918 | 0.16597 | 4.5442 | 5995.6483
910 | 0.058392 | 22 | 0.0094681 | 0.0097304 | 0.88257 | 0.75154 | 0.10327 | 103 | 0.074648 | 0.95111 | 0.82755 | 0.99656 | 0.2278 | 0.49469 | 0.60216 | 95.376 | 0.45248 | 6.5633 | 5505.6823
911 | 0.77698 | 27 | 0.80974 | 0.12445 | 0.44401 | 0.69423 | 0.26885 | 104 | 0.63214 | 1.0706 | 0.61988 | 0.89796 | 0.908 | 0.72219 | 0.030067 | 58.6699 | 0.38315 | 6.0451 | 6954.4251
912 | 0.54193 | 25 | 0.99119 | 0.18374 | 0.57349 | 0.70764 | 0.3036 | 105 | 0.26536 | 0.99637 | 0.40794 | 0.82305 | 0.26196 | 0.50878 | 0.15981 | 69.988 | 0.62822 | 8.0479 | 6109.868
913 | 0.10228 | 22 | 0.9478 | 0.16043 | 0.27392 | 0.67402 | 0.71323 | 108 | 0.24581 | 0.99275 | 0.92948 | 1.0699 | 0.19665 | 0.48089 | 0.3078 | 77.9479 | 0.79547 | 9.8435 | 6026.68
914 | 0.10183 | 22 | 0.71998 | 0.10834 | 0.69612 | 0.72204 | 0.31256 | 105 | 0.5693 | 1.0559 | 0.37908 | 0.81397 | 0.52304 | 0.59502 | 0.15312 | 69.5654 | 0.97286 | 13.1217 | 5832.5415
915 | 0.025268 | 21 | 0.69696 | 0.10465 | 0.79141 | 0.73541 | 0.36737 | 105 | 0.30791 | 1.0039 | 0.16745 | 0.74175 | 0.9237 | 0.73092 | 0.29162 | 77.1106 | 0.083144 | 3.8007 | 5712.6214
916 | 0.7325 | 26 | 0.41223 | 0.06721 | 0.28183 | 0.67508 | 0.2482 | 104 | 0.84911 | 1.1351 | 0.98992 | 1.1508 | 0.57717 | 0.6099 | 0.25639 | 75.3202 | 0.92093 | 11.794 | 7078.3036
917 | 0.6858 | 26 | 0.45853 | 0.072547 | 0.92474 | 0.7612 | 0.091623 | 103 | 0.43496 | 1.0276 | 0.54012 | 0.86778 | 0.11026 | 0.43545 | 0.96217 | 133.1566 | 0.89409 | 11.2895 | 6193.6101
918 | 0.58303 | 25 | 0.19446 | 0.044097 | 0.049589 | 0.63149 | 0.79553 | 109 | 0.62874 | 1.0698 | 0.54177 | 0.86838 | 0.70523 | 0.64491 | 0.64056 | 98.079 | 0.46005 | 6.6218 | 6602.6347
919 | 0.62347 | 26 | 0.3975 | 0.065557 | 0.43914 | 0.69372 | 0.68971 | 108 | 0.96107 | 1.1916 | 0.99189 | 1.1559 | 0.68168 | 0.63805 | 0.3245 | 78.8227 | 0.14581 | 4.3847 | 7295.2746
920 | 0.77539 | 27 | 0.59522 | 0.089803 | 0.28641 | 0.67568 | 0.42957 | 106 | 0.9811 | 1.2093 | 0.40267 | 0.82137 | 0.40144 | 0.55846 | 0.87445 | 119.314 | 0.14952 | 4.4148 | 7036.5641
921 | 0.35678 | 24 | 0.42653 | 0.068836 | 0.76484 | 0.73142 | 0.078984 | 102 | 0.99197 | 1.2235 | 0.27695 | 0.7823 | 0.7957 | 0.67424 | 0.80934 | 112.1857 | 0.41393 | 6.2714 | 6608.0804
922 | 0.03291 | 21 | 0.51303 | 0.079132 | 0.0042858 | 0.60926 | 0.41025 | 106 | 0.47253 | 1.0352 | 0.97218 | 1.1183 | 0.66431 | 0.63315 | 0.67351 | 100.5159 | 0.11946 | 4.1584 | 6287.5796
923 | 0.24577 | 24 | 0.74241 | 0.11209 | 0.95004 | 0.76839 | 0.28518 | 105 | 0.1048 | 0.96056 | 0.91149 | 1.0543 | 0.033747 | 0.37494 | 0.38927 | 82.3206 | 0.39468 | 6.1292 | 5759.0826
924 | 0.30851 | 24 | 0.69415 | 0.10421 | 0.84366 | 0.74408 | 0.15927 | 103 | 0.66751 | 1.0794 | 0.38375 | 0.81542 | 0.53777 | 0.59914 | 0.93861 | 128.5433 | 0.98736 | 13.718 | 6394.5247
925 | 0.32071 | 24 | 0.35885 | 0.061311 | 0.0050894 | 0.61009 | 0.3681 | 105 | 0.71972 | 1.0934 | 0.7837 | 0.97216 | 0.072514 | 0.40985 | 0.1609 | 70.0563 | 0.85009 | 10.5854 | 6008.3381
926 | 0.79062 | 27 | 0.45441 | 0.072063 | 0.34951 | 0.68361 | 0.67244 | 108 | 0.88321 | 1.1489 | 0.93615 | 1.0762 | 0.26643 | 0.51056 | 0.39999 | 82.9172 | 0.98983 | 13.8501 | 6989.1444
927 | 0.69067 | 26 | 0.87346 | 0.13839 | 0.65543 | 0.71699 | 0.65012 | 108 | 0.023021 | 0.92839 | 0.35472 | 0.80647 | 0.53934 | 0.59958 | 0.74405 | 106.1861 | 0.68663 | 8.6174 | 6360.3689
928 | 0.37026 | 24 | 0.87368 | 0.13844 | 0.049678 | 0.63152 | 0.23973 | 104 | 0.88698 | 1.1506 | 0.81078 | 0.98689 | 0.96863 | 0.76288 | 0.63002 | 97.3231 | 0.44227 | 6.485 | 7224.5352
929 | 0.54019 | 25 | 0.86889 | 0.13728 | 0.24344 | 0.66978 | 0.38158 | 105 | 0.14645 | 0.97159 | 0.26761 | 0.7792 | 0.38199 | 0.55212 | 0.45846 | 86.2695 | 0.74344 | 9.2248 | 6119.9214
930 | 0.22669 | 23 | 0.54959 | 0.083758 | 0.37255 | 0.68632 | 0.76108 | 109 | 0.38462 | 1.018 | 0.67147 | 0.9192 | 0.70877 | 0.64597 | 0.54007 | 91.268 | 0.52413 | 7.1347 | 6247.9487
931 | 0.22886 | 23 | 0.40205 | 0.066066 | 0.14736 | 0.65429 | 0.85519 | 110 | 0.16953 | 0.97703 | 0.4713 | 0.84379 | 0.89196 | 0.714 | 0.42573 | 84.3723 | 0.70033 | 8.7585 | 6176.3461
932 | 0.5251 | 25 | 0.53025 | 0.081289 | 0.46314 | 0.69624 | 0.77721 | 109 | 0.16272 | 0.97547 | 0.062872 | 0.68686 | 0.098895 | 0.42828 | 0.2403 | 74.51 | 0.1058 | 4.0313 | 5561.1052
933 | 0.95198 | 28 | 0.11291 | 0.033603 | 0.80363 | 0.73733 | 0.24667 | 104 | 0.35405 | 1.0123 | 0.0024638 | 0.61719 | 0.39912 | 0.55771 | 0.16081 | 70.0506 | 0.13738 | 4.3147 | 5907.9383
934 | 0.84956 | 27 | 0.75424 | 0.11414 | 0.83733 | 0.74296 | 0.39566 | 105 | 0.76383 | 1.1062 | 0.29394 | 0.78781 | 0.15179 | 0.45893 | 0.94627 | 129.9252 | 0.36494 | 5.9139 | 6514.3768
935 | 0.53836 | 25 | 0.20901 | 0.045718 | 0.063309 | 0.63558 | 0.65311 | 108 | 0.14424 | 0.97105 | 0.27496 | 0.78165 | 0.6839 | 0.63869 | 0.73753 | 105.6315 | 0.98088 | 13.4234 | 6290.6759
936 | 0.75574 | 27 | 0.57632 | 0.087259 | 0.11229 | 0.64739 | 0.034021 | 102 | 0.34202 | 1.0101 | 0.88074 | 1.0308 | 0.36725 | 0.5472 | 0.15217 | 69.5043 | 0.85986 | 10.7317 | 6634.0586
937 | 0.20582 | 23 | 0.38127 | 0.063758 | 0.48537 | 0.69853 | 0.16473 | 104 | 0.058709 | 0.94533 | 0.70843 | 0.93547 | 0.078207 | 0.41408 | 0.90649 | 123.5171 | 0.46496 | 6.66 | 5719.4776
938 | 0.54896 | 25 | 0.53242 | 0.081563 | 0.68522 | 0.72066 | 0.72008 | 109 | 0.1047 | 0.96053 | 0.27117 | 0.78039 | 0.38614 | 0.55348 | 0.69791 | 102.4008 | 0.45002 | 6.5444 | 6027.0662
939 | 0.19011 | 23 | 0.34276 | 0.059582 | 0.10778 | 0.64643 | 0.40875 | 106 | 0.12518 | 0.96619 | 0.75487 | 0.95745 | 0.63216 | 0.62441 | 0.13553 | 68.407 | 0.25839 | 5.1812 | 5986.9501
940 | 0.91985 | 28 | 0.50162 | 0.077724 | 0.066015 | 0.63634 | 0.14821 | 103 | 0.73437 | 1.0975 | 0.52701 | 0.86308 | 0.26687 | 0.51073 | 0.4502 | 85.7853 | 0.7474 | 9.2696 | 6714.8192
941 | 0.17657 | 23 | 0.21649 | 0.046529 | 0.59355 | 0.70984 | 0.48579 | 106 | 0.84764 | 1.1345 | 0.54767 | 0.87052 | 0.8738 | 0.70544 | 0.38023 | 81.8218 | 0.96398 | 12.836 | 6381.3815
942 | 0.31438 | 24 | 0.96208 | 0.16627 | 0.60167 | 0.71074 | 0.60062 | 107 | 0.38108 | 1.0173 | 0.11122 | 0.71553 | 0.873 | 0.70507 | 0.74198 | 106.0099 | 0.44379 | 6.4966 | 6417.4754
943 | 0.17671 | 23 | 0.24928 | 0.049928 | 0.57103 | 0.70738 | 0.19177 | 104 | 0.48742 | 1.0382 | 0.81862 | 0.99136 | 0.069267 | 0.40736 | 0.4755 | 87.2804 | 0.74336 | 9.2239 | 5722.9406
944 | 0.74465 | 26 | 0.9514 | 0.16182 | 0.031629 | 0.62515 | 0.35669 | 105 | 0.47097 | 1.0348 | 0.99769 | 1.1765 | 0.80491 | 0.67756 | 0.092866 | 65.237 | 0.63037 | 8.0681 | 7288.2929
945 | 0.087471 | 22 | 0.97842 | 0.17456 | 0.96247 | 0.7726 | 0.52426 | 107 | 0.98651 | 1.2156 | 0.23349 | 0.76739 | 0.085528 | 0.4193 | 0.94176 | 129.1009 | 0.92207 | 11.817 | 6113.8652
946 | 0.64539 | 26 | 0.18252 | 0.042722 | 0.97239 | 0.7765 | 0.58511 | 107 | 0.88307 | 1.1488 | 0.30813 | 0.79229 | 0.55705 | 0.60446 | 0.52039 | 90.0245 | 0.71717 | 8.9363 | 6449.6152
947 | 0.88721 | 28 | 0.84641 | 0.13212 | 0.078678 | 0.63967 | 0.7521 | 109 | 0.38811 | 1.0186 | 0.79642 | 0.97896 | 0.10309 | 0.43097 | 0.25489 | 75.2451 | 0.93613 | 12.1186 | 6643.0335
948 | 0.51525 | 25 | 0.52439 | 0.08055 | 0.70571 | 0.72328 | 0.011158 | 101 | 0.65119 | 1.0753 | 0.8178 | 0.99089 | 0.15434 | 0.46026 | 0.15737 | 69.8348 | 0.55594 | 7.4021 | 6083.3687
949 | 0.1533 | 23 | 0.16676 | 0.040837 | 0.73983 | 0.72786 | 0.45573 | 106 | 0.9957 | 1.2306 | 0.47221 | 0.84409 | 0.74388 | 0.65679 | 0.20812 | 72.8099 | 0.67634 | 8.5134 | 6332.1098
950 | 0.69888 | 26 | 0.82995 | 0.12857 | 0.42332 | 0.69201 | 0.21866 | 104 | 0.37831 | 1.0168 | 0.6949 | 0.9294 | 0.86624 | 0.70205 | 0.051362 | 61.3316 | 0.76628 | 9.4878 | 6718.558
951 | 0.92793 | 28 | 0.63153 | 0.094861 | 0.1318 | 0.65134 | 0.055773 | 102 | 0.20282 | 0.98425 | 0.21286 | 0.75982 | 0.31481 | 0.52888 | 0.99649 | 144.8667 | 0.077866 | 3.7426 | 6608.0193
952 | 0.8565 | 27 | 0.67231 | 0.10085 | 0.22935 | 0.66773 | 0.53453 | 107 | 0.34491 | 1.0106 | 0.37978 | 0.81419 | 0.47874 | 0.58225 | 0.2312 | 74.0417 | 0.38125 | 6.0313 | 6451.0893
953 | 0.79177 | 27 | 0.73334 | 0.11056 | 0.6505 | 0.71639 | 0.063608 | 102 | 0.24599 | 0.99279 | 0.94446 | 1.0845 | 0.46183 | 0.57722 | 0.47067 | 86.9925 | 0.1423 | 4.3557 | 6755.9761
954 | 0.0024926 | 20 | 0.56593 | 0.085885 | 0.81343 | 0.73891 | 0.86104 | 110 | 0.69418 | 1.0864 | 0.62157 | 0.89863 | 0.34256 | 0.53875 | 0.53585 | 90.9986 | 0.98304 | 13.5151 | 5701.0202
955 | 0.97141 | 29 | 0.99059 | 0.1832 | 0.627 | 0.71363 | 0.97447 | 113 | 0.61623 | 1.0668 | 0.42817 | 0.82954 | 0.93737 | 0.73929 | 0.17237 | 70.7588 | 0.31877 | 5.5893 | 7469.3736
956 | 0.77161 | 27 | 0.006726 | 0.0082012 | 0.27129 | 0.67366 | 0.36556 | 105 | 0.26081 | 0.99554 | 0.46774 | 0.84259 | 0.8532 | 0.69644 | 0.66969 | 100.2274 | 0.8222 | 10.1923 | 6634.7999
957 | 0.47445 | 25 | 0.95494 | 0.16323 | 0.52535 | 0.70257 | 0.9968 | 114 | 0.96287 | 1.193 | 0.21022 | 0.75883 | 0.65194 | 0.62974 | 0.36796 | 81.1503 | 0.70965 | 8.8563 | 6845.409
958 | 0.52625 | 25 | 0.23647 | 0.048628 | 0.56426 | 0.70665 | 0.73122 | 109 | 0.6193 | 1.0675 | 0.88897 | 1.0368 | 0.13422 | 0.44945 | 0.37507 | 81.5387 | 0.45165 | 6.5569 | 6201.0068
959 | 0.67003 | 26 | 0.032122 | 0.017923 | 0.66904 | 0.71864 | 0.85631 | 110 | 0.14079 | 0.9702 | 0.80345 | 0.98281 | 0.85398 | 0.69677 | 0.31943 | 78.556 | 0.46397 | 6.6523 | 6547.1286
960 | 0.69405 | 26 | 0.78924 | 0.12048 | 0.48956 | 0.69895 | 0.76304 | 109 | 0.05992 | 0.9458 | 0.35924 | 0.80785 | 0.46278 | 0.5775 | 0.14601 | 69.1054 | 0.12214 | 4.1825 | 6142.4292
961 | 0.84339 | 27 | 0.38079 | 0.063705 | 0.053288 | 0.63265 | 0.72252 | 109 | 0.75323 | 1.1031 | 0.40186 | 0.82111 | 0.27082 | 0.51228 | 0.46097 | 86.4173 | 0.4595 | 6.6176 | 6567.7541
962 | 0.22483 | 23 | 0.54982 | 0.083788 | 0.31767 | 0.67971 | 0.35332 | 105 | 0.045085 | 0.93972 | 0.69933 | 0.93137 | 0.56193 | 0.60579 | 0.89572 | 122.0342 | 0.082607 | 3.7949 | 6127.0722
963 | 0.32236 | 24 | 0.42656 | 0.068839 | 0.60165 | 0.71074 | 0.092751 | 103 | 0.61611 | 1.0667 | 0.046719 | 0.67488 | 0.55401 | 0.60362 | 0.94915 | 130.4705 | 0.50684 | 6.9931 | 6130.4632
964 | 0.14381 | 23 | 0.058118 | 0.024108 | 0.25672 | 0.67165 | 0.50425 | 106 | 0.26219 | 0.99579 | 0.78001 | 0.97022 | 0.44226 | 0.57128 | 0.38865 | 82.2866 | 0.026963 | 3.0255 | 5906.2314
965 | 0.36783 | 24 | 0.72695 | 0.10949 | 0.13543 | 0.65204 | 0.46082 | 106 | 0.24538 | 0.99267 | 0.30277 | 0.79061 | 0.90934 | 0.7229 | 0.27311 | 76.1647 | 0.97312 | 13.1307 | 6333.7762
966 | 0.093358 | 22 | 0.75512 | 0.11429 | 0.043188 | 0.62939 | 0.8237 | 110 | 0.66853 | 1.0797 | 0.16112 | 0.73905 | 0.64537 | 0.62795 | 0.94195 | 129.135 | 0.7763 | 9.6073 | 6306.9552
967 | 0.064255 | 22 | 0.95922 | 0.16502 | 0.18928 | 0.66153 | 0.8599 | 110 | 0.46597 | 1.0338 | 0.29809 | 0.78913 | 0.79361 | 0.67349 | 0.020633 | 57.1821 | 0.33687 | 5.7152 | 6058.4843
968 | 0.041846 | 21 | 0.029205 | 0.017089 | 0.91647 | 0.75913 | 0.18524 | 104 | 0.58032 | 1.0584 | 0.59237 | 0.88722 | 0.7371 | 0.65465 | 0.070303 | 63.2574 | 0.30724 | 5.5101 | 5571.3741
969 | 0.66571 | 26 | 0.8714 | 0.13789 | 0.71616 | 0.72466 | 0.25697 | 104 | 0.31181 | 1.0046 | 0.09669 | 0.70772 | 0.63649 | 0.62556 | 0.79226 | 110.5281 | 0.039653 | 3.2436 | 6371.0207
970 | 0.059057 | 22 | 0.87657 | 0.13915 | 0.22177 | 0.6666 | 0.010067 | 101 | 0.62042 | 1.0678 | 0.9126 | 1.0552 | 0.80125 | 0.67623 | 0.64076 | 98.0931 | 0.10964 | 4.0678 | 6518.7667
971 | 0.42874 | 25 | 0.43029 | 0.069266 | 0.17907 | 0.65985 | 0.57791 | 107 | 0.10407 | 0.96035 | 0.97388 | 1.1208 | 0.77938 | 0.66853 | 0.96813 | 134.5404 | 0.7826 | 9.6837 | 6967.1048
972 | 0.060858 | 22 | 0.65499 | 0.098263 | 0.69421 | 0.7218 | 0.43312 | 106 | 0.5537 | 1.0524 | 0.58606 | 0.88481 | 0.00029615 | 0.30702 | 0.53378 | 90.8678 | 0.88463 | 11.1273 | 5445.3528
973 | 0.28256 | 24 | 0.25791 | 0.050793 | 0.19542 | 0.66252 | 0.58607 | 107 | 0.74598 | 1.1009 | 0.86247 | 1.0183 | 0.18962 | 0.47763 | 0.010975 | 55.2382 | 0.54665 | 7.323 | 6078.8785
974 | 0.75318 | 26 | 0.84232 | 0.13122 | 0.50117 | 0.70012 | 0.79492 | 109 | 0.7154 | 1.0922 | 0.57441 | 0.8804 | 0.36123 | 0.54517 | 0.67837 | 100.8853 | 0.83404 | 10.3551 | 6713.1466
975 | 0.36536 | 24 | 0.6037 | 0.090963 | 0.65697 | 0.71717 | 0.018162 | 101 | 0.18529 | 0.98053 | 0.6085 | 0.89347 | 0.15016 | 0.45807 | 0.63588 | 97.7418 | 0.55899 | 7.4282 | 5822.6402
976 | 0.36181 | 24 | 0.86701 | 0.13684 | 0.4254 | 0.69224 | 0.30398 | 105 | 0.63146 | 1.0704 | 0.91638 | 1.0583 | 0.30277 | 0.52446 | 0.31702 | 78.4296 | 0.067335 | 3.6205 | 6404.9868
977 | 0.54706 | 25 | 0.31382 | 0.056524 | 0.8208 | 0.74013 | 0.94293 | 112 | 0.54366 | 1.0502 | 0.76776 | 0.96391 | 0.047399 | 0.38881 | 0.17727 | 71.0517 | 0.15339 | 4.4459 | 5882.9563
978 | 0.69333 | 26 | 0.092555 | 0.030423 | 0.88948 | 0.75298 | 0.84952 | 110 | 0.65947 | 1.0774 | 0.65444 | 0.91201 | 0.64206 | 0.62706 | 0.48311 | 87.7373 | 0.59143 | 7.7121 | 6558.1922
979 | 0.13948 | 23 | 0.54599 | 0.083294 | 0.45446 | 0.69534 | 0.88254 | 111 | 0.71749 | 1.0928 | 0.68856 | 0.9266 | 0.31839 | 0.53017 | 0.22382 | 73.6551 | 0.58748 | 7.6769 | 6090.5739
980 | 0.23892 | 23 | 0.46208 | 0.072967 | 0.40248 | 0.68972 | 0.81006 | 110 | 0.94912 | 1.1833 | 0.28734 | 0.78569 | 0.35477 | 0.54297 | 0.096293 | 65.5156 | 0.98782 | 13.7416 | 6080.5613
981 | 0.94423 | 28 | 0.77745 | 0.11829 | 0.1049 | 0.6458 | 0.38584 | 105 | 0.85721 | 1.1382 | 0.29695 | 0.78877 | 0.17655 | 0.4714 | 0.051739 | 61.3732 | 0.88739 | 11.1738 | 6584.3931
982 | 0.05559 | 22 | 0.49735 | 0.077201 | 0.95046 | 0.76852 | 0.54628 | 107 | 0.50024 | 1.0409 | 0.57265 | 0.87975 | 0.79633 | 0.67446 | 0.72232 | 104.3641 | 0.72077 | 8.9751 | 6088.078
983 | 0.66 | 26 | 0.62167 | 0.093464 | 0.75262 | 0.72966 | 0.38278 | 105 | 0.72293 | 1.0943 | 0.35847 | 0.80761 | 0.46525 | 0.57824 | 0.47147 | 87.0397 | 0.43224 | 6.4088 | 6421.3493
984 | 0.61925 | 26 | 0.49625 | 0.077067 | 0.11716 | 0.64841 | 0.29033 | 105 | 0.26868 | 0.99697 | 0.48023 | 0.84681 | 0.55323 | 0.60341 | 0.050395 | 61.2244 | 0.3674 | 5.9315 | 6267.2424
985 | 0.60252 | 26 | 0.7907 | 0.12076 | 0.15303 | 0.65532 | 0.50596 | 106 | 0.42223 | 1.0252 | 0.67752 | 0.9218 | 0.84551 | 0.69324 | 0.80841 | 112.0928 | 0.72511 | 9.022 | 7021.1052
986 | 0.1583 | 23 | 0.6603 | 0.09905 | 0.79792 | 0.73643 | 0.85603 | 110 | 0.61296 | 1.066 | 0.89786 | 1.0434 | 0.44979 | 0.57358 | 0.96784 | 134.4696 | 0.14093 | 4.3444 | 6542.4347
987 | 0.32197 | 24 | 0.72073 | 0.10847 | 0.87794 | 0.75059 | 0.74326 | 109 | 0.5513 | 1.0519 | 0.78663 | 0.97371 | 0.11549 | 0.43863 | 0.21164 | 73.002 | 0.26729 | 5.2403 | 5962.8879
988 | 0.83572 | 27 | 0.75562 | 0.11438 | 0.82378 | 0.74063 | 0.84976 | 110 | 0.1597 | 0.97476 | 0.58457 | 0.88424 | 0.51132 | 0.59169 | 0.43374 | 84.8316 | 0.05398 | 3.4509 | 6505.3001
989 | 0.048195 | 22 | 0.68369 | 0.10259 | 0.28556 | 0.67557 | 0.39205 | 105 | 0.87968 | 1.1474 | 0.4635 | 0.84117 | 0.58026 | 0.61073 | 0.4978 | 88.628 | 0.75415 | 9.3467 | 6194.7573
990 | 0.50617 | 25 | 0.56652 | 0.085963 | 0.015126 | 0.61739 | 0.76709 | 109 | 0.64078 | 1.0727 | 0.14901 | 0.73372 | 0.84924 | 0.69478 | 0.15669 | 69.7919 | 0.23183 | 5.0069 | 6483.8947
991 | 0.27592 | 24 | 0.32812 | 0.058027 | 0.94203 | 0.76595 | 0.097944 | 103 | 0.56414 | 1.0547 | 0.30884 | 0.79251 | 0.80556 | 0.6778 | 0.30833 | 77.9754 | 0.81983 | 10.1604 | 6066.3675
992 | 0.034451 | 21 | 0.71633 | 0.10775 | 0.12672 | 0.65034 | 0.95973 | 113 | 0.03408 | 0.93454 | 0.14213 | 0.7306 | 0.72176 | 0.64989 | 0.51424 | 89.6414 | 0.90163 | 11.4239 | 5707.3131
993 | 0.58755 | 25 | 0.74193 | 0.11201 | 0.99219 | 0.7875 | 0.27562 | 105 | 0.51591 | 1.0442 | 0.83516 | 1.0011 | 0.50004 | 0.58845 | 0.27801 | 76.4138 | 0.50756 | 6.9989 | 6386.7422
994 | 0.98301 | 29 | 0.083126 | 0.028832 | 0.21108 | 0.66497 | 0.5418 | 107 | 0.96431 | 1.1941 | 0.24095 | 0.77004 | 0.78032 | 0.66885 | 0.66607 | 99.9551 | 0.2884 | 5.3819 | 7321.581
995 | 0.33552 | 24 | 0.98691 | 0.18018 | 0.0018788 | 0.60613 | 0.067528 | 102 | 0.16151 | 0.97518 | 0.078812 | 0.69725 | 0.99481 | 0.79677 | 0.29304 | 77.1838 | 0.43955 | 6.4643 | 6444.4452
996 | 0.83237 | 27 | 0.1117 | 0.033422 | 0.19584 | 0.66258 | 0.47146 | 106 | 0.84878 | 1.135 | 0.59097 | 0.88668 | 0.48437 | 0.5839 | 0.21254 | 73.0509 | 0.29822 | 5.4485 | 6698.2578
997 | 0.16911 | 23 | 0.32389 | 0.057581 | 0.23035 | 0.66788 | 0.64709 | 108 | 0.65554 | 1.0764 | 0.023292 | 0.65287 | 0.28457 | 0.5176 | 0.27852 | 76.4398 | 0.85777 | 10.7001 | 5663.9491
998 | 0.44483 | 25 | 0.87569 | 0.13893 | 0.24649 | 0.67021 | 0.62772 | 108 | 0.52704 | 1.0466 | 0.89637 | 1.0423 | 0.6275 | 0.62318 | 0.65803 | 99.3566 | 0.56674 | 7.4951 | 6906.1134
999 | 0.51737 | 25 | 0.64913 | 0.097403 | 0.66032 | 0.71758 | 0.74624 | 109 | 0.12459 | 0.96603 | 0.7525 | 0.95628 | 0.66175 | 0.63244 | 0.77576 | 108.9903 | 0.96851 | 12.9766 | 6556.6481
1000 | 0.11607 | 22 | 0.88665 | 0.14169 | 0.052063 | 0.63227 | 0.12717 | 103 | 0.73627 | 1.0981 | 0.73753 | 0.94902 | 0.48078 | 0.58285 | 0.048225 | 60.9801 | 0.77155 | 9.5503 | 6162.0938
1001 | 0.47853 | 25 | 0.36822 | 0.062329 | 0.76369 | 0.73125 | 0.72673 | 109 | 0.33549 | 1.0089 | 0.69792 | 0.93074 | 0.70331 | 0.64434 | 0.2164 | 73.2596 | 0.78011 | 9.6534 | 6350.2351
1002 | 0.06205 | 22 | 0.67372 | 0.10106 | 0.65135 | 0.7165 | 0.18769 | 104 | 0.15598 | 0.97389 | 0.87885 | 1.0295 | 0.19234 | 0.4789 | 0.80163 | 111.4281 | 0.72342 | 9.0037 | 5893.3597
1003 | 0.85187 | 27 | 0.037678 | 0.019411 | 0.76424 | 0.73133 | 0.9002 | 111 | 0.62339 | 1.0685 | 0.91784 | 1.0596 | 0.68523 | 0.63907 | 0.14931 | 69.3206 | 0.90961 | 11.5721 | 6895.181
1004 | 0.90903 | 28 | 0.67988 | 0.102 | 0.20662 | 0.66428 | 0.37778 | 105 | 0.41404 | 1.0236 | 0.98499 | 1.14 | 0.49797 | 0.58786 | 0.01035 | 55.0866 | 0.27652 | 5.302 | 7031.216
1005 | 0.2675 | 24 | 0.89221 | 0.14313 | 0.14234 | 0.65336 | 0.95718 | 112 | 0.59456 | 1.0617 | 0.63715 | 0.9049 | 0.018389 | 0.35532 | 0.90406 | 123.1756 | 0.026089 | 3.0087 | 6169.0189
1006 | 0.0076922 | 21 | 0.036616 | 0.019135 | 0.83443 | 0.74245 | 0.93953 | 112 | 0.9452 | 1.1808 | 0.82091 | 0.99268 | 0.71043 | 0.64646 | 0.28657 | 76.8512 | 0.053837 | 3.449 | 6090.2053
1007 | 0.089327 | 22 | 0.21331 | 0.046185 | 0.77218 | 0.7325 | 0.10783 | 103 | 0.22585 | 0.98891 | 0.94386 | 1.0839 | 0.053101 | 0.394 | 0.41965 | 84.0254 | 0.84892 | 10.5683 | 5537.0008
1008 | 0.4327 | 25 | 0.15674 | 0.03959 | 0.66503 | 0.71815 | 0.66124 | 108 | 0.47558 | 1.0358 | 0.19388 | 0.75253 | 0.33495 | 0.53608 | 0.2014 | 72.4389 | 0.8503 | 10.5885 | 5880.1654
1009 | 0.89821 | 28 | 0.98686 | 0.18015 | 0.71282 | 0.72421 | 0.51815 | 106 | 0.48839 | 1.0384 | 0.54112 | 0.86814 | 0.14341 | 0.45448 | 0.79843 | 111.1182 | 0.57247 | 7.5449 | 6699.7617
1010 | 0.15273 | 23 | 0.28964 | 0.054018 | 0.41711 | 0.69134 | 0.9983 | 114 | 0.11621 | 0.96378 | 0.45216 | 0.8374 | 0.76922 | 0.66508 | 0.20206 | 72.4757 | 0.27205 | 5.272 | 5939.2161
1011 | 0.14733 | 23 | 0.18109 | 0.042554 | 0.90296 | 0.75595 | 0.13721 | 103 | 0.48781 | 1.0383 | 0.82042 | 0.9924 | 0.76075 | 0.66226 | 0.6575 | 99.3169 | 0.10015 | 3.9763 | 6195.5194
1012 | 0.20402 | 23 | 0.97708 | 0.17378 | 0.48042 | 0.69802 | 0.062332 | 102 | 0.83857 | 1.1312 | 0.73568 | 0.94813 | 0.47995 | 0.5826 | 0.55204 | 92.0371 | 0.32824 | 5.655 | 6479.0445
1013 | 0.64063 | 26 | 0.80154 | 0.12284 | 0.25526 | 0.67145 | 0.96642 | 113 | 0.72755 | 1.0956 | 0.60811 | 0.89332 | 0.62549 | 0.62264 | 0.61272 | 96.1058 | 0.78644 | 9.731 | 6972.5155
1014 | 0.59817 | 26 | 0.57998 | 0.087748 | 0.63681 | 0.71477 | 0.27072 | 105 | 0.21301 | 0.98634 | 0.13931 | 0.72929 | 0.57867 | 0.61031 | 0.58787 | 94.4033 | 0.56872 | 7.5122 | 6188.5263
1015 | 0.064043 | 22 | 0.10247 | 0.032011 | 0.13509 | 0.65198 | 0.6749 | 108 | 0.37434 | 1.016 | 0.50341 | 0.85477 | 0.46824 | 0.57913 | 0.66384 | 99.7883 | 0.35904 | 5.8718 | 5838.1089
1016 | 0.83477 | 27 | 0.41715 | 0.067767 | 0.37993 | 0.68717 | 0.63797 | 108 | 0.80805 | 1.1204 | 0.043233 | 0.67203 | 0.62819 | 0.62336 | 0.77916 | 109.3022 | 0.5592 | 7.4301 | 6683.1315
1017 | 0.9236 | 28 | 0.58632 | 0.088598 | 0.31378 | 0.67922 | 0.18313 | 104 | 0.84284 | 1.1327 | 0.56405 | 0.87654 | 0.38321 | 0.55252 | 0.13441 | 68.331 | 0.56222 | 7.4561 | 6796.6959
1018 | 0.72767 | 26 | 0.73973 | 0.11164 | 0.87919 | 0.75085 | 0.82872 | 110 | 0.7605 | 1.1052 | 0.87185 | 1.0246 | 0.33659 | 0.53666 | 0.35475 | 80.4345 | 0.91968 | 11.7686 | 6731.6245
1019 | 0.28969 | 24 | 0.63278 | 0.09504 | 0.37477 | 0.68658 | 0.020747 | 101 | 0.72164 | 1.0939 | 0.40393 | 0.82177 | 0.25769 | 0.50708 | 0.58457 | 94.1813 | 0.34978 | 5.806 | 6065.9496
1020 | 0.49645 | 25 | 0.89064 | 0.14272 | 0.47726 | 0.6977 | 0.55521 | 107 | 0.72312 | 1.0944 | 0.37023 | 0.81123 | 0.42658 | 0.56643 | 0.045755 | 60.6952 | 0.32827 | 5.6552 | 6307.8663
1021 | 0.75414 | 26 | 0.78612 | 0.1199 | 0.99214 | 0.78746 | 0.35112 | 105 | 0.81534 | 1.1229 | 0.62556 | 0.90022 | 0.83373 | 0.6885 | 0.091612 | 65.1337 | 0.97861 | 13.3325 | 6768.7071
1022 | 0.67169 | 26 | 0.34908 | 0.060259 | 0.91207 | 0.75807 | 0.33658 | 105 | 0.6282 | 1.0696 | 0.1908 | 0.75131 | 0.20781 | 0.48595 | 0.81517 | 112.7676 | 0.051821 | 3.4216 | 6087.6323
1023 | 0.16672 | 23 | 0.55198 | 0.084067 | 0.60585 | 0.71121 | 0.34668 | 105 | 0.28478 | 0.99984 | 0.04578 | 0.67412 | 0.099455 | 0.42864 | 0.63827 | 97.9135 | 0.38938 | 6.0904 | 5446.6509
1024 | 0.0036234 | 20 | 0.18711 | 0.043256 | 0.16158 | 0.65685 | 0.65334 | 108 | 0.70331 | 1.0889 | 0.48717 | 0.84917 | 0.068028 | 0.4064 | 0.20971 | 72.897 | 0.1559 | 4.4658 | 5247.4018
1025 | 0.0023652 | 20 | 0.83521 | 0.12969 | 0.75212 | 0.72959 | 0.85631 | 110 | 0.54072 | 1.0495 | 0.55811 | 0.87434 | 0.53835 | 0.5993 | 0.66379 | 99.7846 | 0.064839 | 3.5902 | 5819.894
1026 | 0.96454 | 29 | 0.17546 | 0.041888 | 0.34886 | 0.68353 | 0.10703 | 103 | 0.2388 | 0.99142 | 0.12161 | 0.7208 | 0.58992 | 0.61331 | 0.58625 | 94.294 | 0.98125 | 13.4389 | 6523.0362
1027 | 0.44126 | 25 | 0.36979 | 0.0625 | 0.59958 | 0.71051 | 0.8531 | 110 | 0.28017 | 0.99902 | 0.96645 | 1.1103 | 0.88404 | 0.71018 | 0.47591 | 87.3048 | 0.77725 | 9.6188 | 6856.3834
1028 | 0.16892 | 23 | 0.47455 | 0.074447 | 0.13984 | 0.65288 | 0.27557 | 105 | 0.39152 | 1.0193 | 0.43531 | 0.83186 | 0.015143 | 0.3502 | 0.39749 | 82.7777 | 0.003957 | 2.3928 | 5460.0527
1029 | 0.54206 | 25 | 0.91106 | 0.14834 | 0.25844 | 0.67189 | 0.79616 | 109 | 0.35685 | 1.0128 | 0.54562 | 0.86977 | 0.26752 | 0.51098 | 0.023463 | 57.6587 | 0.74442 | 9.2358 | 6165.2149
1030 | 0.88871 | 28 | 0.17032 | 0.04127 | 0.74078 | 0.728 | 0.69852 | 108 | 0.56919 | 1.0558 | 0.43664 | 0.83229 | 0.13627 | 0.45058 | 0.20522 | 72.6505 | 0.81121 | 10.046 | 6211.395
1031 | 0.61139 | 26 | 0.98773 | 0.18082 | 0.81478 | 0.73914 | 0.55713 | 107 | 0.43456 | 1.0276 | 0.061171 | 0.68568 | 0.078985 | 0.41464 | 0.97195 | 135.4968 | 0.85866 | 10.7135 | 6231.5612
1032 | 0.96801 | 29 | 0.11184 | 0.033443 | 0.61924 | 0.71273 | 0.9687 | 113 | 0.79044 | 1.1146 | 0.68651 | 0.92571 | 0.69358 | 0.64149 | 0.22415 | 73.6722 | 0.51434 | 7.0542 | 7200.9079
1033 | 0.01007 | 21 | 0.48424 | 0.07561 | 0.54538 | 0.70465 | 0.34145 | 105 | 0.93624 | 1.1753 | 0.4252 | 0.82858 | 0.075778 | 0.41229 | 0.86345 | 117.9981 | 0.81434 | 10.0872 | 5749.345
1034 | 0.90532 | 28 | 0.87585 | 0.13897 | 0.21955 | 0.66627 | 0.74222 | 109 | 0.4657 | 1.0338 | 0.30546 | 0.79145 | 0.89436 | 0.71518 | 0.30083 | 77.586 | 0.53894 | 7.258 | 7062.0127
1035 | 0.97951 | 29 | 0.72562 | 0.10927 | 0.4795 | 0.69793 | 0.59706 | 107 | 0.44273 | 1.0292 | 0.95897 | 1.1008 | 0.64784 | 0.62862 | 0.43735 | 85.0392 | 0.10788 | 4.0512 | 7381.2462
1036 | 0.63097 | 26 | 0.74772 | 0.113 | 0.77565 | 0.73301 | 0.92698 | 112 | 0.10749 | 0.96134 | 0.21917 | 0.76217 | 0.78159 | 0.66929 | 0.53767 | 91.1146 | 0.60812 | 7.8625 | 6406.6403
1037 | 0.33413 | 24 | 0.46313 | 0.07309 | 0.9783 | 0.77917 | 0.60305 | 107 | 0.56659 | 1.0553 | 0.42092 | 0.8272 | 0.77403 | 0.6667 | 0.13246 | 68.1978 | 0.89545 | 11.3133 | 6120.8852
1038 | 0.35965 | 24 | 0.15191 | 0.038976 | 0.22121 | 0.66651 | 0.17171 | 104 | 0.544 | 1.0503 | 0.40349 | 0.82163 | 0.28739 | 0.51868 | 0.43491 | 84.8985 | 0.28903 | 5.3861 | 5892.551
1039 | 0.64537 | 26 | 0.42007 | 0.068099 | 0.14989 | 0.65475 | 0.47003 | 106 | 0.028319 | 0.93148 | 0.37669 | 0.81323 | 0.090375 | 0.42263 | 0.57379 | 93.4619 | 0.70185 | 8.7743 | 5844.9043
1040 | 0.96187 | 29 | 0.77434 | 0.11772 | 0.31861 | 0.67983 | 0.39708 | 105 | 0.18879 | 0.98129 | 0.1541 | 0.73598 | 0.63751 | 0.62584 | 0.32492 | 78.8448 | 0.11611 | 4.1279 | 6626.6447
1041 | 0.89873 | 28 | 0.049169 | 0.022174 | 0.92677 | 0.76173 | 0.914 | 111 | 0.369 | 1.015 | 0.0037886 | 0.62132 | 0.24522 | 0.502 | 0.53159 | 90.7286 | 0.22132 | 4.9379 | 5944.5332
1042 | 0.62306 | 26 | 0.59467 | 0.089728 | 0.74905 | 0.72915 | 0.73562 | 109 | 0.88157 | 1.1482 | 0.099051 | 0.70902 | 0.62828 | 0.62338 | 0.26818 | 75.9147 | 0.64601 | 8.2163 | 6499.2692
1043 | 0.020371 | 21 | 0.32505 | 0.057703 | 0.34058 | 0.68253 | 0.69498 | 108 | 0.64232 | 1.0731 | 0.15129 | 0.73474 | 0.045376 | 0.38689 | 0.66269 | 99.7028 | 0.43502 | 6.4299 | 5343.6743
1044 | 0.33402 | 24 | 0.94389 | 0.15897 | 0.53219 | 0.70327 | 0.19525 | 104 | 0.93619 | 1.1753 | 0.26882 | 0.7796 | 0.89567 | 0.71584 | 0.52844 | 90.5299 | 0.11618 | 4.1286 | 6747.1523
1045 | 0.77705 | 27 | 0.64749 | 0.097163 | 0.013835 | 0.61663 | 0.31226 | 105 | 0.57412 | 1.057 | 0.78109 | 0.97079 | 0.30779 | 0.52631 | 0.81417 | 112.6673 | 0.8152 | 10.0985 | 6913.8855
1046 | 0.54427 | 25 | 0.8631 | 0.13591 | 0.86354 | 0.74776 | 0.81551 | 110 | 0.71705 | 1.0927 | 0.31882 | 0.7956 | 0.074429 | 0.41129 | 0.32555 | 78.8775 | 0.87022 | 10.8925 | 6017.5206
1047 | 0.97428 | 29 | 0.73828 | 0.11139 | 0.15759 | 0.65614 | 0.53167 | 107 | 0.026058 | 0.9302 | 0.86214 | 1.0181 | 0.62713 | 0.62308 | 0.52226 | 90.1415 | 0.61341 | 7.9108 | 7082.8666
1048 | 0.93396 | 28 | 0.12453 | 0.035288 | 0.19428 | 0.66234 | 0.8619 | 110 | 0.61569 | 1.0666 | 0.59019 | 0.88638 | 0.97974 | 0.7741 | 0.44058 | 85.2262 | 0.72093 | 8.9767 | 7303.2086
1049 | 0.90274 | 28 | 0.61132 | 0.092017 | 0.73265 | 0.72688 | 0.024916 | 101 | 0.9325 | 1.1731 | 0.64265 | 0.90715 | 0.77757 | 0.66791 | 0.54659 | 91.6858 | 0.23517 | 5.0286 | 7223.1615
1050 | 0.69433 | 26 | 0.98158 | 0.17649 | 0.14448 | 0.65375 | 0.068887 | 102 | 0.72924 | 1.0961 | 0.6691 | 0.91819 | 0.79939 | 0.67556 | 0.89926 | 122.5132 | 0.44786 | 6.5278 | 7258.334
1051 | 0.39335 | 24 | 0.82444 | 0.12743 | 0.7397 | 0.72785 | 0.67223 | 108 | 0.28141 | 0.99924 | 0.88988 | 1.0374 | 0.043104 | 0.38469 | 0.68939 | 101.7346 | 0.13099 | 4.2602 | 6022.1021
1052 | 0.52201 | 25 | 0.36149 | 0.061597 | 0.90789 | 0.75708 | 0.84154 | 110 | 0.25479 | 0.99443 | 0.53437 | 0.86571 | 0.029671 | 0.37027 | 0.51581 | 89.7384 | 0.5655 | 7.4844 | 5697.205
1053 | 0.85986 | 27 | 0.24204 | 0.049197 | 0.76059 | 0.7308 | 0.8049 | 110 | 0.78774 | 1.1137 | 0.24874 | 0.77277 | 0.6766 | 0.63661 | 0.53061 | 90.6665 | 0.92454 | 11.8679 | 6705.4694
1054 | 0.16776 | 23 | 0.072903 | 0.027001 | 0.69541 | 0.72195 | 0.1439 | 103 | 0.77528 | 1.1098 | 0.69401 | 0.92901 | 0.389 | 0.55442 | 0.81875 | 113.13 | 0.28389 | 5.3515 | 6113.7118
1055 | 0.4094 | 25 | 0.29339 | 0.054404 | 0.51874 | 0.70189 | 0.56283 | 107 | 0.41953 | 1.0246 | 0.074344 | 0.69445 | 0.59548 | 0.61478 | 0.90066 | 122.704 | 0.22173 | 4.9407 | 6200.2216
1056 | 0.40707 | 25 | 0.35458 | 0.060851 | 0.66177 | 0.71775 | 0.25049 | 104 | 0.36927 | 1.0151 | 0.1417 | 0.7304 | 0.52097 | 0.59443 | 0.65484 | 99.1208 | 0.24611 | 5.1002 | 6029.752
1057 | 0.022375 | 21 | 0.9691 | 0.16955 | 0.92466 | 0.76118 | 0.59834 | 107 | 0.52458 | 1.046 | 0.60691 | 0.89285 | 0.004997 | 0.32884 | 0.56599 | 92.9468 | 0.42388 | 6.3458 | 5484.3081
1058 | 0.50403 | 25 | 0.44697 | 0.071194 | 0.64412 | 0.71563 | 0.92792 | 112 | 0.078749 | 0.9525 | 0.036743 | 0.6664 | 0.41143 | 0.56165 | 0.24081 | 74.5362 | 0.1043 | 4.0168 | 5732.0826
1059 | 0.024227 | 21 | 0.83256 | 0.12913 | 0.061244 | 0.635 | 0.60707 | 107 | 0.48334 | 1.0374 | 0.80978 | 0.98633 | 0.38263 | 0.55233 | 0.053627 | 61.5787 | 0.83604 | 10.3832 | 5897.2968
1060 | 0.72675 | 26 | 0.090672 | 0.030112 | 0.56693 | 0.70693 | 0.84739 | 110 | 0.27467 | 0.99805 | 0.98012 | 1.1309 | 0.21946 | 0.4911 | 0.35537 | 80.4681 | 0.56388 | 7.4703 | 6394.8829
1061 | 0.035424 | 21 | 0.61703 | 0.092812 | 0.67354 | 0.7192 | 0.28785 | 105 | 0.097846 | 0.95852 | 0.97138 | 1.1171 | 0.60235 | 0.61659 | 0.59704 | 95.0255 | 0.14446 | 4.3736 | 5979.8732
1062 | 0.76177 | 27 | 0.32218 | 0.057401 | 0.41388 | 0.69098 | 0.7221 | 109 | 0.04229 | 0.93847 | 0.6599 | 0.9143 | 0.47707 | 0.58175 | 0.60465 | 95.547 | 0.78269 | 9.6849 | 6454.988
1063 | 0.48877 | 25 | 0.68874 | 0.10337 | 0.56366 | 0.70658 | 0.46377 | 106 | 0.30697 | 1.0037 | 0.81831 | 0.99118 | 0.90357 | 0.71986 | 0.10495 | 66.1982 | 0.98909 | 13.8093 | 6667.6381
1064 | 0.079149 | 22 | 0.54651 | 0.083361 | 0.53546 | 0.70361 | 0.3065 | 105 | 0.19166 | 0.9819 | 0.63517 | 0.9041 | 0.88861 | 0.71237 | 0.0086486 | 54.6499 | 0.81436 | 10.0874 | 5903.2989
1065 | 0.37991 | 24 | 0.15902 | 0.039877 | 0.076061 | 0.639 | 0.47451 | 106 | 0.5237 | 1.0459 | 0.23025 | 0.76622 | 0.45658 | 0.57564 | 0.39314 | 82.5358 | 0.70818 | 8.8407 | 5992.289
1066 | 0.9621 | 29 | 0.068885 | 0.026246 | 0.6007 | 0.71064 | 0.14236 | 103 | 0.13149 | 0.96784 | 0.039879 | 0.66918 | 0.33384 | 0.53569 | 0.65323 | 99.002 | 0.050798 | 3.4075 | 6106.1473
1067 | 0.2623 | 24 | 0.11468 | 0.033865 | 0.27638 | 0.67435 | 0.42601 | 106 | 0.32322 | 1.0067 | 0.96262 | 1.1053 | 0.75084 | 0.65903 | 0.19739 | 72.2142 | 0.7953 | 9.8414 | 6451.646
1068 | 0.90624 | 28 | 0.16147 | 0.040184 | 0.33364 | 0.68169 | 0.80485 | 110 | 0.49982 | 1.0408 | 0.29768 | 0.789 | 0.48169 | 0.58311 | 0.16572 | 70.3543 | 0.88159 | 11.0765 | 6513.5489
1069 | 0.71707 | 26 | 0.56257 | 0.085445 | 0.19806 | 0.66294 | 0.64449 | 108 | 0.6021 | 1.0634 | 0.0011724 | 0.61186 | 0.994 | 0.79502 | 0.60277 | 95.4177 | 0.30062 | 5.4649 | 6677.9411
1070 | 0.67602 | 26 | 0.9966 | 0.18991 | 0.17149 | 0.65856 | 0.67924 | 108 | 0.87209 | 1.1442 | 0.13328 | 0.72647 | 0.20938 | 0.48666 | 0.9482 | 130.2903 | 0.97276 | 13.1181 | 6808.3576
1071 | 0.39278 | 24 | 0.26699 | 0.051708 | 0.03173 | 0.62519 | 0.69503 | 108 | 0.47917 | 1.0365 | 0.68173 | 0.92362 | 0.81076 | 0.67971 | 0.095289 | 65.4345 | 0.27739 | 5.3078 | 6375.5422
1072 | 0.73904 | 26 | 0.95874 | 0.16482 | 0.61446 | 0.71219 | 0.32973 | 105 | 0.29246 | 1.0012 | 0.6671 | 0.91734 | 0.058516 | 0.39868 | 0.90321 | 123.0575 | 0.61819 | 7.9547 | 6347.3616
1073 | 0.8643 | 27 | 0.73312 | 0.11052 | 0.23436 | 0.66846 | 0.18872 | 104 | 0.77027 | 1.1082 | 0.78112 | 0.9708 | 0.65029 | 0.62929 | 0.79506 | 110.7944 | 0.54223 | 7.2857 | 7211.7179
1074 | 0.041982 | 21 | 0.031538 | 0.017759 | 0.43718 | 0.69351 | 0.50877 | 106 | 0.93743 | 1.176 | 0.2271 | 0.76508 | 0.94599 | 0.74505 | 0.15402 | 69.6229 | 0.58723 | 7.6747 | 5961.1681
1075 | 0.92341 | 28 | 0.45269 | 0.071862 | 0.067419 | 0.63672 | 0.52861 | 107 | 0.23864 | 0.99139 | 0.33093 | 0.79928 | 0.010384 | 0.34157 | 0.98725 | 140.2215 | 0.48653 | 6.8298 | 6261.8139
1076 | 0.95768 | 29 | 0.84289 | 0.13135 | 0.66397 | 0.71802 | 0.47546 | 106 | 0.45397 | 1.0314 | 0.18346 | 0.74837 | 0.58893 | 0.61305 | 0.15525 | 69.7011 | 0.72823 | 9.0561 | 6707.2397
1077 | 0.36509 | 24 | 0.65025 | 0.097567 | 0.831 | 0.74186 | 0.79898 | 110 | 0.97114 | 1.1997 | 0.44436 | 0.83483 | 0.38348 | 0.55261 | 0.32724 | 78.967 | 0.25672 | 5.1701 | 6351.8069
1078 | 0.2182 | 23 | 0.42326 | 0.068462 | 0.1606 | 0.65667 | 0.34513 | 105 | 0.79271 | 1.1153 | 0.75532 | 0.95767 | 0.19851 | 0.48175 | 0.85769 | 117.3296 | 0.96502 | 12.8676 | 6261.1989
1079 | 0.62912 | 26 | 0.95322 | 0.16254 | 0.85248 | 0.74568 | 0.065214 | 102 | 0.52762 | 1.0467 | 0.69814 | 0.93084 | 0.84241 | 0.69198 | 0.60261 | 95.4071 | 0.3869 | 6.0724 | 6884.6234
1080 | 0.18221 | 23 | 0.65967 | 0.098956 | 0.70464 | 0.72314 | 0.88215 | 111 | 0.20671 | 0.98506 | 0.19094 | 0.75137 | 0.022196 | 0.36077 | 0.65991 | 99.4956 | 0.53903 | 7.2588 | 5477.3832
1081 | 0.19507 | 23 | 0.35026 | 0.060386 | 0.57532 | 0.70784 | 0.7979 | 109 | 0.93189 | 1.1728 | 0.48414 | 0.84814 | 0.99073 | 0.78894 | 0.7775 | 109.1499 | 0.31468 | 5.5612 | 6786.179
1082 | 0.69242 | 26 | 0.049112 | 0.022161 | 0.43676 | 0.69346 | 0.13473 | 103 | 0.90467 | 1.1587 | 0.385 | 0.81581 | 0.064578 | 0.40366 | 0.31492 | 78.3195 | 0.093062 | 3.9051 | 5976.9027
1083 | 0.26046 | 24 | 0.84469 | 0.13174 | 0.57641 | 0.70796 | 0.47619 | 106 | 0.27185 | 0.99754 | 0.88965 | 1.0373 | 0.6025 | 0.61663 | 0.29302 | 77.1825 | 0.65144 | 8.2685 | 6431.4403
1084 | 0.37359 | 24 | 0.28251 | 0.053287 | 0.54112 | 0.7042 | 0.86488 | 110 | 0.86443 | 1.1411 | 0.7837 | 0.97216 | 0.29421 | 0.52126 | 0.22637 | 73.7892 | 0.067102 | 3.6177 | 6262.1428
1085 | 0.20114 | 23 | 0.81513 | 0.12553 | 0.45987 | 0.6959 | 0.27673 | 105 | 0.89828 | 1.1557 | 0.5927 | 0.88735 | 0.47799 | 0.58202 | 0.3044 | 77.7712 | 0.062553 | 3.5619 | 6297.787
1086 | 0.86243 | 27 | 0.14452 | 0.038015 | 0.74963 | 0.72924 | 0.25794 | 104 | 0.72738 | 1.0956 | 0.48149 | 0.84724 | 0.47789 | 0.58199 | 0.9021 | 122.9036 | 0.14376 | 4.3679 | 6663.3336
1087 | 0.63793 | 26 | 0.99463 | 0.18731 | 0.39064 | 0.68839 | 0.41288 | 106 | 0.49016 | 1.0388 | 0.11897 | 0.71948 | 0.54979 | 0.60247 | 0.057075 | 61.9452 | 0.97284 | 13.1209 | 6409.4222
1088 | 0.76555 | 27 | 0.75911 | 0.11499 | 0.18868 | 0.66143 | 0.012696 | 101 | 0.051865 | 0.94261 | 0.40525 | 0.82219 | 0.031368 | 0.37225 | 0.00326 | 52.8548 | 0.83752 | 10.404 | 5737.1582
1089 | 0.3071 | 24 | 0.10204 | 0.031944 | 0.45571 | 0.69547 | 0.013189 | 101 | 0.53484 | 1.0483 | 0.041628 | 0.67068 | 0.363 | 0.54577 | 0.57068 | 93.2559 | 0.73621 | 9.144 | 5718.5025
1090 | 0.93464 | 28 | 0.87526 | 0.13883 | 0.072459 | 0.63807 | 0.37418 | 105 | 0.55857 | 1.0535 | 0.59348 | 0.88765 | 0.68451 | 0.63886 | 0.010823 | 55.2016 | 0.019192 | 2.8651 | 6943.5999
1091 | 0.35458 | 24 | 0.77322 | 0.11752 | 0.41708 | 0.69133 | 0.7619 | 109 | 0.67849 | 1.0823 | 0.12282 | 0.7214 | 0.27033 | 0.51209 | 0.79252 | 110.5528 | 0.16349 | 4.5251 | 6132.9669
1092 | 0.77117 | 27 | 0.82033 | 0.12658 | 0.81864 | 0.73977 | 0.64494 | 108 | 0.02532 | 0.92977 | 0.81406 | 0.98875 | 0.87985 | 0.70822 | 0.11078 | 66.6418 | 0.023885 | 2.9652 | 6737.975
1093 | 0.32843 | 24 | 0.86059 | 0.13533 | 0.88056 | 0.75113 | 0.50643 | 106 | 0.53613 | 1.0485 | 0.3321 | 0.79963 | 0.73799 | 0.65493 | 0.040473 | 60.059 | 0.9698 | 13.0185 | 6173.926
1094 | 0.79966 | 27 | 0.8192 | 0.12635 | 0.063672 | 0.63569 | 0.84514 | 110 | 0.13491 | 0.96872 | 0.57071 | 0.87902 | 0.6958 | 0.64213 | 0.56502 | 92.8831 | 0.17163 | 4.5872 | 6810.0806
1095 | 0.2944 | 24 | 0.945 | 0.15938 | 0.6711 | 0.71889 | 0.1605 | 103 | 0.39887 | 1.0207 | 0.65265 | 0.91127 | 0.40067 | 0.55821 | 0.044095 | 60.4995 | 0.60792 | 7.8607 | 6110.2587
1096 | 0.0016038 | 20 | 0.27713 | 0.052738 | 0.70312 | 0.72294 | 0.30829 | 105 | 0.94271 | 1.1792 | 0.13566 | 0.72759 | 0.21522 | 0.48924 | 0.39713 | 82.7577 | 0.72476 | 9.0182 | 5406.7644
1097 | 0.84237 | 27 | 0.46553 | 0.073374 | 0.16421 | 0.65731 | 0.63985 | 108 | 0.087516 | 0.95535 | 0.97279 | 1.1192 | 0.054446 | 0.39518 | 0.9175 | 125.1251 | 0.40877 | 6.2331 | 6534.5443
1098 | 0.8849 | 28 | 0.30055 | 0.055143 | 0.97777 | 0.77892 | 0.14276 | 103 | 0.15591 | 0.97387 | 0.62242 | 0.89897 | 0.99192 | 0.791 | 0.91921 | 125.3845 | 0.64648 | 8.2208 | 7059.1605
1099 | 0.57387 | 25 | 0.29421 | 0.054488 | 0.46304 | 0.69623 | 0.7606 | 109 | 0.89345 | 1.1534 | 0.077939 | 0.69671 | 0.18604 | 0.47594 | 0.27469 | 76.2446 | 0.036993 | 3.2011 | 5973.8213
1100 | 0.59384 | 25 | 0.21348 | 0.046204 | 0.077641 | 0.63941 | 0.048947 | 102 | 0.51129 | 1.0432 | 0.19832 | 0.75427 | 0.71123 | 0.6467 | 0.87801 | 119.7522 | 0.91052 | 11.5893 | 6424.0016
1101 | 0.77562 | 27 | 0.87347 | 0.13839 | 0.72614 | 0.72599 | 0.45712 | 106 | 0.40617 | 1.0221 | 0.062736 | 0.68677 | 0.27117 | 0.51242 | 0.78313 | 109.6695 | 0.51838 | 7.0873 | 6305.7887
1102 | 0.44648 | 25 | 0.98139 | 0.17637 | 0.55461 | 0.70562 | 0.76857 | 109 | 0.034196 | 0.9346 | 0.80767 | 0.98515 | 0.65689 | 0.6311 | 0.045332 | 60.6457 | 0.032893 | 3.1326 | 6423.2967
1103 | 0.71086 | 26 | 0.84769 | 0.1324 | 0.036942 | 0.62718 | 0.082848 | 102 | 0.31834 | 1.0058 | 0.6884 | 0.92653 | 0.75644 | 0.66085 | 0.77293 | 108.7321 | 0.24094 | 5.0664 | 6890.2776
1104 | 0.43538 | 25 | 0.24718 | 0.049717 | 0.74412 | 0.72846 | 0.10059 | 103 | 0.80848 | 1.1205 | 0.60243 | 0.89111 | 0.58405 | 0.61175 | 0.24602 | 74.8003 | 0.40555 | 6.2092 | 6348.977
1105 | 0.25376 | 24 | 0.90309 | 0.14608 | 0.31714 | 0.67964 | 0.44283 | 106 | 0.39329 | 1.0196 | 0.24337 | 0.77089 | 0.80265 | 0.67674 | 0.57345 | 93.4389 | 0.76279 | 9.4469 | 6384.5562
1106 | 0.90884 | 28 | 0.25382 | 0.050383 | 0.48628 | 0.69862 | 0.42212 | 106 | 0.26858 | 0.99696 | 0.24885 | 0.77281 | 0.23486 | 0.49769 | 0.70081 | 102.6298 | 0.42375 | 6.3448 | 6270.2769
1107 | 0.77661 | 27 | 0.18142 | 0.042594 | 0.20308 | 0.66373 | 0.27281 | 105 | 0.53305 | 1.0479 | 0.28055 | 0.78348 | 0.15643 | 0.46134 | 0.98502 | 139.4008 | 0.97025 | 13.0333 | 6428.1597
1108 | 0.4768 | 25 | 0.82272 | 0.12707 | 0.41446 | 0.69104 | 0.31421 | 105 | 0.68178 | 1.0831 | 0.19709 | 0.75379 | 0.21063 | 0.48721 | 0.026309 | 58.1101 | 0.49317 | 6.8829 | 5978.2958
1109 | 0.31502 | 24 | 0.45428 | 0.072048 | 0.37403 | 0.68649 | 0.037431 | 102 | 0.2611 | 0.9956 | 0.81298 | 0.98814 | 0.14844 | 0.45716 | 0.083634 | 64.4598 | 0.62878 | 8.0532 | 5808.645
1110 | 0.616 | 26 | 0.47882 | 0.074958 | 0.49842 | 0.69984 | 0.0027381 | 100 | 0.33154 | 1.0082 | 0.19709 | 0.75379 | 0.27885 | 0.51541 | 0.66265 | 99.6996 | 0.14899 | 4.4106 | 6019.7367
1111 | 0.57958 | 25 | 0.16066 | 0.040082 | 0.29725 | 0.6771 | 0.17142 | 104 | 0.021519 | 0.92744 | 0.89373 | 1.0403 | 0.79988 | 0.67573 | 0.82471 | 113.7418 | 0.13033 | 4.2545 | 6537.0583
1112 | 0.91172 | 28 | 0.85366 | 0.13374 | 0.68143 | 0.72018 | 0.097775 | 103 | 0.11072 | 0.96225 | 0.4668 | 0.84227 | 0.5481 | 0.602 | 0.80239 | 111.5021 | 0.58267 | 7.6343 | 6699.8421
1113 | 0.24299 | 23 | 0.40885 | 0.06683 | 0.28293 | 0.67522 | 0.97376 | 113 | 0.24862 | 0.99328 | 0.29972 | 0.78965 | 0.95367 | 0.75058 | 0.58766 | 94.3893 | 0.038952 | 3.2325 | 6239.2124
1114 | 0.0012988 | 20 | 0.36673 | 0.062167 | 0.19213 | 0.66199 | 0.29222 | 105 | 0.75002 | 1.1021 | 0.23017 | 0.76619 | 0.81231 | 0.68029 | 0.38502 | 82.086 | 0.19314 | 4.7446 | 5724.6891
1115 | 0.57681 | 25 | 0.067016 | 0.025887 | 0.87841 | 0.75069 | 0.22304 | 104 | 0.58035 | 1.0584 | 0.53695 | 0.86664 | 0.078981 | 0.41464 | 0.91363 | 124.5491 | 0.010997 | 2.6549 | 5920.8353
1116 | 0.094172 | 22 | 0.084016 | 0.028985 | 0.36096 | 0.68497 | 0.028488 | 101 | 0.39162 | 1.0193 | 0.3953 | 0.81904 | 0.81193 | 0.68015 | 0.49887 | 88.6938 | 0.32466 | 5.6301 | 5813.8152
1117 | 0.74311 | 26 | 0.41949 | 0.068033 | 0.2706 | 0.67357 | 0.84263 | 110 | 0.17709 | 0.97873 | 0.69428 | 0.92913 | 0.29003 | 0.51969 | 0.87925 | 119.9064 | 0.39982 | 6.1669 | 6453.7905
1118 | 0.19953 | 23 | 0.1867 | 0.043209 | 0.96976 | 0.77541 | 0.077377 | 102 | 0.56685 | 1.0553 | 0.69258 | 0.92837 | 0.063656 | 0.40292 | 0.97326 | 135.8395 | 0.17596 | 4.6196 | 5775.4603
1119 | 0.5154 | 25 | 0.010124 | 0.010062 | 0.77843 | 0.73343 | 0.13413 | 103 | 0.82703 | 1.127 | 0.4253 | 0.82861 | 0.29026 | 0.51977 | 0.24505 | 74.7512 | 0.18409 | 4.6794 | 5967.2638
1120 | 0.26947 | 24 | 0.58385 | 0.088266 | 0.55678 | 0.70585 | 0.71043 | 108 | 0.27606 | 0.9983 | 0.64708 | 0.90897 | 0.019181 | 0.35649 | 0.0017739 | 52.1059 | 0.19979 | 4.7914 | 5501.2863
1121 | 0.054993 | 22 | 0.97452 | 0.17235 | 0.083525 | 0.64087 | 0.98536 | 114 | 0.059819 | 0.94576 | 0.75617 | 0.95809 | 0.62833 | 0.62339 | 0.2878 | 76.9145 | 0.19153 | 4.7331 | 6168.817
1122 | 0.18696 | 23 | 0.19987 | 0.044707 | 0.84915 | 0.74507 | 0.75961 | 109 | 0.14658 | 0.97163 | 0.76992 | 0.96501 | 0.13034 | 0.44727 | 0.66384 | 99.7888 | 0.45016 | 6.5455 | 5703.6492
1123 | 0.48188 | 25 | 0.96169 | 0.1661 | 0.029905 | 0.62446 | 0.73182 | 109 | 0.13217 | 0.96801 | 0.37781 | 0.81357 | 0.60035 | 0.61607 | 0.48205 | 87.6733 | 0.10803 | 4.0526 | 6435.1595
1124 | 0.058009 | 22 | 0.28382 | 0.053421 | 0.33003 | 0.68124 | 0.62452 | 107 | 0.71458 | 1.092 | 0.82427 | 0.99464 | 0.42141 | 0.56481 | 0.47455 | 87.2233 | 0.01006 | 2.6264 | 6051.0216
1125 | 0.97012 | 29 | 0.069277 | 0.02632 | 0.74831 | 0.72905 | 0.031232 | 102 | 0.3477 | 1.0111 | 0.99436 | 1.1632 | 0.76539 | 0.6638 | 0.92775 | 126.7217 | 0.99524 | 14.2131 | 7491.6863
1126 | 0.5156 | 25 | 0.57873 | 0.08758 | 0.090171 | 0.64247 | 0.66323 | 108 | 0.38703 | 1.0184 | 0.12491 | 0.72243 | 0.43951 | 0.57043 | 0.63778 | 97.8787 | 0.015268 | 2.7716 | 6162.9475
1127 | 0.95324 | 28 | 0.041437 | 0.020356 | 0.90844 | 0.75721 | 0.26939 | 104 | 0.35453 | 1.0123 | 0.083802 | 0.70028 | 0.2705 | 0.51216 | 0.70948 | 103.3212 | 0.58707 | 7.6733 | 6063.4443
1128 | 0.29162 | 24 | 0.42709 | 0.068899 | 0.0026825 | 0.60732 | 0.18822 | 104 | 0.4056 | 1.0219 | 0.19725 | 0.75385 | 0.53919 | 0.59953 | 0.78283 | 109.642 | 0.028224 | 3.0492 | 6164.6655
1129 | 0.62268 | 26 | 0.79805 | 0.12216 | 0.55131 | 0.70527 | 0.85461 | 110 | 0.76198 | 1.1057 | 0.27394 | 0.78131 | 0.069385 | 0.40745 | 0.73676 | 105.5671 | 0.70242 | 8.7802 | 6284.8861
1130 | 0.38592 | 24 | 0.33803 | 0.059078 | 0.094331 | 0.64344 | 0.29716 | 105 | 0.15409 | 0.97344 | 0.49064 | 0.85036 | 0.60853 | 0.61821 | 0.0023157 | 52.4061 | 0.85397 | 10.643 | 5924.0253
1131 | 0.64919 | 26 | 0.63814 | 0.095809 | 0.12113 | 0.64922 | 0.3637 | 105 | 0.43708 | 1.0281 | 0.81357 | 0.98847 | 0.082077 | 0.41687 | 0.69983 | 102.5527 | 0.44999 | 6.5442 | 6352.2874
1132 | 0.17685 | 23 | 0.48919 | 0.076209 | 0.016575 | 0.61821 | 0.43172 | 106 | 0.90452 | 1.1586 | 0.6824 | 0.92391 | 0.2436 | 0.50133 | 0.8413 | 115.5001 | 0.055174 | 3.4669 | 6367.5702
1133 | 0.71823 | 26 | 0.17195 | 0.041467 | 0.75774 | 0.73039 | 0.99405 | 114 | 0.58094 | 1.0585 | 0.78595 | 0.97335 | 0.57878 | 0.61034 | 0.75172 | 106.8481 | 0.4465 | 6.5174 | 6767.3064
1134 | 0.56797 | 25 | 0.65302 | 0.097974 | 0.37006 | 0.68603 | 0.55206 | 107 | 0.3955 | 1.02 | 0.010067 | 0.63476 | 0.77929 | 0.6685 | 0.12921 | 67.9731 | 0.6643 | 8.3939 | 6070.2373
1135 | 0.63226 | 26 | 0.9231 | 0.15197 | 0.47552 | 0.69752 | 0.28245 | 105 | 0.50518 | 1.0419 | 0.1384 | 0.72887 | 0.3585 | 0.54424 | 0.69867 | 102.4609 | 0.57445 | 7.5621 | 6377.7003
1136 | 0.30834 | 24 | 0.91068 | 0.14823 | 0.14184 | 0.65326 | 0.9824 | 113 | 0.80061 | 1.1179 | 0.55894 | 0.87465 | 0.12542 | 0.44447 | 0.19865 | 72.285 | 0.99801 | 14.4909 | 6266.8027
1137 | 0.76446 | 27 | 0.56303 | 0.085505 | 0.73636 | 0.72739 | 0.98781 | 114 | 0.5716 | 1.0564 | 0.68566 | 0.92533 | 0.43346 | 0.56856 | 0.11598 | 67.0276 | 0.27874 | 5.3169 | 6630.6344
1138 | 0.2088 | 23 | 0.72765 | 0.10961 | 0.27021 | 0.67351 | 0.72177 | 109 | 0.24969 | 0.99348 | 0.77191 | 0.96603 | 0.74932 | 0.65854 | 0.59081 | 94.602 | 0.26348 | 5.2149 | 6365.0561
1139 | 0.29418 | 24 | 0.72333 | 0.10889 | 0.5424 | 0.70433 | 0.099261 | 103 | 0.48431 | 1.0376 | 0.62255 | 0.89902 | 0.1397 | 0.45247 | 0.45437 | 86.0297 | 0.96889 | 12.9888 | 5967.8295
1140 | 0.46598 | 25 | 0.71727 | 0.1079 | 0.32379 | 0.68047 | 0.81755 | 110 | 0.53885 | 1.0491 | 0.56731 | 0.87775 | 0.49109 | 0.58586 | 0.77703 | 109.1067 | 0.28752 | 5.3759 | 6570.0575
1141 | 0.34445 | 24 | 0.094459 | 0.030734 | 0.45673 | 0.69557 | 0.038845 | 102 | 0.59205 | 1.0611 | 0.51783 | 0.85982 | 0.86235 | 0.70035 | 0.63805 | 97.8979 | 0.76072 | 9.4227 | 6349.1886
1142 | 0.015679 | 21 | 0.43929 | 0.070303 | 0.39563 | 0.68895 | 0.57424 | 107 | 0.54375 | 1.0502 | 0.14703 | 0.73283 | 0.27443 | 0.5137 | 0.77134 | 108.5883 | 0.66593 | 8.4099 | 5594.2816
1143 | 0.7806 | 27 | 0.73787 | 0.11132 | 0.38353 | 0.68758 | 0.69854 | 108 | 0.065803 | 0.94799 | 0.74255 | 0.95143 | 0.23929 | 0.49954 | 0.76004 | 107.5774 | 0.68755 | 8.6268 | 6509.23
1144 | 0.89375 | 28 | 0.45253 | 0.071844 | 0.3285 | 0.68106 | 0.78394 | 109 | 0.77422 | 1.1094 | 0.19443 | 0.75275 | 0.5035 | 0.58945 | 0.0091031 | 54.7705 | 0.54519 | 7.3107 | 6601.4469
1145 | 0.53898 | 25 | 0.16487 | 0.040604 | 0.88449 | 0.75193 | 0.42782 | 106 | 0.81459 | 1.1226 | 0.46261 | 0.84087 | 0.61738 | 0.62052 | 0.0058607 | 53.8278 | 0.77176 | 9.5528 | 6198.6751
1146 | 0.93892 | 28 | 0.65504 | 0.098271 | 0.88747 | 0.75256 | 0.72363 | 109 | 0.066344 | 0.94819 | 0.7397 | 0.95006 | 0.39094 | 0.55505 | 0.53455 | 90.9165 | 0.51915 | 7.0937 | 6577.565
1147 | 0.14331 | 23 | 0.49893 | 0.077395 | 0.2123 | 0.66516 | 0.9844 | 113 | 0.51969 | 1.045 | 0.42202 | 0.82755 | 0.72534 | 0.65099 | 0.57818 | 93.7536 | 0.352 | 5.8218 | 6253.3257
1148 | 0.57206 | 25 | 0.72075 | 0.10847 | 0.741 | 0.72803 | 0.58234 | 107 | 0.67942 | 1.0825 | 0.080791 | 0.69846 | 0.95942 | 0.75503 | 0.98682 | 140.0588 | 0.05465 | 3.4599 | 6783.8344
1149 | 0.22394 | 23 | 0.42751 | 0.068948 | 0.028189 | 0.62374 | 0.65815 | 108 | 0.25724 | 0.99489 | 0.52323 | 0.86173 | 0.56298 | 0.60607 | 0.81491 | 112.7417 | 0.39559 | 6.1359 | 6176.4275
1150 | 0.024446 | 21 | 0.71204 | 0.10706 | 0.71082 | 0.72395 | 0.60937 | 107 | 0.0075271 | 0.91623 | 0.099164 | 0.70909 | 0.1388 | 0.45197 | 0.9269 | 126.5855 | 0.97209 | 13.0951 | 5399.5504
1151 | 0.8134 | 27 | 0.014572 | 0.012071 | 0.21205 | 0.66512 | 0.99839 | 115 | 0.17338 | 0.9779 | 0.37529 | 0.81279 | 0.082474 | 0.41715 | 0.40339 | 83.1075 | 0.48123 | 6.7878 | 5941.1835
1152 | 0.78198 | 27 | 0.41016 | 0.066976 | 0.21628 | 0.66577 | 0.36232 | 105 | 0.25539 | 0.99454 | 0.12591 | 0.72292 | 0.84722 | 0.69395 | 0.48324 | 87.7447 | 0.23083 | 5.0004 | 6484.3772
1153 | 0.89825 | 28 | 0.79672 | 0.12191 | 0.36916 | 0.68593 | 0.70271 | 108 | 0.48639 | 1.038 | 0.53498 | 0.86593 | 0.87907 | 0.70785 | 0.89535 | 121.9842 | 0.84404 | 10.4973 | 7338.2301
1154 | 0.6765 | 26 | 0.63095 | 0.094779 | 0.1786 | 0.65977 | 0.41853 | 106 | 0.63062 | 1.0702 | 0.0078376 | 0.63067 | 0.28093 | 0.51621 | 0.18522 | 71.5187 | 0.69047 | 8.6566 | 6029.4745
1155 | 0.56341 | 25 | 0.4046 | 0.066351 | 0.041006 | 0.62864 | 0.54328 | 107 | 0.53623 | 1.0486 | 0.6233 | 0.89932 | 0.15872 | 0.46251 | 0.4698 | 86.9407 | 0.93996 | 12.2061 | 6183.9509
1156 | 0.57341 | 25 | 0.49704 | 0.077164 | 0.74932 | 0.72919 | 0.92773 | 112 | 0.58877 | 1.0603 | 0.76698 | 0.96352 | 0.067118 | 0.40568 | 0.63139 | 97.421 | 0.71635 | 8.9276 | 6152.5659
1157 | 0.61833 | 26 | 0.22924 | 0.047879 | 0.59941 | 0.71049 | 0.96562 | 113 | 0.14685 | 0.97169 | 0.88098 | 1.031 | 0.85187 | 0.69588 | 0.96292 | 133.3242 | 0.88131 | 11.0719 | 7035.1907
1158 | 0.24024 | 23 | 0.35895 | 0.061322 | 0.71746 | 0.72483 | 0.23013 | 104 | 0.82985 | 1.128 | 0.88861 | 1.0365 | 0.40114 | 0.55836 | 0.17606 | 70.9798 | 0.39132 | 6.1046 | 6170.2557
1159 | 0.35505 | 24 | 0.17553 | 0.041897 | 0.88536 | 0.75212 | 0.51035 | 106 | 0.86889 | 1.1429 | 0.43372 | 0.83134 | 0.53749 | 0.59906 | 0.59535 | 94.9101 | 0.55952 | 7.4328 | 6234.3347
1160 | 0.65945 | 26 | 0.92429 | 0.15234 | 0.092011 | 0.6429 | 0.31784 | 105 | 0.54645 | 1.0508 | 0.87126 | 1.0242 | 0.2301 | 0.49567 | 0.00036731 | 50.9583 | 0.23872 | 5.0518 | 6507.2312
1161 | 0.32852 | 24 | 0.59715 | 0.090065 | 0.56138 | 0.70634 | 0.93123 | 112 | 0.87939 | 1.1473 | 0.50452 | 0.85516 | 0.58714 | 0.61257 | 0.18849 | 71.7078 | 0.17232 | 4.5924 | 6425.9619
1162 | 0.33399 | 24 | 0.79547 | 0.12167 | 0.94702 | 0.76745 | 0.62779 | 108 | 0.4476 | 1.0301 | 0.27316 | 0.78105 | 0.27 | 0.51196 | 0.45324 | 85.9632 | 0.55007 | 7.3521 | 5903.9327
1163 | 0.42983 | 25 | 0.2088 | 0.045694 | 0.68326 | 0.72041 | 0.27967 | 105 | 0.032735 | 0.93385 | 0.79862 | 0.98016 | 0.69885 | 0.64303 | 0.42905 | 84.562 | 0.76717 | 9.4983 | 6239.9818
1164 | 0.51715 | 25 | 0.74819 | 0.11308 | 0.51056 | 0.70106 | 0.84022 | 110 | 0.83142 | 1.1285 | 0.68586 | 0.92542 | 0.17094 | 0.46866 | 0.43988 | 85.1854 | 0.74345 | 9.2249 | 6416.3479
1165 | 0.89082 | 28 | 0.73621 | 0.11104 | 0.80657 | 0.7378 | 0.99458 | 114 | 0.62548 | 1.069 | 0.00604 | 0.62692 | 0.89161 | 0.71383 | 0.53918 | 91.2113 | 0.42453 | 6.3506 | 6836.5479
1166 | 0.81592 | 27 | 0.5507 | 0.083901 | 0.79096 | 0.73534 | 0.87576 | 111 | 0.53564 | 1.0484 | 0.018549 | 0.64718 | 0.8385 | 0.6904 | 0.35215 | 80.2944 | 0.93122 | 12.0098 | 6500.3646
1167 | 0.172 | 23 | 0.58128 | 0.087921 | 0.5748 | 0.70778 | 0.88212 | 111 | 0.82651 | 1.1268 | 0.64799 | 0.90934 | 0.17038 | 0.46838 | 0.20565 | 72.6741 | 0.85489 | 10.6567 | 6005.94
1168 | 0.36045 | 24 | 0.52977 | 0.081227 | 0.37897 | 0.68706 | 0.51783 | 106 | 0.88221 | 1.1485 | 0.45945 | 0.83982 | 0.8329 | 0.68817 | 0.48323 | 87.7444 | 0.33673 | 5.7143 | 6591.2275
1169 | 0.059119 | 22 | 0.048683 | 0.022064 | 0.17654 | 0.65942 | 0.90818 | 111 | 0.64801 | 1.0745 | 0.77756 | 0.96895 | 0.57813 | 0.61016 | 0.55755 | 92.3948 | 0.82961 | 10.2935 | 6143.7906
1170 | 0.79767 | 27 | 0.5805 | 0.087817 | 0.54217 | 0.70431 | 0.43792 | 106 | 0.72852 | 1.0959 | 0.26194 | 0.77729 | 0.82911 | 0.68669 | 0.79387 | 110.6813 | 0.4912 | 6.8671 | 6930.4344
1171 | 0.63977 | 26 | 0.20179 | 0.044921 | 0.92647 | 0.76165 | 0.63457 | 108 | 0.18064 | 0.97951 | 0.76333 | 0.96167 | 0.76751 | 0.6645 | 0.26418 | 75.7125 | 0.57784 | 7.5919 | 6428.7849
1172 | 0.54307 | 25 | 0.30791 | 0.055908 | 0.53804 | 0.70388 | 0.22092 | 104 | 0.79796 | 1.117 | 0.038532 | 0.668 | 0.31952 | 0.53058 | 0.99477 | 143.7378 | 0.73235 | 9.1014 | 6275.7497
1173 | 0.93402 | 28 | 0.071795 | 0.026795 | 0.21918 | 0.66621 | 0.91848 | 112 | 0.55511 | 1.0527 | 0.66892 | 0.91811 | 0.026571 | 0.36649 | 0.58455 | 94.1799 | 0.51009 | 7.0195 | 6303.8139
1174 | 0.17001 | 23 | 0.5605 | 0.085175 | 0.31797 | 0.67975 | 0.79553 | 109 | 0.14614 | 0.97152 | 0.06325 | 0.68712 | 0.14138 | 0.45338 | 0.27198 | 76.1073 | 0.83285 | 10.3385 | 5441.1166
1175 | 0.026304 | 21 | 0.093547 | 0.030585 | 0.68306 | 0.72038 | 0.3434 | 105 | 0.43724 | 1.0281 | 0.57886 | 0.88208 | 0.037821 | 0.37933 | 0.30967 | 78.0454 | 0.053249 | 3.4411 | 5164.601
1176 | 0.91385 | 28 | 0.17271 | 0.041558 | 0.89663 | 0.75453 | 0.92373 | 112 | 0.91223 | 1.1624 | 0.089593 | 0.70369 | 0.46254 | 0.57743 | 0.92456 | 126.2135 | 0.78369 | 9.6972 | 6855.6343
1177 | 0.2619 | 24 | 0.35623 | 0.061029 | 0.58151 | 0.70851 | 0.10106 | 103 | 0.60571 | 1.0643 | 0.77731 | 0.96882 | 0.35676 | 0.54365 | 0.32046 | 78.6099 | 0.86871 | 10.8686 | 6144.1509
1178 | 0.78547 | 27 | 0.43328 | 0.069609 | 0.29862 | 0.67728 | 0.21323 | 104 | 0.87938 | 1.1473 | 0.40361 | 0.82167 | 0.71305 | 0.64725 | 0.27444 | 76.2323 | 0.29331 | 5.4151 | 6828.559
1179 | 0.90777 | 28 | 0.14041 | 0.037471 | 0.032043 | 0.62532 | 0.64451 | 108 | 0.44708 | 1.03 | 0.071622 | 0.69271 | 0.78359 | 0.66998 | 0.63317 | 97.5481 | 0.98724 | 13.7122 | 6737.365
1180 | 0.96307 | 29 | 0.73775 | 0.1113 | 0.80358 | 0.73732 | 0.93299 | 112 | 0.0074117 | 0.91611 | 0.7941 | 0.9777 | 0.022866 | 0.36168 | 0.55531 | 92.2492 | 0.44859 | 6.5334 | 6290.6495
1181 | 0.78951 | 27 | 0.94622 | 0.15983 | 0.91836 | 0.75959 | 0.10941 | 103 | 0.79258 | 1.1153 | 0.72282 | 0.94208 | 0.81674 | 0.68195 | 0.89103 | 121.4126 | 0.63752 | 8.1354 | 7311.8948
1182 | 0.042014 | 21 | 0.6152 | 0.092557 | 0.27028 | 0.67352 | 0.77112 | 109 | 0.30334 | 1.0031 | 0.29164 | 0.78708 | 0.25413 | 0.50564 | 0.63584 | 97.7392 | 0.16458 | 4.5335 | 5568.9464
1183 | 0.95178 | 28 | 0.92249 | 0.15178 | 0.95933 | 0.77148 | 0.18376 | 104 | 0.15305 | 0.97319 | 0.00058857 | 0.6084 | 0.6447 | 0.62777 | 0.62995 | 97.3181 | 0.78039 | 9.6568 | 6319.4815
1184 | 0.88389 | 28 | 0.22382 | 0.04731 | 0.78086 | 0.7338 | 0.72736 | 109 | 0.14278 | 0.97069 | 0.21178 | 0.75942 | 0.92706 | 0.73291 | 0.09535 | 65.4394 | 0.077956 | 3.7436 | 6497.4788
1185 | 0.42231 | 25 | 0.66945 | 0.10042 | 0.11444 | 0.64784 | 0.94226 | 112 | 0.61606 | 1.0667 | 0.69062 | 0.92751 | 0.65889 | 0.63165 | 0.21128 | 72.9824 | 0.8262 | 10.2467 | 6680.2941
1186 | 0.50247 | 25 | 0.47781 | 0.074837 | 0.17743 | 0.65957 | 0.94461 | 112 | 0.65823 | 1.0771 | 0.73502 | 0.94782 | 0.14628 | 0.45601 | 0.48827 | 88.0484 | 0.30275 | 5.4794 | 6295.7955
1187 | 0.14471 | 23 | 0.05502 | 0.023456 | 0.66794 | 0.71851 | 0.744 | 109 | 0.90064 | 1.1568 | 0.53478 | 0.86586 | 0.013924 | 0.34813 | 0.49157 | 88.2484 | 0.015193 | 2.7698 | 5610.7749
1188 | 0.065912 | 22 | 0.48618 | 0.075844 | 0.9685 | 0.7749 | 0.49291 | 106 | 0.92371 | 1.1683 | 0.08277 | 0.69966 | 0.39552 | 0.55654 | 0.19592 | 72.1315 | 0.63746 | 8.1349 | 5683.889
1189 | 0.74313 | 26 | 0.28056 | 0.053088 | 0.48617 | 0.69861 | 0.59499 | 107 | 0.9259 | 1.1695 | 0.75105 | 0.95557 | 0.4827 | 0.58341 | 0.91642 | 124.9631 | 0.38871 | 6.0855 | 6990.2477
1190 | 0.26514 | 24 | 0.80956 | 0.12442 | 0.25818 | 0.67186 | 0.3109 | 105 | 0.84338 | 1.1329 | 0.67758 | 0.92183 | 0.063071 | 0.40245 | 0.70444 | 102.9181 | 0.66144 | 8.3657 | 6219.8147
1191 | 0.31481 | 24 | 0.81545 | 0.12559 | 0.44872 | 0.69473 | 0.87461 | 111 | 0.56685 | 1.0553 | 0.79622 | 0.97885 | 0.14171 | 0.45356 | 0.71071 | 103.4198 | 0.69851 | 8.7396 | 6301.8634
1192 | 0.11269 | 22 | 0.70926 | 0.10661 | 0.89871 | 0.75499 | 0.16291 | 103 | 0.76683 | 1.1072 | 0.40299 | 0.82147 | 0.97223 | 0.76626 | 0.22747 | 73.8467 | 0.45046 | 6.5477 | 6178.9972
1193 | 0.96002 | 29 | 0.68775 | 0.10321 | 0.012082 | 0.61554 | 0.33911 | 105 | 0.15986 | 0.9748 | 0.84411 | 1.0066 | 0.5393 | 0.59956 | 0.61996 | 96.6116 | 0.34258 | 5.7553 | 7158.9946
1194 | 0.22916 | 23 | 0.69074 | 0.10368 | 0.76401 | 0.7313 | 0.94174 | 112 | 0.19352 | 0.9823 | 0.58722 | 0.88525 | 0.44349 | 0.57166 | 0.32166 | 78.6731 | 0.72957 | 9.0707 | 5953.1327
1195 | 0.59127 | 25 | 0.38154 | 0.063788 | 0.41493 | 0.6911 | 0.45049 | 106 | 0.98704 | 1.2163 | 0.76591 | 0.96297 | 0.46456 | 0.57803 | 0.61003 | 95.9191 | 0.77312 | 9.5692 | 6827.0399
1196 | 0.024341 | 21 | 0.6388 | 0.095904 | 0.45331 | 0.69522 | 0.69864 | 108 | 0.44226 | 1.0291 | 0.15714 | 0.73732 | 0.90807 | 0.72222 | 0.37499 | 81.5341 | 0.25847 | 5.1817 | 5832.1761
1197 | 0.75654 | 27 | 0.41851 | 0.067922 | 0.01309 | 0.61618 | 0.78408 | 109 | 0.8353 | 1.13 | 0.94323 | 1.0833 | 0.91509 | 0.72603 | 0.89167 | 121.4967 | 0.1133 | 4.1021 | 7806.0894
1198 | 0.01872 | 21 | 0.54955 | 0.083753 | 0.93752 | 0.76465 | 0.86051 | 110 | 0.78639 | 1.1133 | 0.36382 | 0.80925 | 0.8287 | 0.68653 | 0.93862 | 128.5439 | 0.36607 | 5.922 | 6173.6462
1199 | 0.061829 | 22 | 0.6304 | 0.094701 | 0.40333 | 0.68981 | 0.61509 | 107 | 0.74718 | 1.1013 | 0.13873 | 0.72903 | 0.21087 | 0.48732 | 0.28127 | 76.58 | 0.98941 | 13.8268 | 5678.8221
1200 | 0.86694 | 27 | 0.84101 | 0.13094 | 0.051983 | 0.63224 | 0.89802 | 111 | 0.32606 | 1.0072 | 0.64509 | 0.90814 | 0.5529 | 0.60332 | 0.58337 | 94.101 | 0.26789 | 5.2443 | 6894.9276
1201 | 0.50569 | 25 | 0.53795 | 0.082265 | 0.61963 | 0.71278 | 0.20742 | 104 | 0.22157 | 0.98806 | 0.84526 | 1.0073 | 0.30689 | 0.52598 | 0.74875 | 106.5909 | 0.56137 | 7.4487 | 6318.1485
1202 | 0.2989 | 24 | 0.63433 | 0.095261 | 0.33126 | 0.68139 | 0.78465 | 109 | 0.53845 | 1.049 | 0.50427 | 0.85507 | 0.36037 | 0.54488 | 0.64969 | 98.7429 | 0.21529 | 4.8976 | 6214.9876
1203 | 0.011328 | 21 | 0.62645 | 0.094139 | 0.88607 | 0.75227 | 0.54541 | 107 | 0.65722 | 1.0768 | 0.59808 | 0.88942 | 0.81933 | 0.68293 | 0.7901 | 110.3236 | 0.99022 | 13.8722 | 6149.9627
1204 | 0.17365 | 23 | 0.94951 | 0.16108 | 0.61616 | 0.71238 | 0.97513 | 113 | 0.44625 | 1.0299 | 0.32734 | 0.79819 | 0.50098 | 0.58873 | 0.375 | 81.5348 | 0.56114 | 7.4468 | 6133.7608
1205 | 0.07749 | 22 | 0.98202 | 0.17677 | 0.86623 | 0.74827 | 0.017736 | 101 | 0.32593 | 1.0071 | 0.62394 | 0.89958 | 0.50069 | 0.58864 | 0.07798 | 63.9625 | 0.35687 | 5.8563 | 5848.6838
1206 | 0.14243 | 23 | 0.34287 | 0.059594 | 0.82969 | 0.74164 | 0.22579 | 104 | 0.76075 | 1.1053 | 0.7465 | 0.95334 | 0.0032765 | 0.32335 | 0.90476 | 123.2739 | 0.436 | 6.4373 | 5763.742
1207 | 0.14114 | 23 | 0.17867 | 0.04227 | 0.30481 | 0.67808 | 0.14022 | 103 | 0.10507 | 0.96064 | 0.31372 | 0.79403 | 0.67303 | 0.6356 | 0.044684 | 60.5693 | 0.34949 | 5.804 | 5636.403
1208 | 0.020522 | 21 | 0.79503 | 0.12158 | 0.81746 | 0.73958 | 0.54998 | 107 | 0.64289 | 1.0732 | 0.020677 | 0.64981 | 0.52726 | 0.5962 | 0.86771 | 118.5012 | 0.67986 | 8.5488 | 5785.9015
1209 | 0.73576 | 26 | 0.76322 | 0.11572 | 0.88325 | 0.75168 | 0.94964 | 112 | 0.78664 | 1.1134 | 0.46057 | 0.84019 | 0.054335 | 0.39509 | 0.42027 | 84.0609 | 0.1871 | 4.7013 | 6172.506
1210 | 0.0051956 | 21 | 0.70779 | 0.10637 | 0.068474 | 0.63701 | 0.6597 | 108 | 0.19944 | 0.98355 | 0.83719 | 1.0023 | 0.86882 | 0.7032 | 0.91748 | 125.1225 | 0.381 | 6.0295 | 6358.8057
1211 | 0.13345 | 23 | 0.93637 | 0.15631 | 0.8932 | 0.75378 | 0.50569 | 106 | 0.52678 | 1.0465 | 0.53407 | 0.8656 | 0.38012 | 0.5515 | 0.91442 | 124.6647 | 0.40025 | 6.1701 | 6249.5187
1212 | 0.9481 | 28 | 0.22858 | 0.04781 | 0.002844 | 0.60754 | 0.81765 | 110 | 0.68161 | 1.0831 | 0.89137 | 1.0385 | 0.94228 | 0.74252 | 0.44715 | 85.6074 | 0.93615 | 12.1188 | 7667.6311
1213 | 0.39615 | 24 | 0.79783 | 0.12212 | 0.70993 | 0.72383 | 0.32963 | 105 | 0.49375 | 1.0395 | 0.80358 | 0.98288 | 0.88002 | 0.70829 | 0.30337 | 77.7179 | 0.70652 | 8.8232 | 6592.9025
1214 | 0.48465 | 25 | 0.69459 | 0.10428 | 0.53318 | 0.70338 | 0.59951 | 107 | 0.02866 | 0.93167 | 0.082313 | 0.69939 | 0.46228 | 0.57735 | 0.61355 | 96.1634 | 0.61816 | 7.9545 | 5923.5634
1215 | 0.24537 | 24 | 0.014215 | 0.011922 | 0.63003 | 0.71398 | 0.73678 | 109 | 0.97684 | 1.205 | 0.29273 | 0.78742 | 0.47778 | 0.58196 | 0.40404 | 83.1444 | 0.30542 | 5.4976 | 6225.1545
1216 | 0.2317 | 23 | 0.54982 | 0.083788 | 0.43604 | 0.69339 | 0.7138 | 108 | 0.37509 | 1.0162 | 0.28712 | 0.78562 | 0.11584 | 0.43884 | 0.11889 | 67.2404 | 0.54905 | 7.3434 | 5526.5228
1217 | 0.71237 | 26 | 0.0021031 | 0.0045859 | 0.98087 | 0.78044 | 0.26292 | 104 | 0.60818 | 1.0648 | 0.031127 | 0.66112 | 0.90605 | 0.72116 | 0.36999 | 81.2608 | 0.59272 | 7.7236 | 6125.5466
1218 | 0.8462 | 27 | 0.20055 | 0.044782 | 0.48658 | 0.69865 | 0.93779 | 112 | 0.89191 | 1.1527 | 0.77356 | 0.96688 | 0.46262 | 0.57745 | 0.58844 | 94.442 | 0.63941 | 8.1533 | 7018.3455
1219 | 0.91856 | 28 | 0.58022 | 0.08778 | 0.34305 | 0.68283 | 0.69795 | 108 | 0.6204 | 1.0678 | 0.91947 | 1.061 | 0.35866 | 0.5443 | 0.92766 | 126.7065 | 0.080531 | 3.7722 | 7226.2102
1220 | 0.5703 | 25 | 0.93391 | 0.15547 | 0.053757 | 0.63279 | 0.6039 | 107 | 0.91813 | 1.1654 | 0.45189 | 0.83731 | 0.43878 | 0.57021 | 0.79825 | 111.1014 | 0.344 | 5.7653 | 6881.3011
1221 | 0.33468 | 24 | 0.50566 | 0.078221 | 0.71183 | 0.72408 | 0.5154 | 106 | 0.64076 | 1.0727 | 0.34868 | 0.80463 | 0.52231 | 0.59481 | 0.75636 | 107.2531 | 0.83111 | 10.3143 | 6242.2005
1222 | 0.34738 | 24 | 0.11715 | 0.034228 | 0.20232 | 0.66361 | 0.97215 | 113 | 0.92534 | 1.1692 | 0.07937 | 0.69759 | 0.47984 | 0.58257 | 0.93772 | 128.3876 | 0.95567 | 12.5993 | 6461.4895
1223 | 0.7848 | 27 | 0.83018 | 0.12862 | 0.89529 | 0.75424 | 0.79318 | 109 | 0.88611 | 1.1502 | 0.081606 | 0.69896 | 0.92692 | 0.73282 | 0.0070827 | 54.2079 | 0.21216 | 4.8765 | 6804.383
1224 | 0.81718 | 27 | 0.70259 | 0.10554 | 0.49649 | 0.69965 | 0.68385 | 108 | 0.83397 | 1.1295 | 0.093003 | 0.70564 | 0.78004 | 0.66875 | 0.47671 | 87.3528 | 0.54937 | 7.3461 | 6817.0531
1225 | 0.98957 | 29 | 0.0080104 | 0.0089501 | 0.38049 | 0.68723 | 0.3799 | 105 | 0.2017 | 0.98402 | 0.84656 | 1.0081 | 0.35091 | 0.54164 | 0.80641 | 111.8962 | 0.85191 | 10.6124 | 6820.2084
1226 | 0.45189 | 25 | 0.62033 | 0.093275 | 0.25796 | 0.67183 | 0.82524 | 110 | 0.74399 | 1.1003 | 0.70007 | 0.9317 | 0.34624 | 0.54003 | 0.34316 | 79.8126 | 0.22128 | 4.9377 | 6481.7591
1227 | 0.93684 | 28 | 0.57283 | 0.086797 | 0.75276 | 0.72968 | 0.7922 | 109 | 0.74093 | 1.0994 | 0.95873 | 1.1005 | 0.6443 | 0.62766 | 0.19573 | 72.1206 | 0.035077 | 3.1696 | 7257.5585
1228 | 0.77737 | 27 | 0.9774 | 0.17396 | 0.07276 | 0.63815 | 0.23619 | 104 | 0.80012 | 1.1178 | 0.80355 | 0.98287 | 0.70423 | 0.64461 | 0.81586 | 112.8371 | 0.17427 | 4.607 | 7480.2962
1229 | 0.10058 | 22 | 0.26766 | 0.051776 | 0.099692 | 0.64465 | 0.58475 | 107 | 0.92163 | 1.1672 | 0.00203 | 0.61561 | 0.21363 | 0.48854 | 0.35617 | 80.5112 | 0.49532 | 6.9001 | 5613.2656
1230 | 0.23717 | 23 | 0.22584 | 0.047523 | 0.46481 | 0.69642 | 0.090592 | 103 | 0.5983 | 1.0625 | 0.024457 | 0.65417 | 0.78492 | 0.67044 | 0.28242 | 76.6391 | 0.58014 | 7.6121 | 5795.2286
1231 | 0.17045 | 23 | 0.68323 | 0.10252 | 0.82005 | 0.74001 | 0.36763 | 105 | 0.60228 | 1.0635 | 0.28011 | 0.78334 | 0.85554 | 0.69743 | 0.18487 | 71.4983 | 0.95757 | 12.6513 | 6110.8077
1232 | 0.85162 | 27 | 0.33708 | 0.058976 | 0.25196 | 0.67099 | 0.89948 | 111 | 0.69905 | 1.0877 | 0.4466 | 0.83556 | 0.58781 | 0.61275 | 0.43355 | 84.8205 | 0.95801 | 12.6636 | 6782.9328
1233 | 0.96512 | 29 | 0.02158 | 0.01469 | 0.039151 | 0.62798 | 0.38936 | 105 | 0.98956 | 1.2198 | 0.24321 | 0.77084 | 0.31415 | 0.52864 | 0.60125 | 95.3134 | 0.97909 | 13.3514 | 7027.3526
1234 | 0.22619 | 23 | 0.20421 | 0.04519 | 0.42121 | 0.69178 | 0.76477 | 109 | 0.99067 | 1.2214 | 0.9188 | 1.0604 | 0.62967 | 0.62375 | 0.1013 | 65.9137 | 0.17566 | 4.6174 | 6578.5742
1235 | 0.92782 | 28 | 0.93889 | 0.15718 | 0.42315 | 0.69199 | 0.2534 | 104 | 0.58343 | 1.0591 | 0.84953 | 1.01 | 0.19388 | 0.47962 | 0.21535 | 73.2028 | 0.62538 | 8.0214 | 6798.9344
1236 | 0.35442 | 24 | 0.56186 | 0.085352 | 0.9509 | 0.76866 | 0.29214 | 105 | 0.66541 | 1.0789 | 0.7131 | 0.9376 | 0.42227 | 0.56508 | 0.87822 | 119.7789 | 0.66739 | 8.4243 | 6367.9294
1237 | 0.91618 | 28 | 0.95611 | 0.16371 | 0.12411 | 0.64982 | 0.045827 | 102 | 0.90084 | 1.1569 | 0.24141 | 0.7702 | 0.55173 | 0.603 | 0.14444 | 69.0028 | 0.31112 | 5.5367 | 6998.3109
1238 | 0.07829 | 22 | 0.14054 | 0.037488 | 0.23765 | 0.66894 | 0.46241 | 106 | 0.058347 | 0.94519 | 0.89044 | 1.0378 | 0.88995 | 0.71302 | 0.58484 | 94.1996 | 0.71949 | 8.9613 | 6152.3141
1239 | 0.49446 | 25 | 0.22136 | 0.047048 | 0.71591 | 0.72462 | 0.86462 | 110 | 0.36505 | 1.0143 | 0.070395 | 0.69191 | 0.46087 | 0.57693 | 0.22874 | 73.9135 | 0.05261 | 3.4324 | 5837.5397
1240 | 0.20117 | 23 | 0.7737 | 0.1176 | 0.79789 | 0.73642 | 0.81538 | 110 | 0.90138 | 1.1571 | 0.50056 | 0.85379 | 0.95085 | 0.7485 | 0.63379 | 97.5919 | 0.99484 | 14.1807 | 6755.4775
1241 | 0.82424 | 27 | 0.032262 | 0.017962 | 0.093865 | 0.64333 | 0.88385 | 111 | 0.96935 | 1.1982 | 0.93091 | 1.0712 | 0.8528 | 0.69627 | 0.5946 | 94.859 | 0.9935 | 14.0809 | 7672.0284
1242 | 0.23007 | 23 | 0.54711 | 0.083437 | 0.21763 | 0.66597 | 0.49346 | 106 | 0.93482 | 1.1745 | 0.79044 | 0.97574 | 0.65567 | 0.63076 | 0.89854 | 122.4141 | 0.64041 | 8.1628 | 6768.9439
1243 | 0.040269 | 21 | 0.99575 | 0.18871 | 0.47352 | 0.69732 | 0.95946 | 113 | 0.35838 | 1.0131 | 0.3024 | 0.79049 | 0.94431 | 0.74389 | 0.15662 | 69.7874 | 0.68494 | 8.6002 | 6120.9491
1244 | 0.99818 | 30 | 0.97119 | 0.1706 | 0.46459 | 0.69639 | 0.34885 | 105 | 0.35331 | 1.0121 | 0.41262 | 0.82454 | 0.10935 | 0.43489 | 0.84154 | 115.5263 | 0.23917 | 5.0547 | 6788.512
1245 | 0.66658 | 26 | 0.198 | 0.044497 | 0.47002 | 0.69696 | 0.74266 | 109 | 0.58215 | 1.0588 | 0.72093 | 0.9412 | 0.45688 | 0.57573 | 0.092757 | 65.228 | 0.50373 | 6.9679 | 6417.7224
1246 | 0.36848 | 24 | 0.092057 | 0.030341 | 0.73503 | 0.7272 | 0.51687 | 106 | 0.3619 | 1.0137 | 0.10636 | 0.71298 | 0.32815 | 0.53368 | 0.56426 | 92.8334 | 0.8227 | 10.1991 | 5698.7382
1247 | 0.87199 | 27 | 0.77818 | 0.11842 | 0.34789 | 0.68341 | 0.4298 | 106 | 0.76497 | 1.1066 | 0.9344 | 1.0745 | 0.23615 | 0.49823 | 0.14511 | 69.0469 | 0.41159 | 6.2539 | 6828.0311
1248 | 0.042203 | 21 | 0.9623 | 0.16637 | 0.84089 | 0.74359 | 0.12225 | 103 | 0.56597 | 1.0551 | 0.32568 | 0.79769 | 0.97848 | 0.77269 | 0.50867 | 89.2962 | 0.059967 | 3.5293 | 6116.7552
1249 | 0.67792 | 26 | 0.6822 | 0.10236 | 0.95894 | 0.77134 | 0.010571 | 101 | 0.87554 | 1.1456 | 0.60237 | 0.89108 | 0.40662 | 0.56012 | 0.46749 | 86.8033 | 0.76158 | 9.4327 | 6520.4017
1250 | 0.23208 | 23 | 0.80102 | 0.12274 | 0.65685 | 0.71716 | 0.22469 | 104 | 0.51008 | 1.043 | 0.10273 | 0.71103 | 0.28992 | 0.51964 | 0.91117 | 124.1893 | 0.31745 | 5.5803 | 5930.7146
1251 | 0.33559 | 24 | 0.85053 | 0.13304 | 0.34558 | 0.68314 | 0.66033 | 108 | 0.05498 | 0.94387 | 0.013028 | 0.63954 | 0.17872 | 0.47245 | 0.24326 | 74.6608 | 0.34391 | 5.7646 | 5538.9273
1252 | 0.067336 | 22 | 0.47452 | 0.074444 | 0.76404 | 0.7313 | 0.81858 | 110 | 0.83344 | 1.1293 | 0.74967 | 0.95489 | 0.86355 | 0.70088 | 0.0078149 | 54.4201 | 0.40075 | 6.1738 | 6230.0964
1253 | 0.095758 | 22 | 0.36576 | 0.062061 | 0.25219 | 0.67102 | 0.47339 | 106 | 0.6289 | 1.0698 | 0.13243 | 0.72606 | 0.35291 | 0.54233 | 0.12741 | 67.8469 | 0.58584 | 7.6624 | 5586.8898
1254 | 0.52824 | 25 | 0.048898 | 0.022113 | 0.42012 | 0.69166 | 0.36112 | 105 | 0.37576 | 1.0163 | 0.47941 | 0.84653 | 0.58189 | 0.61117 | 0.14784 | 69.225 | 0.30306 | 5.4815 | 6047.4263
1255 | 0.53422 | 25 | 0.97402 | 0.17208 | 0.025129 | 0.62242 | 0.85767 | 110 | 0.83055 | 1.1282 | 0.90612 | 1.0499 | 0.1723 | 0.46932 | 0.5425 | 91.4233 | 0.29696 | 5.4399 | 6824.1313
1256 | 0.53245 | 25 | 0.32307 | 0.057495 | 0.82542 | 0.74091 | 0.70573 | 108 | 0.49087 | 1.0389 | 0.65538 | 0.91241 | 0.97644 | 0.7705 | 0.067036 | 62.9457 | 0.62351 | 8.0041 | 6570.4098
1257 | 0.59797 | 26 | 0.25118 | 0.050118 | 0.46075 | 0.69599 | 0.32649 | 105 | 0.22009 | 0.98777 | 0.27855 | 0.78283 | 0.51117 | 0.59165 | 0.90416 | 123.189 | 0.53022 | 7.1852 | 6317.6363
1258 | 0.87323 | 27 | 0.63906 | 0.095941 | 0.72584 | 0.72595 | 0.96144 | 113 | 0.22999 | 0.98972 | 0.35217 | 0.80569 | 0.65645 | 0.63098 | 0.15267 | 69.5362 | 0.022467 | 2.9361 | 6446.5099
1259 | 0.21449 | 23 | 0.73821 | 0.11138 | 0.30283 | 0.67782 | 0.81438 | 110 | 0.25786 | 0.995 | 0.89539 | 1.0416 | 0.43073 | 0.56772 | 0.35881 | 80.6535 | 0.93213 | 12.0295 | 6251.1119
1260 | 0.057454 | 22 | 0.26342 | 0.051348 | 0.12271 | 0.64954 | 0.18107 | 104 | 0.42064 | 1.0248 | 0.20132 | 0.75543 | 0.43475 | 0.56897 | 0.26406 | 75.7061 | 0.28766 | 5.3769 | 5597.5369
1261 | 0.076871 | 22 | 0.47687 | 0.074724 | 0.51569 | 0.70158 | 0.73868 | 109 | 0.94039 | 1.1778 | 0.95452 | 1.0955 | 0.7005 | 0.64351 | 0.73846 | 105.7105 | 0.56851 | 7.5104 | 6677.0519
1262 | 0.19447 | 23 | 0.12693 | 0.035627 | 0.4879 | 0.69878 | 0.26953 | 104 | 0.74279 | 1.1 | 0.1953 | 0.75309 | 0.81348 | 0.68072 | 0.85109 | 116.5806 | 0.50795 | 7.0021 | 6206.9602
1263 | 0.73269 | 26 | 0.69635 | 0.10456 | 0.60452 | 0.71106 | 0.79723 | 109 | 0.47234 | 1.0351 | 0.36548 | 0.80976 | 0.18881 | 0.47725 | 0.72725 | 104.7716 | 0.32356 | 5.6225 | 6258.2534
1264 | 0.57698 | 25 | 0.92401 | 0.15225 | 0.92588 | 0.7615 | 0.98548 | 114 | 0.6384 | 1.0721 | 0.51264 | 0.858 | 0.46259 | 0.57744 | 0.22351 | 73.6386 | 0.69221 | 8.6745 | 6457.3426
1265 | 0.41975 | 25 | 0.71575 | 0.10766 | 0.63933 | 0.71507 | 0.80024 | 110 | 0.41699 | 1.0241 | 0.075633 | 0.69527 | 0.20387 | 0.48418 | 0.36076 | 80.7592 | 0.16897 | 4.5671 | 5861.3205
1266 | 0.64162 | 26 | 0.8962 | 0.1442 | 0.054185 | 0.63292 | 0.77836 | 109 | 0.29557 | 1.0017 | 0.83176 | 0.99906 | 0.037982 | 0.3795 | 0.53119 | 90.7035 | 0.97309 | 13.1297 | 6361.4506
1267 | 0.9227 | 28 | 0.58864 | 0.08891 | 0.51641 | 0.70165 | 0.92747 | 112 | 0.72023 | 1.0935 | 0.073512 | 0.69392 | 0.57577 | 0.60953 | 0.33845 | 79.5614 | 0.78898 | 9.7624 | 6701.6881
1268 | 0.039082 | 21 | 0.45003 | 0.071551 | 0.28768 | 0.67585 | 0.60326 | 107 | 0.48755 | 1.0382 | 0.19905 | 0.75455 | 0.1823 | 0.47417 | 0.30327 | 77.7123 | 0.8249 | 10.229 | 5399.8627
1269 | 0.43454 | 25 | 0.81957 | 0.12643 | 0.4618 | 0.6961 | 0.89948 | 111 | 0.17696 | 0.9787 | 0.22298 | 0.76358 | 0.14021 | 0.45275 | 0.63798 | 97.8927 | 0.068144 | 3.6302 | 5949.6474
1270 | 0.40314 | 24 | 0.58756 | 0.088765 | 0.60128 | 0.7107 | 0.31144 | 105 | 0.36241 | 1.0138 | 0.032825 | 0.66276 | 0.089822 | 0.42226 | 0.9622 | 133.1622 | 0.75901 | 9.4028 | 5760.636
1271 | 0.30509 | 24 | 0.14587 | 0.038193 | 0.57462 | 0.70776 | 0.17107 | 104 | 0.74794 | 1.1015 | 0.12062 | 0.72031 | 0.20179 | 0.48324 | 0.56354 | 92.7856 | 0.30368 | 5.4857 | 5773.4797
1272 | 0.47331 | 25 | 0.84363 | 0.13151 | 0.91866 | 0.75967 | 0.87662 | 111 | 0.20915 | 0.98556 | 0.1794 | 0.74673 | 0.72676 | 0.65143 | 0.18266 | 71.3695 | 0.94773 | 12.3932 | 6188.6356
1273 | 0.26655 | 24 | 0.091078 | 0.030179 | 0.6011 | 0.71068 | 0.67586 | 108 | 0.24623 | 0.99283 | 0.84763 | 1.0088 | 0.24593 | 0.50229 | 0.6926 | 101.9847 | 0.040732 | 3.2604 | 6030.6462
1274 | 0.49981 | 25 | 0.52241 | 0.080301 | 0.93159 | 0.76301 | 0.31625 | 105 | 0.99641 | 1.2323 | 0.78523 | 0.97296 | 0.0028283 | 0.32169 | 0.58861 | 94.4534 | 0.89069 | 11.2303 | 6152.3451
1275 | 0.046213 | 22 | 0.078286 | 0.02798 | 0.63957 | 0.7151 | 0.59433 | 107 | 0.35952 | 1.0133 | 0.90472 | 1.0488 | 0.12142 | 0.44214 | 0.2996 | 77.5223 | 0.1168 | 4.1343 | 5585.4774
1276 | 0.99716 | 30 | 0.46817 | 0.073687 | 0.91977 | 0.75994 | 0.019487 | 101 | 0.93264 | 1.1732 | 0.27091 | 0.7803 | 0.97171 | 0.76576 | 0.4929 | 88.3293 | 0.83065 | 10.3079 | 7463.6583
1277 | 0.63617 | 26 | 0.71234 | 0.1071 | 0.53847 | 0.70392 | 0.98291 | 113 | 0.082356 | 0.95369 | 0.22894 | 0.76575 | 0.46044 | 0.5768 | 0.016404 | 56.4038 | 0.22723 | 4.9769 | 6047.8834
1278 | 0.50807 | 25 | 0.8749 | 0.13874 | 0.13602 | 0.65216 | 0.21684 | 104 | 0.16954 | 0.97703 | 0.6709 | 0.91896 | 0.23152 | 0.49628 | 0.14468 | 69.0183 | 0.045713 | 3.3352 | 6103.4778
1279 | 0.29039 | 24 | 0.33434 | 0.058685 | 0.2131 | 0.66528 | 0.29393 | 105 | 0.78632 | 1.1133 | 0.16586 | 0.74108 | 0.63941 | 0.62635 | 0.30308 | 77.7026 | 0.80342 | 9.9447 | 6182.299
1280 | 0.94994 | 28 | 0.75248 | 0.11383 | 0.25253 | 0.67107 | 0.39534 | 105 | 0.034362 | 0.93468 | 0.66377 | 0.91593 | 0.23145 | 0.49625 | 0.28543 | 76.793 | 0.46309 | 6.6455 | 6376.2221
1281 | 0.93056 | 28 | 0.75607 | 0.11445 | 0.62381 | 0.71326 | 0.54649 | 107 | 0.57273 | 1.0566 | 0.87244 | 1.025 | 0.87496 | 0.70596 | 0.20628 | 72.709 | 0.98246 | 13.4899 | 7346.4924
1282 | 0.24865 | 24 | 0.54458 | 0.083113 | 0.37549 | 0.68666 | 0.81448 | 110 | 0.3092 | 1.0041 | 0.36407 | 0.80933 | 0.30097 | 0.52379 | 0.66469 | 99.8521 | 0.15334 | 4.4454 | 6000.3706
1283 | 0.51167 | 25 | 0.082751 | 0.028766 | 0.65488 | 0.71692 | 0.56859 | 107 | 0.32795 | 1.0075 | 0.79173 | 0.97643 | 0.73747 | 0.65476 | 0.5249 | 90.307 | 0.85817 | 10.7061 | 6448.0642
1284 | 0.52185 | 25 | 0.80989 | 0.12448 | 0.92881 | 0.76227 | 0.55309 | 107 | 0.10617 | 0.96096 | 0.72128 | 0.94136 | 0.50761 | 0.59063 | 0.6117 | 96.0345 | 0.90961 | 11.5721 | 6343.5582
1285 | 0.28195 | 24 | 0.31544 | 0.056693 | 0.46795 | 0.69674 | 0.38451 | 105 | 0.22407 | 0.98856 | 0.14428 | 0.73158 | 0.59352 | 0.61426 | 0.21459 | 73.1622 | 0.33963 | 5.7345 | 5790.5199
1286 | 0.71011 | 26 | 0.59516 | 0.089795 | 0.67096 | 0.71888 | 0.65426 | 108 | 0.092962 | 0.95704 | 0.61369 | 0.89551 | 0.83891 | 0.69056 | 0.10147 | 65.9271 | 0.62384 | 8.0071 | 6440.8377
1287 | 0.40738 | 25 | 0.58581 | 0.08853 | 0.013015 | 0.61613 | 0.64375 | 108 | 0.36794 | 1.0148 | 0.087767 | 0.70263 | 0.53427 | 0.59816 | 0.71414 | 103.697 | 0.88805 | 11.1851 | 6291.8323
1288 | 0.76059 | 27 | 0.054253 | 0.023292 | 0.31424 | 0.67928 | 0.5528 | 107 | 0.17669 | 0.97864 | 0.37174 | 0.81169 | 0.76457 | 0.66352 | 0.78945 | 110.2614 | 0.87739 | 11.0076 | 6572.9856
1289 | 0.065333 | 22 | 0.49975 | 0.077495 | 0.7916 | 0.73544 | 0.6783 | 108 | 0.54073 | 1.0495 | 0.89711 | 1.0429 | 0.32061 | 0.53097 | 0.2948 | 77.2746 | 0.95102 | 12.4767 | 5960.555
1290 | 0.39742 | 24 | 0.16466 | 0.040578 | 0.21081 | 0.66493 | 0.66965 | 108 | 0.44088 | 1.0288 | 0.23127 | 0.76659 | 0.69083 | 0.64068 | 0.58143 | 93.9709 | 0.27502 | 5.2919 | 6118.1672
1291 | 0.15296 | 23 | 0.49852 | 0.077344 | 0.49003 | 0.699 | 0.063142 | 102 | 0.37759 | 1.0166 | 0.53362 | 0.86544 | 0.74066 | 0.65577 | 0.75798 | 107.3956 | 0.99345 | 14.0772 | 6199.1046
1292 | 0.27994 | 24 | 0.74803 | 0.11306 | 0.78907 | 0.73505 | 0.14472 | 103 | 0.23888 | 0.99144 | 0.96143 | 1.1038 | 0.058217 | 0.39842 | 0.56932 | 93.1659 | 0.25516 | 5.1598 | 5988.7566
1293 | 0.3552 | 24 | 0.89613 | 0.14418 | 0.43172 | 0.69292 | 0.51975 | 107 | 0.9002 | 1.1566 | 0.92505 | 1.0659 | 0.37163 | 0.54868 | 0.20928 | 72.8735 | 0.25064 | 5.13 | 6662.9689
1294 | 0.14989 | 23 | 0.58942 | 0.089016 | 0.45037 | 0.69491 | 0.93002 | 112 | 0.031101 | 0.93299 | 0.3984 | 0.82002 | 0.78063 | 0.66896 | 0.31025 | 78.0757 | 0.67521 | 8.5021 | 5952.7613
1295 | 0.30709 | 24 | 0.88179 | 0.14045 | 0.39834 | 0.68926 | 0.62307 | 107 | 0.12368 | 0.96579 | 0.36607 | 0.80995 | 0.90212 | 0.71911 | 0.22951 | 73.9534 | 0.20907 | 4.8555 | 6271.3475
1296 | 0.54579 | 25 | 0.46346 | 0.073129 | 0.84934 | 0.74511 | 0.18046 | 104 | 0.79176 | 1.115 | 0.38049 | 0.81441 | 0.74825 | 0.65819 | 0.72678 | 104.7323 | 0.68061 | 8.5563 | 6529.3681
1297 | 0.15782 | 23 | 0.58363 | 0.088237 | 0.76403 | 0.7313 | 0.45209 | 106 | 0.39125 | 1.0192 | 0.55191 | 0.87206 | 0.60064 | 0.61614 | 0.65506 | 99.1367 | 0.69651 | 8.7188 | 6095.569
1298 | 0.67139 | 26 | 0.14613 | 0.038226 | 0.59603 | 0.71011 | 0.58772 | 107 | 0.33063 | 1.008 | 0.23023 | 0.76622 | 0.10217 | 0.43039 | 0.55019 | 91.9173 | 0.39232 | 6.1119 | 5812.7756
1299 | 0.7639 | 27 | 0.82966 | 0.12851 | 0.37207 | 0.68626 | 0.52793 | 107 | 0.17448 | 0.97815 | 0.4107 | 0.82392 | 0.99946 | 0.81254 | 0.82057 | 113.3156 | 0.069482 | 3.6462 | 7124.9142
1300 | 0.0036484 | 20 | 0.38562 | 0.064238 | 0.71766 | 0.72486 | 0.793 | 109 | 0.89035 | 1.152 | 0.29236 | 0.7873 | 0.45878 | 0.5763 | 0.36841 | 81.1745 | 0.15215 | 4.4359 | 5618.4086
1301 | 0.82856 | 27 | 0.11554 | 0.033991 | 0.19369 | 0.66224 | 0.59067 | 107 | 0.09423 | 0.95743 | 0.80425 | 0.98325 | 0.33429 | 0.53585 | 0.54285 | 91.4458 | 0.42875 | 6.3824 | 6421.4303
1302 | 0.76324 | 27 | 0.21042 | 0.045872 | 0.070661 | 0.63759 | 0.23975 | 104 | 0.79072 | 1.1147 | 0.41185 | 0.82429 | 0.050867 | 0.392 | 0.88562 | 120.7113 | 0.19304 | 4.7438 | 6358.3733
1303 | 0.93491 | 28 | 0.63107 | 0.094796 | 0.74066 | 0.72798 | 0.49619 | 106 | 0.58739 | 1.06 | 0.45483 | 0.83828 | 0.2972 | 0.52238 | 0.34529 | 79.9264 | 0.99023 | 13.8731 | 6549.4836
1304 | 0.87838 | 28 | 0.24187 | 0.049181 | 0.10872 | 0.64663 | 0.71184 | 108 | 0.94143 | 1.1784 | 0.9833 | 1.1367 | 0.049847 | 0.39107 | 0.93475 | 127.8779 | 0.81109 | 10.0444 | 7159.7093
1305 | 0.85834 | 27 | 0.060454 | 0.024587 | 0.80184 | 0.73705 | 0.21538 | 104 | 0.60449 | 1.064 | 0.28583 | 0.7852 | 0.99855 | 0.80772 | 0.96896 | 134.7418 | 0.59053 | 7.7041 | 7041.3498
1306 | 0.12535 | 23 | 0.52383 | 0.08048 | 0.44425 | 0.69426 | 0.90167 | 111 | 0.45235 | 1.0311 | 0.91135 | 1.0541 | 0.58224 | 0.61126 | 0.81556 | 112.8077 | 0.16924 | 4.5691 | 6482.2222
1307 | 0.74753 | 26 | 0.63522 | 0.095389 | 0.57344 | 0.70764 | 0.73535 | 109 | 0.96485 | 1.1945 | 0.1659 | 0.7411 | 0.56951 | 0.60784 | 0.68477 | 101.377 | 0.93705 | 12.1393 | 6809.7041
1308 | 0.23605 | 23 | 0.91261 | 0.1488 | 0.027245 | 0.62334 | 0.98932 | 114 | 0.97783 | 1.206 | 0.93857 | 1.0786 | 0.36871 | 0.54769 | 0.24935 | 74.9673 | 0.58794 | 7.681 | 6824.5356
1309 | 0.66282 | 26 | 0.85305 | 0.1336 | 0.58421 | 0.70881 | 0.31604 | 105 | 0.87417 | 1.1451 | 0.15468 | 0.73624 | 0.84441 | 0.69279 | 0.98494 | 139.3722 | 0.076055 | 3.7223 | 7056.2383
1310 | 0.032353 | 21 | 0.67786 | 0.10169 | 0.17232 | 0.65871 | 0.69354 | 108 | 0.52833 | 1.0468 | 0.87755 | 1.0286 | 0.48431 | 0.58388 | 0.33871 | 79.5748 | 0.89728 | 11.3458 | 6044.402
1311 | 0.47136 | 25 | 0.046415 | 0.021544 | 0.12145 | 0.64928 | 0.32927 | 105 | 0.62423 | 1.0687 | 0.48088 | 0.84703 | 0.49891 | 0.58813 | 0.88395 | 120.4977 | 0.42802 | 6.3769 | 6430.8852
1312 | 0.30356 | 24 | 0.4946 | 0.076865 | 0.5199 | 0.70201 | 0.61398 | 107 | 0.78486 | 1.1128 | 0.7792 | 0.9698 | 0.042659 | 0.38425 | 0.55005 | 91.9085 | 0.73556 | 9.1368 | 6027.3829
1313 | 0.77555 | 27 | 0.55545 | 0.084516 | 0.40445 | 0.68994 | 0.63717 | 108 | 0.7695 | 1.108 | 0.63798 | 0.90524 | 0.54167 | 0.60022 | 0.74178 | 105.9928 | 0.91255 | 11.6283 | 6996.4455
1314 | 0.069068 | 22 | 0.98644 | 0.17983 | 0.66319 | 0.71793 | 0.095043 | 103 | 0.50412 | 1.0417 | 0.7661 | 0.96307 | 0.21113 | 0.48743 | 0.64617 | 98.4857 | 0.5357 | 7.2309 | 6037.5852
1315 | 0.34866 | 24 | 0.37112 | 0.062645 | 0.87212 | 0.74943 | 0.028229 | 101 | 0.091979 | 0.95674 | 0.13925 | 0.72927 | 0.1959 | 0.48055 | 0.51627 | 89.767 | 0.21239 | 4.8781 | 5462.1096
1316 | 0.22015 | 23 | 0.86832 | 0.13715 | 0.99555 | 0.79056 | 0.3255 | 105 | 0.96714 | 1.1964 | 0.87388 | 1.026 | 0.2676 | 0.51102 | 0.35035 | 80.1977 | 0.12392 | 4.1984 | 6302.3494
1317 | 0.609 | 26 | 0.26327 | 0.051333 | 0.61134 | 0.71183 | 0.70803 | 108 | 0.79733 | 1.1168 | 0.35288 | 0.80591 | 0.53782 | 0.59915 | 0.12773 | 67.8693 | 0.93892 | 12.1821 | 6424.3953
1318 | 0.71603 | 26 | 0.41098 | 0.067069 | 0.60655 | 0.71129 | 0.71145 | 108 | 0.87486 | 1.1454 | 0.63304 | 0.90323 | 0.76676 | 0.66426 | 0.15321 | 69.5708 | 0.77965 | 9.6478 | 6823.8327
1319 | 0.47147 | 25 | 0.55229 | 0.084107 | 0.60686 | 0.71133 | 0.76806 | 109 | 0.12581 | 0.96636 | 0.63725 | 0.90494 | 0.75834 | 0.66147 | 0.90809 | 123.7446 | 0.68203 | 8.5706 | 6574.5987
1320 | 0.88705 | 28 | 0.07325 | 0.027065 | 0.17603 | 0.65933 | 0.84731 | 110 | 0.0050658 | 0.91332 | 0.08696 | 0.70215 | 0.32241 | 0.53162 | 0.72853 | 104.8775 | 0.16017 | 4.4993 | 6090.1095
1321 | 0.19446 | 23 | 0.83814 | 0.13032 | 0.7527 | 0.72967 | 0.49688 | 106 | 0.073878 | 0.95085 | 0.65991 | 0.91431 | 0.039971 | 0.38155 | 0.79811 | 111.0878 | 0.99235 | 14.0025 | 5749.7513
1322 | 0.81923 | 27 | 0.36533 | 0.062015 | 0.49825 | 0.69982 | 0.31316 | 105 | 0.59157 | 1.061 | 0.52339 | 0.86179 | 0.28091 | 0.5162 | 0.48103 | 87.6121 | 0.18692 | 4.7 | 6388.3796
1323 | 0.83613 | 27 | 0.49531 | 0.076952 | 0.84246 | 0.74387 | 0.99798 | 114 | 0.2972 | 1.002 | 0.25552 | 0.77511 | 0.11968 | 0.44112 | 0.68035 | 101.0373 | 0.046079 | 3.3405 | 6111.8369
1324 | 0.33568 | 24 | 0.35612 | 0.061017 | 0.41751 | 0.69138 | 0.19117 | 104 | 0.5235 | 1.0458 | 0.72063 | 0.94106 | 0.76642 | 0.66414 | 0.15699 | 69.811 | 0.40806 | 6.2277 | 6297.3888
1325 | 0.4819 | 25 | 0.1125 | 0.033541 | 0.15491 | 0.65566 | 0.58979 | 107 | 0.9998 | 1.2458 | 0.10164 | 0.71044 | 0.66402 | 0.63307 | 0.89413 | 121.8216 | 0.19033 | 4.7245 | 6774.8527
1326 | 0.18245 | 23 | 0.76989 | 0.11691 | 0.11463 | 0.64788 | 0.14365 | 103 | 0.0076735 | 0.91639 | 0.75985 | 0.95993 | 0.42233 | 0.56509 | 0.29571 | 77.3216 | 0.78096 | 9.6638 | 5934.9656
1327 | 0.76625 | 27 | 0.98993 | 0.18262 | 0.64019 | 0.71517 | 0.19772 | 104 | 0.9063 | 1.1595 | 0.34301 | 0.80291 | 0.93374 | 0.73698 | 0.31648 | 78.401 | 0.32395 | 5.6252 | 7240.7735
1328 | 0.33566 | 24 | 0.61807 | 0.092959 | 0.38578 | 0.68784 | 0.23305 | 104 | 0.030248 | 0.93254 | 0.02434 | 0.65404 | 0.86363 | 0.70091 | 0.36041 | 80.7403 | 0.029641 | 3.0752 | 5824.2454
1329 | 0.58513 | 25 | 0.93781 | 0.15681 | 0.3987 | 0.6893 | 0.84994 | 110 | 0.78963 | 1.1143 | 0.77433 | 0.96727 | 0.13931 | 0.45225 | 0.91297 | 124.4512 | 0.27146 | 5.2681 | 6690.6146
1330 | 0.27675 | 24 | 0.63911 | 0.095949 | 0.36997 | 0.68602 | 0.207 | 104 | 0.80615 | 1.1198 | 0.74889 | 0.95451 | 0.41148 | 0.56167 | 0.99381 | 143.187 | 0.54565 | 7.3146 | 6700.3269
1331 | 0.12977 | 23 | 0.26112 | 0.051116 | 0.76917 | 0.73205 | 0.85467 | 110 | 0.30885 | 1.0041 | 0.77166 | 0.9659 | 0.058326 | 0.39852 | 0.80724 | 111.9777 | 0.036641 | 3.1954 | 5745.0921
1332 | 0.6815 | 26 | 0.28414 | 0.053454 | 0.068749 | 0.63708 | 0.69255 | 108 | 0.6069 | 1.0645 | 0.030602 | 0.6606 | 0.43665 | 0.56955 | 0.099109 | 65.7408 | 0.52047 | 7.1045 | 6101.368
1333 | 0.26436 | 24 | 0.20497 | 0.045274 | 0.30782 | 0.67846 | 0.39785 | 105 | 0.33488 | 1.0088 | 0.23293 | 0.76719 | 0.2341 | 0.49737 | 0.2513 | 75.065 | 0.38266 | 6.0415 | 5660.7857
1334 | 0.43171 | 25 | 0.74022 | 0.11172 | 0.093212 | 0.64318 | 0.0050962 | 101 | 0.62181 | 1.0681 | 0.27191 | 0.78063 | 0.0090184 | 0.33874 | 0.60396 | 95.4993 | 0.28968 | 5.3906 | 5830.7008
1335 | 0.72451 | 26 | 0.54602 | 0.083298 | 0.33333 | 0.68165 | 0.53417 | 107 | 0.017789 | 0.92495 | 0.91126 | 1.0541 | 0.42067 | 0.56457 | 0.4383 | 85.0945 | 0.8638 | 10.7921 | 6456.249
1336 | 0.9596 | 29 | 0.69842 | 0.10488 | 0.86537 | 0.74811 | 0.51112 | 106 | 0.10958 | 0.96193 | 0.42132 | 0.82733 | 0.42451 | 0.56578 | 0.22933 | 73.9441 | 0.85559 | 10.6671 | 6482.3231
1337 | 0.6946 | 26 | 0.31278 | 0.056416 | 0.15201 | 0.65514 | 0.16205 | 103 | 0.85965 | 1.1392 | 0.27455 | 0.78151 | 0.89863 | 0.71732 | 0.99109 | 141.8272 | 0.72823 | 9.0561 | 7102.2997
1338 | 0.14197 | 23 | 0.49457 | 0.076862 | 0.10777 | 0.64643 | 0.65067 | 108 | 0.20892 | 0.98551 | 0.14808 | 0.7333 | 0.25133 | 0.5045 | 0.88388 | 120.4891 | 0.277 | 5.3052 | 5822.4024
1339 | 0.72243 | 26 | 0.80505 | 0.12352 | 0.37168 | 0.68622 | 0.3775 | 105 | 0.034406 | 0.9347 | 0.034303 | 0.66416 | 0.20084 | 0.48281 | 0.31291 | 78.2146 | 0.099801 | 3.9729 | 5747.2324
1340 | 0.9543 | 28 | 0.97636 | 0.17337 | 0.11937 | 0.64886 | 0.74071 | 109 | 0.95645 | 1.1883 | 0.040528 | 0.66974 | 0.72935 | 0.65223 | 0.20898 | 72.8573 | 0.077516 | 3.7387 | 7174.0527
1341 | 0.35781 | 24 | 0.91458 | 0.14938 | 0.049282 | 0.63139 | 0.67962 | 108 | 0.68952 | 1.0852 | 0.60161 | 0.89078 | 0.45818 | 0.57612 | 0.33895 | 79.5877 | 0.46885 | 6.6904 | 6491.8144
1342 | 0.559 | 25 | 0.010691 | 0.01034 | 0.639 | 0.71503 | 0.42651 | 106 | 0.52829 | 1.0468 | 0.74922 | 0.95467 | 0.46281 | 0.57751 | 0.12789 | 67.8806 | 0.41026 | 6.2441 | 6144.3019
1343 | 0.49073 | 25 | 0.4883 | 0.076101 | 0.92137 | 0.76034 | 0.15886 | 103 | 0.72619 | 1.0952 | 0.70583 | 0.93429 | 0.15383 | 0.45999 | 0.4204 | 84.0685 | 0.83405 | 10.3553 | 6096.3532
1344 | 0.60538 | 26 | 0.096441 | 0.031055 | 0.97043 | 0.77568 | 0.60331 | 107 | 0.39544 | 1.02 | 0.52704 | 0.86309 | 0.44241 | 0.57132 | 0.53176 | 90.7393 | 0.26793 | 5.2445 | 6165.0154
1345 | 0.39786 | 24 | 0.72088 | 0.10849 | 0.025303 | 0.6225 | 0.99719 | 114 | 0.19244 | 0.98207 | 0.59714 | 0.88906 | 0.51672 | 0.59323 | 0.16574 | 70.3559 | 0.55491 | 7.3933 | 6240.4666
1346 | 0.19588 | 23 | 0.057597 | 0.023999 | 0.11639 | 0.64825 | 0.8236 | 110 | 0.86064 | 1.1396 | 0.37902 | 0.81395 | 0.91109 | 0.72384 | 0.94202 | 129.1464 | 0.38161 | 6.0339 | 6644.3813
1347 | 0.19957 | 23 | 0.45276 | 0.071871 | 0.84552 | 0.74442 | 0.26055 | 104 | 0.79972 | 1.1176 | 0.51917 | 0.86029 | 0.04928 | 0.39056 | 0.76729 | 108.2227 | 0.045681 | 3.3348 | 5752.3969
1348 | 0.035876 | 21 | 0.44749 | 0.071254 | 0.47675 | 0.69765 | 0.767 | 109 | 0.4575 | 1.0321 | 0.29435 | 0.78794 | 0.018701 | 0.35578 | 0.35102 | 80.2335 | 0.61433 | 7.9192 | 5211.8152
1349 | 0.9072 | 28 | 0.42514 | 0.068677 | 0.70278 | 0.7229 | 0.94957 | 112 | 0.45056 | 1.0307 | 0.30158 | 0.79024 | 0.4556 | 0.57534 | 0.31807 | 78.4843 | 0.77325 | 9.5707 | 6536.6789
1350 | 0.98793 | 29 | 0.82877 | 0.12833 | 0.051916 | 0.63222 | 0.22855 | 104 | 0.61063 | 1.0654 | 0.30021 | 0.7898 | 0.83056 | 0.68725 | 0.34785 | 80.0633 | 0.50789 | 7.0016 | 7198.8357
1351 | 0.38075 | 24 | 0.26466 | 0.051474 | 0.52482 | 0.70251 | 0.36666 | 105 | 0.98331 | 1.2118 | 0.52141 | 0.86109 | 0.73101 | 0.65274 | 0.68889 | 101.6956 | 0.64931 | 8.248 | 6657.8374
1352 | 0.35605 | 24 | 0.37522 | 0.063093 | 0.011243 | 0.615 | 0.32597 | 105 | 0.31155 | 1.0046 | 0.59508 | 0.88826 | 0.84135 | 0.69155 | 0.47777 | 87.4163 | 0.17744 | 4.6306 | 6390.1567
1353 | 0.24278 | 23 | 0.5053 | 0.078177 | 0.10791 | 0.64646 | 0.71221 | 108 | 0.067713 | 0.94868 | 0.69775 | 0.93067 | 0.84289 | 0.69217 | 0.74406 | 106.1872 | 0.58167 | 7.6255 | 6310.8207
1354 | 0.41142 | 25 | 0.73559 | 0.11094 | 0.19912 | 0.66311 | 0.58656 | 107 | 0.28454 | 0.99979 | 0.72685 | 0.94396 | 0.15473 | 0.46046 | 0.93141 | 127.3187 | 0.99721 | 14.3973 | 6406.6703
1355 | 0.43842 | 25 | 0.27167 | 0.052183 | 0.0095408 | 0.61381 | 0.98348 | 113 | 0.95234 | 1.1854 | 0.4899 | 0.85011 | 0.7768 | 0.66764 | 0.49204 | 88.277 | 0.26298 | 5.2116 | 6942.6531
1356 | 0.52676 | 25 | 0.63 | 0.094643 | 0.36222 | 0.68511 | 0.76085 | 109 | 0.58374 | 1.0592 | 0.29993 | 0.78971 | 0.29334 | 0.52093 | 0.60166 | 95.3415 | 0.67307 | 8.4807 | 6226.4131
1357 | 0.097309 | 22 | 0.81209 | 0.12492 | 0.15988 | 0.65655 | 0.67437 | 108 | 0.8815 | 1.1482 | 0.0090686 | 0.63299 | 0.35856 | 0.54426 | 0.94828 | 130.3057 | 0.64318 | 8.1893 | 6117.1531
1358 | 0.63669 | 26 | 0.45382 | 0.071995 | 0.13404 | 0.65178 | 0.12554 | 103 | 0.96122 | 1.1917 | 0.43806 | 0.83276 | 0.98655 | 0.7826 | 0.36077 | 80.7595 | 0.13809 | 4.3207 | 7184.6832
1359 | 0.11544 | 22 | 0.55403 | 0.084332 | 0.70185 | 0.72278 | 0.97785 | 113 | 0.11344 | 0.96301 | 0.48374 | 0.848 | 0.12605 | 0.44483 | 0.68826 | 101.6468 | 0.57749 | 7.5887 | 5586.9409
1360 | 0.59388 | 25 | 0.069208 | 0.026307 | 0.98554 | 0.78299 | 0.76828 | 109 | 0.96763 | 1.1968 | 0.26125 | 0.77706 | 0.96183 | 0.75699 | 0.50782 | 89.2436 | 0.94121 | 12.2354 | 6728.3215
1361 | 0.84704 | 27 | 0.40923 | 0.066871 | 0.31379 | 0.67922 | 0.64556 | 108 | 0.16724 | 0.97651 | 0.67063 | 0.91884 | 0.36865 | 0.54767 | 0.06352 | 62.6016 | 0.90193 | 11.4294 | 6340.2778
1362 | 0.37343 | 24 | 0.01133 | 0.010644 | 0.54388 | 0.70449 | 0.1486 | 103 | 0.70431 | 1.0892 | 0.37867 | 0.81384 | 0.05193 | 0.39296 | 0.14016 | 68.7188 | 0.34212 | 5.7521 | 5494.2718
1363 | 0.17408 | 23 | 0.46541 | 0.07336 | 0.12548 | 0.6501 | 0.28741 | 105 | 0.64137 | 1.0729 | 0.0035969 | 0.62078 | 0.013959 | 0.3482 | 0.51749 | 89.8435 | 0.27549 | 5.295 | 5365.133
1364 | 0.32126 | 24 | 0.12364 | 0.035162 | 0.69209 | 0.72153 | 0.55544 | 107 | 0.53444 | 1.0482 | 0.23393 | 0.76755 | 0.31749 | 0.52985 | 0.30661 | 77.8863 | 0.75152 | 9.3164 | 5780.2684
1365 | 0.63548 | 26 | 0.78216 | 0.11916 | 0.064156 | 0.63582 | 0.80125 | 110 | 0.063011 | 0.94696 | 0.10065 | 0.7099 | 0.40985 | 0.56115 | 0.27248 | 76.1326 | 0.91038 | 11.5868 | 6125.1477
1366 | 0.60743 | 26 | 0.10573 | 0.032515 | 0.17545 | 0.65924 | 0.40385 | 106 | 0.74255 | 1.0999 | 0.099955 | 0.70952 | 0.79536 | 0.67411 | 0.8233 | 113.5962 | 0.66523 | 8.403 | 6631.6475
1367 | 0.022819 | 21 | 0.49703 | 0.077163 | 0.03641 | 0.62699 | 0.84256 | 110 | 0.16838 | 0.97677 | 0.92339 | 1.0644 | 0.63679 | 0.62565 | 0.31796 | 78.4789 | 0.18555 | 4.6901 | 5996.3496
1368 | 0.16863 | 23 | 0.82276 | 0.12708 | 0.79187 | 0.73548 | 0.98491 | 113 | 0.24133 | 0.99191 | 0.39473 | 0.81886 | 0.61771 | 0.62061 | 0.0003812 | 50.9762 | 0.95775 | 12.6565 | 5918.2058
1369 | 0.63552 | 26 | 0.73501 | 0.11084 | 0.73769 | 0.72757 | 0.2666 | 104 | 0.93709 | 1.1758 | 0.74417 | 0.95221 | 0.12399 | 0.44364 | 0.52827 | 90.5189 | 0.57829 | 7.5958 | 6524.7391
1370 | 0.35318 | 24 | 0.31528 | 0.056676 | 0.086872 | 0.64168 | 0.62432 | 107 | 0.070233 | 0.94958 | 0.78804 | 0.97446 | 0.45627 | 0.57554 | 0.17416 | 70.866 | 0.3932 | 6.1184 | 6040.3821
1371 | 0.17039 | 23 | 0.17159 | 0.041423 | 0.073915 | 0.63845 | 0.40311 | 106 | 0.14534 | 0.97132 | 0.046896 | 0.67502 | 0.49001 | 0.58555 | 0.82304 | 113.5692 | 0.60011 | 7.7899 | 5759.729
1372 | 0.65729 | 26 | 0.091068 | 0.030177 | 0.6394 | 0.71508 | 0.1617 | 103 | 0.39889 | 1.0207 | 0.67531 | 0.92085 | 0.6353 | 0.62525 | 0.33602 | 79.4319 | 0.70407 | 8.7975 | 6363.5454
1373 | 0.3338 | 24 | 0.13809 | 0.037161 | 0.15086 | 0.65493 | 0.23275 | 104 | 0.5118 | 1.0433 | 0.58315 | 0.8837 | 0.43798 | 0.56996 | 0.27439 | 76.2295 | 0.82701 | 10.2577 | 6060.6047
1374 | 0.34702 | 24 | 0.84735 | 0.13233 | 0.096179 | 0.64386 | 0.16441 | 104 | 0.5003 | 1.0409 | 0.93322 | 1.0734 | 0.80415 | 0.67728 | 0.70488 | 102.9534 | 0.61777 | 7.9508 | 6903.3491
1375 | 0.39447 | 24 | 0.25941 | 0.050944 | 0.022584 | 0.62125 | 0.19052 | 104 | 0.61166 | 1.0657 | 0.26995 | 0.77998 | 0.68029 | 0.63765 | 0.96995 | 134.9866 | 0.35246 | 5.825 | 6457.3115
1376 | 0.87857 | 28 | 0.85034 | 0.13299 | 0.32787 | 0.68098 | 0.13037 | 103 | 0.98748 | 1.2169 | 0.41824 | 0.82634 | 0.9682 | 0.76249 | 0.98937 | 141.0702 | 0.42145 | 6.3275 | 7912.3516
1377 | 0.4561 | 25 | 0.5687 | 0.08625 | 0.71467 | 0.72446 | 0.15966 | 103 | 0.53611 | 1.0485 | 0.5264 | 0.86286 | 0.99709 | 0.8026 | 0.14268 | 68.8866 | 0.39954 | 6.1648 | 6621.7736
1378 | 0.92851 | 28 | 0.94859 | 0.16073 | 0.25705 | 0.6717 | 0.96214 | 113 | 0.12062 | 0.96497 | 0.37431 | 0.81249 | 0.047347 | 0.38876 | 0.02534 | 57.9592 | 0.64407 | 8.1977 | 6145.0798
1379 | 0.58934 | 25 | 0.93504 | 0.15586 | 0.22713 | 0.6674 | 0.29953 | 105 | 0.078789 | 0.95251 | 0.70016 | 0.93174 | 0.51129 | 0.59168 | 0.7863 | 109.9659 | 0.22229 | 4.9443 | 6515.7873
1380 | 0.78787 | 27 | 0.91743 | 0.15023 | 0.68475 | 0.7206 | 0.14544 | 103 | 0.036322 | 0.93565 | 0.012036 | 0.638 | 0.99542 | 0.79817 | 0.35653 | 80.5303 | 0.85691 | 10.687 | 6471.9434
1381 | 0.4006 | 24 | 0.14239 | 0.037735 | 0.23194 | 0.66811 | 0.66773 | 108 | 0.019111 | 0.92586 | 0.36407 | 0.80933 | 0.31996 | 0.53074 | 0.33052 | 79.1404 | 0.74863 | 9.2835 | 5676.2507
1382 | 0.4021 | 24 | 0.4069 | 0.06661 | 0.85119 | 0.74544 | 0.042953 | 102 | 0.18554 | 0.98058 | 0.40612 | 0.82247 | 0.73657 | 0.65448 | 0.47895 | 87.4868 | 0.43507 | 6.4302 | 5976.1735
1383 | 0.48954 | 25 | 0.99266 | 0.18516 | 0.53342 | 0.7034 | 0.70299 | 108 | 0.80593 | 1.1197 | 0.49323 | 0.85125 | 0.981 | 0.77555 | 0.36579 | 81.0322 | 0.90493 | 11.4844 | 7124.1102
1384 | 0.42044 | 25 | 0.2092 | 0.045738 | 0.87644 | 0.75029 | 0.28026 | 105 | 0.30982 | 1.0043 | 0.08257 | 0.69954 | 0.18164 | 0.47385 | 0.46435 | 86.6173 | 0.69794 | 8.7336 | 5621.4317
1385 | 0.70276 | 26 | 0.59066 | 0.089183 | 0.78879 | 0.73501 | 0.683 | 108 | 0.012102 | 0.92058 | 0.72907 | 0.94501 | 0.45001 | 0.57365 | 0.78535 | 109.8767 | 0.36092 | 5.8851 | 6366.7841
1386 | 0.20219 | 23 | 0.37718 | 0.063309 | 0.16891 | 0.65812 | 0.060468 | 102 | 0.94168 | 1.1786 | 0.63945 | 0.90584 | 0.79372 | 0.67353 | 0.057812 | 62.022 | 0.23555 | 5.0311 | 6379.6821
1387 | 0.49341 | 25 | 0.2179 | 0.04668 | 0.14202 | 0.65329 | 0.56252 | 107 | 0.39805 | 1.0205 | 0.026731 | 0.65664 | 0.15041 | 0.4582 | 0.38232 | 81.9367 | 0.021908 | 2.9244 | 5656.3051
1388 | 0.7205 | 26 | 0.68836 | 0.10331 | 0.32744 | 0.68092 | 0.49179 | 106 | 0.85055 | 1.1356 | 0.040087 | 0.66936 | 0.13563 | 0.45023 | 0.42826 | 84.5171 | 0.479 | 6.7702 | 6122.3429
1389 | 0.7018 | 26 | 0.6042 | 0.091031 | 0.87452 | 0.7499 | 0.92949 | 112 | 0.35788 | 1.013 | 0.53213 | 0.86491 | 0.98417 | 0.77942 | 0.95084 | 130.7982 | 0.92979 | 11.9789 | 7081.9274
1390 | 0.49294 | 25 | 0.063521 | 0.025203 | 0.65332 | 0.71673 | 0.13084 | 103 | 0.94675 | 1.1817 | 0.29711 | 0.78882 | 0.76521 | 0.66374 | 0.37759 | 81.6765 | 0.79189 | 9.7986 | 6465.3372
1391 | 0.15481 | 23 | 0.10349 | 0.03217 | 0.54293 | 0.70439 | 0.54199 | 107 | 0.44378 | 1.0294 | 0.79421 | 0.97776 | 0.55436 | 0.60372 | 0.075478 | 63.7366 | 0.27458 | 5.2889 | 5957.3842
1392 | 0.96383 | 29 | 0.5904 | 0.089148 | 0.7167 | 0.72473 | 0.99745 | 114 | 0.096471 | 0.95811 | 0.23537 | 0.76806 | 0.2199 | 0.49129 | 0.27775 | 76.4005 | 0.16105 | 4.5062 | 6288.3847
1393 | 0.9021 | 28 | 0.71725 | 0.1079 | 0.12815 | 0.65063 | 0.95986 | 113 | 0.36418 | 1.0141 | 0.47123 | 0.84376 | 0.69891 | 0.64304 | 0.3787 | 81.7379 | 0.61133 | 7.8918 | 6952.6544
1394 | 0.42394 | 25 | 0.0072818 | 0.0085334 | 0.6 | 0.71056 | 0.80082 | 110 | 0.51187 | 1.0433 | 0.35713 | 0.8072 | 0.79135 | 0.67269 | 0.52988 | 90.6208 | 0.51561 | 7.0646 | 6302.7275
1395 | 0.76955 | 27 | 0.28905 | 0.053957 | 0.57117 | 0.70739 | 0.13223 | 103 | 0.47519 | 1.0357 | 0.48829 | 0.84956 | 0.57847 | 0.61025 | 0.95379 | 131.3828 | 0.29402 | 5.4199 | 6700.043
1396 | 0.14737 | 23 | 0.5171 | 0.079637 | 0.83782 | 0.74305 | 0.25893 | 104 | 0.99967 | 1.2446 | 0.74618 | 0.95319 | 0.37116 | 0.54852 | 0.98825 | 140.612 | 0.055034 | 3.465 | 6609.1522
1397 | 0.53651 | 25 | 0.54248 | 0.082844 | 0.99017 | 0.78598 | 0.39082 | 105 | 0.6887 | 1.085 | 0.76053 | 0.96027 | 0.075776 | 0.41229 | 0.84199 | 115.5752 | 0.61564 | 7.9313 | 6155.9516
1398 | 0.50042 | 25 | 0.69576 | 0.10446 | 0.73963 | 0.72784 | 0.99239 | 114 | 0.28079 | 0.99913 | 0.79038 | 0.9757 | 0.40834 | 0.56067 | 0.3107 | 78.0989 | 0.31679 | 5.5757 | 6368.9702
1399 | 0.037837 | 21 | 0.30653 | 0.055763 | 0.39315 | 0.68867 | 0.56008 | 107 | 0.59904 | 1.0627 | 0.45823 | 0.83941 | 0.034738 | 0.37603 | 0.99454 | 143.5992 | 0.091251 | 3.8865 | 5603.1124
1400 | 0.2756 | 24 | 0.52908 | 0.081141 | 0.44165 | 0.69398 | 0.84223 | 110 | 0.29282 | 1.0012 | 0.64885 | 0.9097 | 0.72259 | 0.65015 | 0.8708 | 118.8716 | 0.0082768 | 2.5682 | 6464.7384
1401 | 0.71248 | 26 | 0.58402 | 0.088288 | 0.22721 | 0.66741 | 0.27983 | 105 | 0.25836 | 0.99509 | 0.2636 | 0.77785 | 0.14913 | 0.45753 | 0.71658 | 103.8953 | 0.80783 | 10.0018 | 6080.5879
1402 | 0.54498 | 25 | 0.45999 | 0.07272 | 0.85949 | 0.74699 | 0.8454 | 110 | 0.086781 | 0.95511 | 0.38999 | 0.81737 | 0.77479 | 0.66696 | 0.91301 | 124.458 | 0.66684 | 8.4189 | 6375.83
1403 | 0.79608 | 27 | 0.033039 | 0.018177 | 0.75093 | 0.72942 | 0.71191 | 108 | 0.82165 | 1.1251 | 0.3329 | 0.79987 | 0.43219 | 0.56817 | 0.58495 | 94.2069 | 0.298 | 5.447 | 6500.4965
1404 | 0.89435 | 28 | 0.47621 | 0.074646 | 0.38267 | 0.68748 | 0.75582 | 109 | 0.75819 | 1.1045 | 0.48888 | 0.84976 | 0.98979 | 0.78742 | 0.042556 | 60.3145 | 0.97203 | 13.093 | 7302.3442
1405 | 0.59167 | 25 | 0.24415 | 0.049412 | 0.5073 | 0.70073 | 0.80067 | 110 | 0.86342 | 1.1407 | 0.4366 | 0.83228 | 0.079249 | 0.41483 | 0.081633 | 64.2858 | 0.10922 | 4.0639 | 5924.4955
1406 | 0.34578 | 24 | 0.17311 | 0.041606 | 0.46505 | 0.69644 | 0.78932 | 109 | 0.44475 | 1.0296 | 0.7277 | 0.94436 | 0.096255 | 0.42656 | 0.76475 | 107.9953 | 0.34961 | 5.8049 | 5951.2479
1407 | 0.22221 | 23 | 0.79727 | 0.12201 | 0.019681 | 0.61984 | 0.3824 | 105 | 0.39966 | 1.0208 | 0.48866 | 0.84968 | 0.5505 | 0.60266 | 0.4711 | 87.0181 | 0.24363 | 5.084 | 6166.6574
1408 | 0.098027 | 22 | 0.2569 | 0.050691 | 0.78442 | 0.73434 | 0.76721 | 109 | 0.9328 | 1.1733 | 0.46798 | 0.84267 | 0.16618 | 0.46629 | 0.78845 | 110.1675 | 0.12156 | 4.1773 | 5887.8941
1409 | 0.94245 | 28 | 0.69162 | 0.10382 | 0.30736 | 0.6784 | 0.014272 | 101 | 0.59718 | 1.0623 | 0.16187 | 0.73937 | 0.22848 | 0.49499 | 0.28927 | 76.9899 | 0.4661 | 6.6689 | 6319.6816
1410 | 0.036624 | 21 | 0.5176 | 0.0797 | 0.11936 | 0.64886 | 0.018086 | 101 | 0.81675 | 1.1234 | 0.70219 | 0.93265 | 0.090575 | 0.42277 | 0.60449 | 95.536 | 0.5126 | 7.04 | 5705.0037
1411 | 0.20017 | 23 | 0.62813 | 0.094378 | 0.33022 | 0.68127 | 0.45635 | 106 | 0.37279 | 1.0157 | 0.73357 | 0.94713 | 0.68492 | 0.63898 | 0.94328 | 129.3742 | 0.41956 | 6.3134 | 6449.8731
1412 | 0.70003 | 26 | 0.31173 | 0.056306 | 0.83054 | 0.74178 | 0.23857 | 104 | 0.30923 | 1.0042 | 0.90284 | 1.0473 | 0.79152 | 0.67275 | 0.75801 | 107.3979 | 0.82601 | 10.2441 | 6806.9136
1413 | 0.87168 | 27 | 0.49245 | 0.076604 | 0.51376 | 0.70139 | 0.91595 | 111 | 0.55357 | 1.0524 | 0.17152 | 0.74347 | 0.8287 | 0.68653 | 0.17664 | 71.0143 | 0.62388 | 8.0075 | 6625.6955
1414 | 0.0019641 | 20 | 0.67894 | 0.10186 | 0.38865 | 0.68816 | 0.45385 | 106 | 0.79286 | 1.1154 | 0.10678 | 0.7132 | 0.74685 | 0.65774 | 0.73879 | 105.7386 | 0.026214 | 3.0111 | 5821.8634
1415 | 0.39794 | 24 | 0.95058 | 0.16149 | 0.49587 | 0.69959 | 0.35345 | 105 | 0.25675 | 0.9948 | 0.10295 | 0.71115 | 0.065929 | 0.40474 | 0.39437 | 82.6039 | 0.10575 | 4.0308 | 5644.7135
1416 | 0.65842 | 26 | 0.6483 | 0.097282 | 0.32522 | 0.68065 | 0.9573 | 112 | 0.55751 | 1.0532 | 0.24235 | 0.77054 | 0.35016 | 0.54138 | 0.64713 | 98.5555 | 0.52596 | 7.1498 | 6421.0422
1417 | 0.24895 | 24 | 0.8522 | 0.13341 | 0.3734 | 0.68642 | 0.42765 | 106 | 0.9822 | 1.2105 | 0.87051 | 1.0237 | 0.079772 | 0.41521 | 0.69704 | 102.3327 | 0.003182 | 2.3523 | 6494.8552
1418 | 0.59127 | 25 | 0.69727 | 0.1047 | 0.12532 | 0.65006 | 0.80162 | 110 | 0.16772 | 0.97662 | 0.028492 | 0.65847 | 0.72429 | 0.65067 | 0.92153 | 125.7403 | 0.6839 | 8.5896 | 6356.5309
1419 | 0.263 | 24 | 0.77898 | 0.11857 | 0.77735 | 0.73327 | 0.44554 | 106 | 0.99105 | 1.222 | 0.5516 | 0.87195 | 0.01042 | 0.34164 | 0.34607 | 79.9681 | 0.089737 | 3.8708 | 5962.451
1420 | 0.37255 | 24 | 0.25046 | 0.050046 | 0.0047129 | 0.60971 | 0.39899 | 106 | 0.21549 | 0.98684 | 0.10843 | 0.71407 | 0.67689 | 0.63669 | 0.38861 | 82.2843 | 0.66892 | 8.4395 | 5971.7479
1421 | 0.12193 | 22 | 0.81252 | 0.125 | 0.92097 | 0.76024 | 0.15445 | 103 | 0.43901 | 1.0284 | 0.12567 | 0.7228 | 0.47925 | 0.5824 | 0.23848 | 74.4173 | 0.14496 | 4.3777 | 5594.222
1422 | 0.72336 | 26 | 0.32554 | 0.057754 | 0.35938 | 0.68478 | 0.07825 | 102 | 0.42546 | 1.0258 | 0.23041 | 0.76628 | 0.18922 | 0.47744 | 0.10887 | 66.4979 | 0.85917 | 10.7212 | 5864.8758
1423 | 0.46089 | 25 | 0.24907 | 0.049907 | 0.99145 | 0.78693 | 0.94204 | 112 | 0.022798 | 0.92825 | 0.28109 | 0.78366 | 0.45236 | 0.57436 | 0.37934 | 81.773 | 0.01208 | 2.6864 | 5771.6872
1424 | 0.34237 | 24 | 0.76134 | 0.11538 | 0.51596 | 0.70161 | 0.51996 | 107 | 0.64668 | 1.0742 | 0.90716 | 1.0507 | 0.13006 | 0.44711 | 0.95844 | 132.3447 | 0.56239 | 7.4575 | 6477.0634
1425 | 0.73342 | 26 | 0.84527 | 0.13187 | 0.40115 | 0.68957 | 0.085708 | 103 | 0.81291 | 1.1221 | 0.78439 | 0.97252 | 0.51435 | 0.59255 | 0.29922 | 77.5025 | 0.61349 | 7.9116 | 6837.2214
1426 | 0.36541 | 24 | 0.68257 | 0.10241 | 0.15653 | 0.65595 | 0.45886 | 106 | 0.29097 | 1.0009 | 0.78084 | 0.97066 | 0.28397 | 0.51737 | 0.93164 | 127.3571 | 0.14567 | 4.3835 | 6365.0755
1427 | 0.28831 | 24 | 0.86649 | 0.13671 | 0.76358 | 0.73124 | 0.95063 | 112 | 0.89918 | 1.1561 | 0.86039 | 1.017 | 0.61511 | 0.61993 | 0.24081 | 74.536 | 0.19266 | 4.7411 | 6769.3704
1428 | 0.48861 | 25 | 0.81854 | 0.12622 | 0.99391 | 0.78897 | 0.55944 | 107 | 0.27682 | 0.99843 | 0.28758 | 0.78577 | 0.79501 | 0.67399 | 0.37419 | 81.4901 | 0.75074 | 9.3075 | 6251.518
1429 | 0.42445 | 25 | 0.46926 | 0.073817 | 0.2593 | 0.67201 | 0.76867 | 109 | 0.70592 | 1.0896 | 0.083071 | 0.69984 | 0.58873 | 0.61299 | 0.5134 | 89.5891 | 0.5888 | 7.6887 | 6304.493
1430 | 0.81447 | 27 | 0.37634 | 0.063216 | 0.20008 | 0.66326 | 0.41935 | 106 | 0.41255 | 1.0233 | 0.97109 | 1.1167 | 0.30297 | 0.52453 | 0.33951 | 79.6174 | 0.81875 | 10.1459 | 6751.7237
1431 | 0.069209 | 22 | 0.35888 | 0.061315 | 0.35594 | 0.68437 | 0.9589 | 113 | 0.059037 | 0.94546 | 0.83229 | 0.99938 | 0.46875 | 0.57929 | 0.38016 | 81.8182 | 0.55925 | 7.4305 | 5875.0333
1432 | 0.22861 | 23 | 0.72534 | 0.10923 | 0.29449 | 0.67675 | 0.80889 | 110 | 0.4191 | 1.0245 | 0.83688 | 1.0021 | 0.59655 | 0.61507 | 0.31253 | 78.1947 | 0.60189 | 7.8059 | 6324.3053
1433 | 0.25571 | 24 | 0.45461 | 0.072087 | 0.36145 | 0.68502 | 0.52119 | 107 | 0.68899 | 1.085 | 0.12141 | 0.7207 | 0.050051 | 0.39126 | 0.75122 | 106.8047 | 0.81045 | 10.036 | 5785.0158
1434 | 0.71674 | 26 | 0.61257 | 0.09219 | 0.69589 | 0.72201 | 0.082507 | 102 | 0.70123 | 1.0883 | 0.10504 | 0.71227 | 0.27726 | 0.51479 | 0.064352 | 62.6838 | 0.5036 | 6.9668 | 5982.8777
1435 | 0.32514 | 24 | 0.50735 | 0.078429 | 0.96173 | 0.77233 | 0.1488 | 103 | 0.86588 | 1.1417 | 0.51196 | 0.85776 | 0.08718 | 0.42044 | 0.13675 | 68.4899 | 0.21847 | 4.9189 | 5753.3502
1436 | 0.57138 | 25 | 0.59469 | 0.089731 | 0.52857 | 0.7029 | 0.40916 | 106 | 0.31131 | 1.0045 | 0.83905 | 1.0035 | 0.46408 | 0.57789 | 0.17873 | 71.1383 | 0.69426 | 8.6956 | 6343.481
1437 | 0.66218 | 26 | 0.14255 | 0.037756 | 0.28752 | 0.67583 | 0.71567 | 108 | 0.012569 | 0.92097 | 0.27421 | 0.7814 | 0.62434 | 0.62234 | 0.96388 | 133.5409 | 0.30737 | 5.511 | 6303.587
1438 | 0.96179 | 29 | 0.37928 | 0.063539 | 0.55739 | 0.70591 | 0.88384 | 111 | 0.26022 | 0.99543 | 0.89227 | 1.0392 | 0.37023 | 0.54821 | 0.27722 | 76.3735 | 0.84104 | 10.4541 | 6907.3982
1439 | 0.50642 | 25 | 0.25864 | 0.050866 | 0.14481 | 0.65382 | 0.22881 | 104 | 0.88127 | 1.1481 | 0.45793 | 0.83931 | 0.72552 | 0.65104 | 0.77531 | 108.9489 | 0.80148 | 9.9199 | 6746.0866
1440 | 0.061126 | 22 | 0.9675 | 0.16878 | 0.9828 | 0.78146 | 0.82586 | 110 | 0.48441 | 1.0376 | 0.79983 | 0.98082 | 0.32478 | 0.53247 | 0.25149 | 75.0747 | 0.63774 | 8.1375 | 6006.8356
1441 | 0.45534 | 25 | 0.40123 | 0.065974 | 0.22119 | 0.66651 | 0.70253 | 108 | 0.007941 | 0.91667 | 0.809 | 0.98589 | 0.090554 | 0.42275 | 0.62508 | 96.9727 | 0.24176 | 5.0717 | 5919.9648
1442 | 0.60628 | 26 | 0.76026 | 0.11519 | 0.010696 | 0.61463 | 0.020305 | 101 | 0.026846 | 0.93065 | 0.47122 | 0.84376 | 0.11133 | 0.43611 | 0.85648 | 117.1914 | 0.77347 | 9.5733 | 6139.748
1443 | 0.55572 | 25 | 0.35237 | 0.060612 | 0.24585 | 0.67012 | 0.94647 | 112 | 0.61982 | 1.0676 | 0.21885 | 0.76206 | 0.20977 | 0.48683 | 0.40972 | 83.4636 | 0.12132 | 4.1752 | 6029.4375
1444 | 0.57336 | 25 | 0.57431 | 0.086992 | 0.68808 | 0.72102 | 0.38504 | 105 | 0.7842 | 1.1126 | 0.60379 | 0.89163 | 0.4284 | 0.56699 | 0.62231 | 96.7773 | 0.1237 | 4.1965 | 6451.599
1445 | 0.27849 | 24 | 0.93343 | 0.15531 | 0.74226 | 0.7282 | 0.85537 | 110 | 0.96421 | 1.194 | 0.083107 | 0.69986 | 0.63196 | 0.62436 | 0.85261 | 116.7522 | 0.32285 | 5.6176 | 6652.7948
1446 | 0.78581 | 27 | 0.55053 | 0.083879 | 0.052324 | 0.63235 | 0.68466 | 108 | 0.53858 | 1.0491 | 0.48013 | 0.84677 | 0.64403 | 0.62759 | 0.90817 | 123.7571 | 0.1727 | 4.5953 | 6968.8632
1447 | 0.91164 | 28 | 0.53452 | 0.081829 | 0.76597 | 0.73158 | 0.27552 | 105 | 0.77136 | 1.1086 | 0.94495 | 1.0851 | 0.98689 | 0.78307 | 0.83545 | 114.8702 | 0.91784 | 11.7318 | 7858.2586
1448 | 0.51989 | 25 | 0.15801 | 0.039751 | 0.37425 | 0.68652 | 0.24854 | 104 | 0.41558 | 1.0239 | 0.36472 | 0.80953 | 0.71111 | 0.64667 | 0.27126 | 76.0705 | 0.13856 | 4.3246 | 6147.8461
1449 | 0.71461 | 26 | 0.32326 | 0.057515 | 0.17687 | 0.65948 | 0.42674 | 106 | 0.0057883 | 0.91423 | 0.7543 | 0.95717 | 0.24498 | 0.5019 | 0.86384 | 118.044 | 0.30132 | 5.4696 | 6251.7489
1450 | 0.49242 | 25 | 0.7735 | 0.11757 | 0.95818 | 0.77108 | 0.724 | 109 | 0.35234 | 1.0119 | 0.55636 | 0.8737 | 0.16521 | 0.46581 | 0.48337 | 87.7529 | 0.75979 | 9.4119 | 6037.1241
1451 | 0.30616 | 24 | 0.14681 | 0.038316 | 0.18487 | 0.66081 | 0.20239 | 104 | 0.78031 | 1.1114 | 0.01834 | 0.64691 | 0.38957 | 0.55461 | 0.32611 | 78.9071 | 0.38692 | 6.0725 | 5839.1207
1452 | 0.40416 | 24 | 0.9105 | 0.14818 | 0.83084 | 0.74183 | 0.95072 | 112 | 0.53473 | 1.0482 | 0.33685 | 0.80105 | 0.26891 | 0.51154 | 0.40967 | 83.4605 | 0.49675 | 6.9116 | 6085.1546
1453 | 0.055202 | 22 | 0.35624 | 0.061029 | 0.10133 | 0.64502 | 0.67158 | 108 | 0.64554 | 1.0739 | 0.33965 | 0.8019 | 0.34997 | 0.54132 | 0.96175 | 133.0623 | 0.85622 | 10.6767 | 6073.87
1454 | 0.79784 | 27 | 0.93976 | 0.15749 | 0.75249 | 0.72964 | 0.18416 | 104 | 0.94529 | 1.1808 | 0.79624 | 0.97886 | 0.74013 | 0.6556 | 0.15179 | 69.48 | 0.66657 | 8.4162 | 7262.3148
1455 | 0.099537 | 22 | 0.062115 | 0.024923 | 0.18612 | 0.66101 | 0.40632 | 106 | 0.26632 | 0.99655 | 0.00092432 | 0.61053 | 0.09099 | 0.42305 | 0.77856 | 109.2467 | 0.75054 | 9.3052 | 5253.5257
1456 | 0.19119 | 23 | 0.68597 | 0.10294 | 0.43311 | 0.69307 | 0.94443 | 112 | 0.81312 | 1.1221 | 0.056105 | 0.68205 | 0.43272 | 0.56834 | 0.43761 | 85.0543 | 0.24521 | 5.0943 | 6019.0595
1457 | 0.91111 | 28 | 0.3985 | 0.065669 | 0.35892 | 0.68473 | 0.93294 | 112 | 0.99699 | 1.2338 | 0.26361 | 0.77786 | 0.69228 | 0.64111 | 0.36981 | 81.2508 | 0.66883 | 8.4385 | 7253.6196
1458 | 0.73198 | 26 | 0.33211 | 0.058449 | 0.99028 | 0.78606 | 0.48741 | 106 | 0.61911 | 1.0674 | 0.046331 | 0.67456 | 0.35175 | 0.54193 | 0.70817 | 103.2163 | 0.94142 | 12.2403 | 6059.4221
1459 | 0.36367 | 24 | 0.77367 | 0.1176 | 0.14615 | 0.65406 | 0.75162 | 109 | 0.5777 | 1.0578 | 0.75142 | 0.95575 | 0.92548 | 0.73196 | 0.85448 | 116.9641 | 0.11026 | 4.0737 | 6956.5529
1460 | 0.9373 | 28 | 0.30224 | 0.055318 | 0.90399 | 0.75618 | 0.15436 | 103 | 0.81493 | 1.1227 | 0.5033 | 0.85474 | 0.81134 | 0.67992 | 0.14775 | 69.2194 | 0.96488 | 12.8632 | 6869.4376
1461 | 0.94298 | 28 | 0.19268 | 0.043895 | 0.45039 | 0.69491 | 0.75109 | 109 | 0.47728 | 1.0361 | 0.97916 | 1.1293 | 0.30126 | 0.5239 | 0.84502 | 115.9066 | 0.12024 | 4.1655 | 7047.6218
1462 | 0.39395 | 24 | 0.67791 | 0.1017 | 0.47883 | 0.69786 | 0.16846 | 104 | 0.37787 | 1.0167 | 0.25231 | 0.774 | 0.65418 | 0.63035 | 0.13674 | 68.4894 | 0.43272 | 6.4124 | 6005.5348
1463 | 0.55581 | 25 | 0.95269 | 0.16233 | 0.14259 | 0.6534 | 0.09015 | 103 | 0.91593 | 1.1642 | 0.67964 | 0.92271 | 0.18933 | 0.4775 | 0.3013 | 77.6102 | 0.83495 | 10.3679 | 6564.7777
1464 | 0.73456 | 26 | 0.11656 | 0.034141 | 0.58159 | 0.70852 | 0.63238 | 108 | 0.10332 | 0.96013 | 0.067706 | 0.69014 | 0.8683 | 0.70297 | 0.5264 | 90.401 | 0.62111 | 7.9818 | 6164.9034
1465 | 0.90573 | 28 | 0.82115 | 0.12675 | 0.96565 | 0.77379 | 0.039301 | 102 | 0.0051401 | 0.91341 | 0.62893 | 0.90157 | 0.77054 | 0.66552 | 0.3658 | 81.0327 | 0.75683 | 9.3775 | 6571.4735
1466 | 0.61249 | 26 | 0.57068 | 0.086511 | 0.77641 | 0.73313 | 0.41271 | 106 | 0.71579 | 1.0923 | 0.061952 | 0.68622 | 0.96387 | 0.75871 | 0.043897 | 60.4758 | 0.86179 | 10.7613 | 6507.5209
1467 | 0.54979 | 25 | 0.045509 | 0.021333 | 0.16404 | 0.65728 | 0.14865 | 103 | 0.50447 | 1.0418 | 0.87643 | 1.0278 | 0.31081 | 0.52742 | 0.68804 | 101.6297 | 0.62246 | 7.9943 | 6365.3233
1468 | 0.41937 | 25 | 0.55517 | 0.08448 | 0.90139 | 0.75559 | 0.6865 | 108 | 0.23256 | 0.99022 | 0.5502 | 0.87144 | 0.72347 | 0.65042 | 0.82288 | 113.5526 | 0.57981 | 7.6091 | 6430.4974
1469 | 0.83098 | 27 | 0.93043 | 0.15431 | 0.30022 | 0.67749 | 0.091039 | 103 | 0.91169 | 1.1621 | 0.71436 | 0.93817 | 0.99316 | 0.79333 | 0.44893 | 85.7112 | 0.62614 | 8.0285 | 7659.8143
1470 | 0.89744 | 28 | 0.90268 | 0.14597 | 0.041841 | 0.62893 | 0.12057 | 103 | 0.34456 | 1.0105 | 0.72789 | 0.94445 | 0.47625 | 0.58151 | 0.80299 | 111.561 | 0.14468 | 4.3754 | 7077.3222
1471 | 0.98193 | 29 | 0.54335 | 0.082956 | 0.39511 | 0.68889 | 0.99714 | 114 | 0.34333 | 1.0103 | 0.20146 | 0.75548 | 0.98234 | 0.77714 | 0.077409 | 63.9112 | 0.019623 | 2.8748 | 7054.2458
1472 | 0.91162 | 28 | 0.46822 | 0.073693 | 0.9378 | 0.76473 | 0.081366 | 102 | 0.37912 | 1.0169 | 0.0057491 | 0.62627 | 0.99106 | 0.7895 | 0.46267 | 86.5181 | 0.051355 | 3.4152 | 6508.2684
1473 | 0.79816 | 27 | 0.43453 | 0.069754 | 0.93735 | 0.7646 | 0.00066658 | 100 | 0.15818 | 0.97441 | 0.9024 | 1.0469 | 0.0431 | 0.38469 | 0.77772 | 109.1701 | 0.69637 | 8.7174 | 6158.3004
1474 | 0.24504 | 24 | 0.89375 | 0.14354 | 0.74494 | 0.72858 | 0.40176 | 106 | 0.81227 | 1.1218 | 0.4384 | 0.83287 | 0.44203 | 0.57121 | 0.86868 | 118.6168 | 0.34501 | 5.7724 | 6501.7161
1475 | 0.85567 | 27 | 0.0024792 | 0.0049791 | 0.4898 | 0.69897 | 0.085888 | 103 | 0.49457 | 1.0397 | 0.55342 | 0.87262 | 0.99543 | 0.79821 | 0.95363 | 131.3516 | 0.32618 | 5.6407 | 7089.4711
1476 | 0.65151 | 26 | 0.50622 | 0.07829 | 0.70269 | 0.72289 | 0.58487 | 107 | 0.069991 | 0.94949 | 0.64378 | 0.90761 | 0.8825 | 0.70946 | 0.43044 | 84.6419 | 0.43503 | 6.4299 | 6525.2152
1477 | 0.77509 | 27 | 0.70651 | 0.10617 | 0.99902 | 0.79557 | 0.83948 | 110 | 0.28587 | 1 | 0.79455 | 0.97794 | 0.931 | 0.73529 | 0.22004 | 73.454 | 0.42594 | 6.3613 | 6910.7217
1478 | 0.85093 | 27 | 0.80508 | 0.12353 | 0.25017 | 0.67073 | 0.48551 | 106 | 0.86362 | 1.1408 | 0.56046 | 0.87521 | 0.27183 | 0.51268 | 0.70186 | 102.7128 | 0.070212 | 3.6548 | 6838.3861
1479 | 0.097639 | 22 | 0.86046 | 0.1353 | 0.8848 | 0.752 | 0.60602 | 107 | 0.88256 | 1.1486 | 0.52349 | 0.86182 | 0.97256 | 0.76658 | 0.50499 | 89.0692 | 0.33532 | 5.7044 | 6513.5611
1480 | 0.89747 | 28 | 0.63367 | 0.095167 | 0.13252 | 0.65148 | 0.54139 | 107 | 0.31667 | 1.0055 | 0.24362 | 0.77098 | 0.8777 | 0.70722 | 0.84535 | 115.9431 | 0.82119 | 10.1787 | 7038.6878
1481 | 0.33577 | 24 | 0.99668 | 0.19002 | 0.15178 | 0.6551 | 0.49722 | 106 | 0.91609 | 1.1643 | 0.4426 | 0.83425 | 0.086846 | 0.42021 | 0.044071 | 60.4966 | 0.27171 | 5.2697 | 6161.9489
1482 | 0.74633 | 26 | 0.099523 | 0.031547 | 0.071998 | 0.63795 | 0.40632 | 106 | 0.0062825 | 0.91483 | 0.58535 | 0.88454 | 0.096048 | 0.42642 | 0.41664 | 83.8548 | 0.1097 | 4.0684 | 5779.6496
1483 | 0.40028 | 24 | 0.68209 | 0.10234 | 0.079736 | 0.63993 | 0.17476 | 104 | 0.047511 | 0.94078 | 0.3811 | 0.8146 | 0.6455 | 0.62799 | 0.7896 | 110.2762 | 0.95431 | 12.5627 | 6211.7043
1484 | 0.68933 | 26 | 0.45683 | 0.072347 | 0.7769 | 0.7332 | 0.8635 | 110 | 0.74225 | 1.0998 | 0.66443 | 0.91621 | 0.37918 | 0.55119 | 0.35751 | 80.5834 | 0.47766 | 6.7596 | 6513.9
1485 | 0.11813 | 22 | 0.066677 | 0.025822 | 0.52459 | 0.70249 | 0.54404 | 107 | 0.90696 | 1.1598 | 0.46253 | 0.84085 | 0.67798 | 0.637 | 0.90705 | 123.5975 | 0.043663 | 3.3049 | 6234.8527
1486 | 0.34782 | 24 | 0.05014 | 0.022392 | 0.86126 | 0.74732 | 0.32283 | 105 | 0.1642 | 0.97581 | 0.19088 | 0.75135 | 0.24571 | 0.5022 | 0.074047 | 63.6058 | 0.38943 | 6.0908 | 5397.258
1487 | 0.1088 | 22 | 0.51046 | 0.078813 | 0.88944 | 0.75298 | 0.70586 | 108 | 0.43241 | 1.0271 | 0.41375 | 0.8249 | 0.34588 | 0.5399 | 0.4356 | 84.9383 | 0.21065 | 4.8663 | 5658.7009
1488 | 0.80364 | 27 | 0.024219 | 0.015563 | 0.75418 | 0.72988 | 0.93498 | 112 | 0.32289 | 1.0066 | 0.5253 | 0.86247 | 0.76972 | 0.66524 | 0.23091 | 74.0264 | 0.35288 | 5.828 | 6497.598
1489 | 0.97806 | 29 | 0.77656 | 0.11813 | 0.074186 | 0.63852 | 0.95651 | 112 | 0.65064 | 1.0752 | 0.20639 | 0.75737 | 0.3558 | 0.54332 | 0.083493 | 64.4475 | 0.7691 | 9.5212 | 6810.3529
1490 | 0.54446 | 25 | 0.077881 | 0.027907 | 0.16867 | 0.65808 | 0.96831 | 113 | 0.80068 | 1.1179 | 0.4589 | 0.83963 | 0.62049 | 0.62133 | 0.51028 | 89.3955 | 0.54887 | 7.3419 | 6554.3573
1491 | 0.4756 | 25 | 0.91513 | 0.14954 | 0.60505 | 0.71112 | 0.069499 | 102 | 0.73237 | 1.097 | 0.14604 | 0.73238 | 0.47194 | 0.58023 | 0.51446 | 89.6547 | 0.74373 | 9.228 | 6327.5938
1492 | 0.31598 | 24 | 0.17276 | 0.041564 | 0.38714 | 0.68799 | 0.049203 | 102 | 0.45754 | 1.0321 | 0.0031706 | 0.61951 | 0.77731 | 0.66782 | 0.099163 | 65.7451 | 0.13366 | 4.2831 | 5725.2449
1493 | 0.25423 | 24 | 0.46503 | 0.073315 | 0.86066 | 0.74721 | 0.3636 | 105 | 0.16102 | 0.97507 | 0.3023 | 0.79046 | 0.028033 | 0.3683 | 0.76914 | 108.3889 | 0.066003 | 3.6044 | 5515.8823
1494 | 0.8002 | 27 | 0.24132 | 0.049124 | 0.2404 | 0.66934 | 0.57978 | 107 | 0.31556 | 1.0053 | 0.73533 | 0.94797 | 0.59796 | 0.61544 | 0.35805 | 80.6127 | 0.4512 | 6.5534 | 6641.809
1495 | 0.29557 | 24 | 0.70016 | 0.10516 | 0.73139 | 0.7267 | 0.42301 | 106 | 0.67002 | 1.0801 | 0.326 | 0.79779 | 0.063531 | 0.40282 | 0.28431 | 76.7356 | 0.86223 | 10.768 | 5757.8631
1496 | 0.29906 | 24 | 0.080912 | 0.028445 | 0.0013057 | 0.60511 | 0.19949 | 104 | 0.026386 | 0.93039 | 0.68012 | 0.92292 | 0.13514 | 0.44996 | 0.44212 | 85.3154 | 0.66074 | 8.3589 | 5708.7655
1497 | 0.53003 | 25 | 0.96804 | 0.16903 | 0.027719 | 0.62355 | 0.36432 | 105 | 0.40599 | 1.022 | 0.1463 | 0.7325 | 0.30227 | 0.52427 | 0.37649 | 81.6162 | 0.68353 | 8.5859 | 6208.6108
1498 | 0.79015 | 27 | 0.32475 | 0.057671 | 0.64911 | 0.71623 | 0.073221 | 102 | 0.56396 | 1.0547 | 0.17283 | 0.74401 | 0.067699 | 0.40614 | 0.9613 | 132.9636 | 0.8254 | 10.2358 | 6142.7103
1499 | 0.89133 | 28 | 0.82658 | 0.12787 | 0.28592 | 0.67562 | 0.14175 | 103 | 0.64301 | 1.0733 | 0.70161 | 0.93239 | 0.34908 | 0.54101 | 0.34421 | 79.8684 | 0.60312 | 7.8171 | 6852.4438
1500 | 0.28122 | 24 | 0.96571 | 0.16793 | 0.30019 | 0.67748 | 0.88462 | 111 | 0.33633 | 1.009 | 0.20074 | 0.75521 | 0.42242 | 0.56512 | 0.076423 | 63.8223 | 0.36009 | 5.8792 | 6057.2015
1501 | 0.51898 | 25 | 0.057879 | 0.024058 | 0.3169 | 0.67961 | 0.24147 | 104 | 0.85373 | 1.1369 | 0.36524 | 0.80969 | 0.884 | 0.71016 | 0.84398 | 115.7923 | 0.98887 | 13.7971 | 6764.4466
1502 | 0.78469 | 27 | 0.92989 | 0.15414 | 0.92016 | 0.76004 | 0.53435 | 107 | 0.97574 | 1.2039 | 0.80097 | 0.98145 | 0.020636 | 0.3586 | 0.93184 | 127.3894 | 0.16275 | 4.5193 | 6793.3617
1503 | 0.016961 | 21 | 0.58804 | 0.088829 | 0.30445 | 0.67803 | 0.3303 | 105 | 0.71387 | 1.0918 | 0.53762 | 0.86688 | 0.80937 | 0.6792 | 0.39009 | 82.3665 | 0.034798 | 3.165 | 6008.5055
1504 | 0.65001 | 26 | 0.13734 | 0.037059 | 0.075822 | 0.63894 | 0.07984 | 102 | 0.38746 | 1.0185 | 0.71248 | 0.93731 | 0.24914 | 0.50361 | 0.69017 | 101.7952 | 0.27415 | 5.286 | 6310.686
1505 | 0.37558 | 24 | 0.1221 | 0.034943 | 0.63715 | 0.71481 | 0.70852 | 108 | 0.54929 | 1.0514 | 0.6945 | 0.92922 | 0.50323 | 0.58937 | 0.39347 | 82.5538 | 0.48214 | 6.795 | 6157.0292
1506 | 0.90643 | 28 | 0.16651 | 0.040806 | 0.12231 | 0.64946 | 0.75246 | 109 | 0.32593 | 1.0071 | 0.4251 | 0.82855 | 0.39145 | 0.55522 | 0.61533 | 96.2877 | 0.30378 | 5.4864 | 6561.3493
1507 | 0.66034 | 26 | 0.21273 | 0.046123 | 0.77544 | 0.73298 | 0.86944 | 111 | 0.1966 | 0.98295 | 0.091268 | 0.70465 | 0.50437 | 0.5897 | 0.27338 | 76.1783 | 0.98076 | 13.4186 | 5999.2788
1508 | 0.0073002 | 21 | 0.63017 | 0.094667 | 0.72379 | 0.72567 | 0.72156 | 109 | 0.62298 | 1.0684 | 0.76277 | 0.96139 | 0.0091892 | 0.3391 | 0.97664 | 136.7642 | 0.1673 | 4.5544 | 5702.7007
1509 | 0.88955 | 28 | 0.17318 | 0.041615 | 0.81318 | 0.73887 | 0.27218 | 105 | 0.054774 | 0.94378 | 0.9525 | 1.0932 | 0.22763 | 0.49462 | 0.58173 | 93.9911 | 0.23455 | 5.0246 | 6487.5942
1510 | 0.11411 | 22 | 0.35598 | 0.061002 | 0.05451 | 0.63302 | 0.52595 | 107 | 0.99453 | 1.2281 | 0.87502 | 1.0268 | 0.041301 | 0.3829 | 0.94334 | 129.3854 | 0.56468 | 7.4772 | 6241.7826
1511 | 0.58707 | 25 | 0.86088 | 0.1354 | 0.21909 | 0.66619 | 0.02483 | 101 | 0.59498 | 1.0617 | 0.82025 | 0.9923 | 0.38787 | 0.55405 | 0.0055283 | 53.7176 | 0.37234 | 5.967 | 6386.5746
1512 | 0.14537 | 23 | 0.97006 | 0.17003 | 0.91522 | 0.75882 | 0.80632 | 110 | 0.2117 | 0.98608 | 0.81519 | 0.9894 | 0.6152 | 0.61995 | 0.17408 | 70.8617 | 0.54787 | 7.3334 | 6238.3129
1513 | 0.10952 | 22 | 0.67221 | 0.10083 | 0.29611 | 0.67696 | 0.62642 | 108 | 0.56475 | 1.0548 | 0.33612 | 0.80084 | 0.33649 | 0.53663 | 0.30688 | 77.9003 | 0.77915 | 9.6417 | 5797.2073
1514 | 0.41957 | 25 | 0.28857 | 0.053907 | 0.068545 | 0.63703 | 0.49621 | 106 | 0.41671 | 1.0241 | 0.41424 | 0.82506 | 0.4212 | 0.56474 | 0.50223 | 88.8998 | 0.030395 | 3.0888 | 6175.1069
1515 | 0.27488 | 24 | 0.70653 | 0.10617 | 0.17939 | 0.6599 | 0.15958 | 103 | 0.76104 | 1.1054 | 0.10592 | 0.71274 | 0.62438 | 0.62235 | 0.46684 | 86.7647 | 0.19676 | 4.7701 | 6225.7614
1516 | 0.19903 | 23 | 0.55182 | 0.084045 | 0.022942 | 0.62142 | 0.17785 | 104 | 0.014815 | 0.92277 | 0.14614 | 0.73243 | 0.25703 | 0.50681 | 0.68399 | 101.3164 | 0.8529 | 10.627 | 5642.3403
1517 | 0.0024722 | 20 | 0.89095 | 0.1428 | 0.86153 | 0.74738 | 0.85189 | 110 | 0.72162 | 1.0939 | 0.0090479 | 0.63295 | 0.70312 | 0.64428 | 0.32394 | 78.7928 | 0.24294 | 5.0794 | 5606.6712
1518 | 0.45596 | 25 | 0.85472 | 0.13398 | 0.055411 | 0.63329 | 0.42645 | 106 | 0.084819 | 0.95449 | 0.25193 | 0.77387 | 0.45879 | 0.5763 | 0.34044 | 79.6675 | 0.17575 | 4.6181 | 6116.8019
1519 | 0.62676 | 26 | 0.97662 | 0.17352 | 0.56139 | 0.70634 | 0.80979 | 110 | 0.71207 | 1.0913 | 0.57385 | 0.88019 | 0.0016216 | 0.31643 | 0.51737 | 89.8357 | 0.49968 | 6.9351 | 6192.4495
1520 | 0.18066 | 23 | 0.68599 | 0.10294 | 0.062978 | 0.63549 | 0.3293 | 105 | 0.96657 | 1.1959 | 0.8068 | 0.98467 | 0.068099 | 0.40645 | 0.35287 | 80.3332 | 0.62418 | 8.0103 | 6164.3489
1521 | 0.059954 | 22 | 0.64352 | 0.096586 | 0.58279 | 0.70865 | 0.72978 | 109 | 0.19337 | 0.98227 | 0.1998 | 0.75484 | 0.89324 | 0.71463 | 0.65025 | 98.7833 | 0.39133 | 6.1046 | 5974.8782
1522 | 0.13054 | 23 | 0.73041 | 0.11007 | 0.31064 | 0.67882 | 0.1377 | 103 | 0.005853 | 0.91431 | 0.22636 | 0.76481 | 0.015464 | 0.35073 | 0.18886 | 71.7287 | 0.95066 | 12.4673 | 5239.5483
1523 | 0.22187 | 23 | 0.33761 | 0.059033 | 0.65672 | 0.71714 | 0.13933 | 103 | 0.40311 | 1.0215 | 0.76736 | 0.96371 | 0.95376 | 0.75065 | 0.83286 | 114.5945 | 0.82487 | 10.2285 | 6498.0349
1524 | 0.53271 | 25 | 0.20528 | 0.045308 | 0.15965 | 0.65651 | 0.8118 | 110 | 0.7183 | 1.093 | 0.05423 | 0.68067 | 0.8119 | 0.68014 | 0.088763 | 64.8965 | 0.84761 | 10.549 | 6290.8047
1525 | 0.60153 | 26 | 0.59562 | 0.089858 | 0.70657 | 0.72339 | 0.64077 | 108 | 0.60148 | 1.0633 | 0.54679 | 0.8702 | 0.92751 | 0.73317 | 0.87471 | 119.3453 | 0.99028 | 13.8761 | 7040.7382
1526 | 0.32589 | 24 | 0.17375 | 0.041684 | 0.062439 | 0.63534 | 0.26672 | 104 | 0.36087 | 1.0135 | 0.24416 | 0.77117 | 0.27806 | 0.5151 | 0.4347 | 84.8868 | 0.54333 | 7.295 | 5801.0342
1527 | 0.27288 | 24 | 0.82224 | 0.12697 | 0.85889 | 0.74688 | 0.86669 | 111 | 0.33805 | 1.0093 | 0.48401 | 0.84809 | 0.85379 | 0.69669 | 0.34103 | 79.6988 | 0.5362 | 7.2351 | 6364.8686
1528 | 0.85908 | 27 | 0.23746 | 0.048729 | 0.80696 | 0.73787 | 0.56534 | 107 | 0.022996 | 0.92837 | 0.27715 | 0.78237 | 0.46751 | 0.57891 | 0.6663 | 99.9728 | 0.16891 | 4.5666 | 6118.6982
1529 | 0.32093 | 24 | 0.96353 | 0.16692 | 0.1056 | 0.64596 | 0.10327 | 103 | 0.6269 | 1.0693 | 0.8815 | 1.0314 | 0.45005 | 0.57366 | 0.10666 | 66.3297 | 0.73891 | 9.1741 | 6553.1568
1530 | 0.40807 | 25 | 0.88597 | 0.14151 | 0.18791 | 0.6613 | 0.69663 | 108 | 0.59963 | 1.0628 | 0.26531 | 0.77843 | 0.28903 | 0.5193 | 0.14021 | 68.722 | 0.78339 | 9.6934 | 6210.7087
1531 | 0.8174 | 27 | 0.753 | 0.11392 | 0.4187 | 0.69151 | 0.19549 | 104 | 0.9586 | 1.1898 | 0.48699 | 0.84911 | 0.69636 | 0.6423 | 0.27942 | 76.4855 | 0.016664 | 2.8062 | 7022.3156
1532 | 0.9648 | 29 | 0.26392 | 0.051398 | 0.39038 | 0.68836 | 0.51382 | 106 | 0.26547 | 0.99639 | 0.22682 | 0.76498 | 0.83469 | 0.68888 | 0.62737 | 97.135 | 0.24512 | 5.0937 | 6813.5073
1533 | 0.75607 | 27 | 0.3864 | 0.064324 | 0.87711 | 0.75042 | 0.90855 | 111 | 0.05972 | 0.94572 | 0.3003 | 0.78983 | 0.039571 | 0.38115 | 0.65924 | 99.4461 | 0.062539 | 3.5617 | 5807.3411
1534 | 0.8707 | 27 | 0.90852 | 0.14761 | 0.69888 | 0.7224 | 0.25786 | 104 | 0.12217 | 0.96539 | 0.77936 | 0.96989 | 0.57145 | 0.60837 | 0.092672 | 65.221 | 0.31776 | 5.5824 | 6587.7487
1535 | 0.52987 | 25 | 0.65068 | 0.097631 | 0.98888 | 0.78509 | 0.53172 | 107 | 0.00056388 | 0.90444 | 0.94832 | 1.0886 | 0.28601 | 0.51816 | 0.097551 | 65.6166 | 0.20602 | 4.8346 | 6008.6426
1536 | 0.52977 | 25 | 0.96537 | 0.16777 | 0.1055 | 0.64593 | 0.0057808 | 101 | 0.36085 | 1.0135 | 0.36948 | 0.81099 | 0.098632 | 0.42811 | 0.093295 | 65.2721 | 0.010636 | 2.644 | 5910.3496
1537 | 0.91365 | 28 | 0.9384 | 0.15701 | 0.69605 | 0.72203 | 0.40943 | 106 | 0.98277 | 1.2112 | 0.52433 | 0.86212 | 0.22165 | 0.49205 | 0.16056 | 70.0353 | 0.60135 | 7.8011 | 6913.9702
1538 | 0.36735 | 24 | 0.43586 | 0.069906 | 0.76026 | 0.73076 | 0.1413 | 103 | 0.76306 | 1.106 | 0.72835 | 0.94467 | 0.78284 | 0.66972 | 0.69391 | 102.0872 | 0.60718 | 7.8539 | 6560.8445
1539 | 0.76958 | 27 | 0.86014 | 0.13523 | 0.70444 | 0.72312 | 0.53975 | 107 | 0.73444 | 1.0976 | 0.98887 | 1.1483 | 0.68865 | 0.64005 | 0.97549 | 136.4405 | 0.47379 | 6.7292 | 7627.9707
1540 | 0.22687 | 23 | 0.14286 | 0.037797 | 0.27979 | 0.6748 | 0.47595 | 106 | 0.98589 | 1.2149 | 0.87516 | 1.0269 | 0.46968 | 0.57956 | 0.83412 | 114.7282 | 0.70604 | 8.8182 | 6650.518
1541 | 0.72935 | 26 | 0.42491 | 0.068651 | 0.19425 | 0.66233 | 0.66217 | 108 | 0.19925 | 0.98351 | 0.48135 | 0.84719 | 0.61518 | 0.61995 | 0.32146 | 78.6623 | 0.52665 | 7.1555 | 6362.9819
1542 | 0.38766 | 24 | 0.22875 | 0.047828 | 0.23364 | 0.66836 | 0.54075 | 107 | 0.735 | 1.0977 | 0.76064 | 0.96032 | 0.56155 | 0.60568 | 0.011261 | 55.306 | 0.27964 | 5.3229 | 6267.5106
1543 | 0.38231 | 24 | 0.22886 | 0.047839 | 0.62445 | 0.71333 | 0.82569 | 110 | 0.044806 | 0.9396 | 0.9258 | 1.0666 | 0.35148 | 0.54184 | 0.37697 | 81.6428 | 0.35481 | 5.8417 | 6053.0316
1544 | 0.56751 | 25 | 0.47807 | 0.074869 | 0.81711 | 0.73952 | 0.93523 | 112 | 0.69869 | 1.0876 | 0.28287 | 0.78424 | 0.32441 | 0.53234 | 0.3311 | 79.1708 | 0.20796 | 4.8479 | 6128.2955
1545 | 0.36833 | 24 | 0.052109 | 0.022827 | 0.1195 | 0.64889 | 0.53109 | 107 | 0.63677 | 1.0717 | 0.85615 | 1.0142 | 0.24247 | 0.50087 | 0.27979 | 76.5046 | 0.99937 | 14.7135 | 6168.382
1546 | 0.6119 | 26 | 0.3371 | 0.058978 | 0.50956 | 0.70096 | 0.07486 | 102 | 0.86861 | 1.1428 | 0.53501 | 0.86594 | 0.30874 | 0.52666 | 0.52101 | 90.0629 | 0.74978 | 9.2966 | 6446.679
1547 | 0.34017 | 24 | 0.069357 | 0.026336 | 0.99032 | 0.78609 | 0.076433 | 102 | 0.38935 | 1.0188 | 0.49449 | 0.85169 | 0.55912 | 0.60502 | 0.81798 | 113.0524 | 0.41165 | 6.2544 | 5980.6166
1548 | 0.90833 | 28 | 0.10096 | 0.031775 | 0.47245 | 0.69721 | 0.98354 | 113 | 0.48679 | 1.0381 | 0.56356 | 0.87636 | 0.87408 | 0.70556 | 0.73278 | 105.2324 | 0.66075 | 8.359 | 7111.8242
1549 | 0.63117 | 26 | 0.32259 | 0.057444 | 0.86411 | 0.74787 | 0.52083 | 107 | 0.28367 | 0.99964 | 0.15268 | 0.73536 | 0.15253 | 0.45931 | 0.40554 | 83.2286 | 0.92649 | 11.9087 | 5796.7143
1550 | 0.47078 | 25 | 0.98799 | 0.18102 | 0.21564 | 0.66567 | 0.13519 | 103 | 0.41513 | 1.0238 | 0.65484 | 0.91218 | 0.49938 | 0.58827 | 0.9013 | 122.7918 | 0.2136 | 4.8862 | 6734.8307
1551 | 0.18779 | 23 | 0.41669 | 0.067715 | 0.8842 | 0.75188 | 0.89143 | 111 | 0.12615 | 0.96645 | 0.12453 | 0.72224 | 0.55423 | 0.60368 | 0.86927 | 118.6871 | 0.71442 | 8.9069 | 5856.3203
1552 | 0.92661 | 28 | 0.44787 | 0.071299 | 0.34099 | 0.68258 | 0.27331 | 105 | 0.82808 | 1.1274 | 0.5744 | 0.8804 | 0.97603 | 0.77007 | 0.33119 | 79.1756 | 0.087802 | 3.8505 | 7360.4927
1553 | 0.56191 | 25 | 0.54932 | 0.083723 | 0.15011 | 0.65479 | 0.62208 | 107 | 0.432 | 1.0271 | 0.96729 | 1.1114 | 0.38423 | 0.55285 | 0.10804 | 66.4348 | 0.88465 | 11.1276 | 6533.1463
1554 | 0.58064 | 25 | 0.91493 | 0.14948 | 0.49146 | 0.69914 | 0.90937 | 111 | 0.33698 | 1.0091 | 0.13641 | 0.72794 | 0.03878 | 0.38033 | 0.47128 | 87.0288 | 0.29389 | 5.4191 | 5818.5173
1555 | 0.049196 | 22 | 0.84789 | 0.13245 | 0.41216 | 0.69079 | 0.89502 | 111 | 0.45321 | 1.0313 | 0.75234 | 0.9562 | 0.62834 | 0.6234 | 0.8809 | 120.1127 | 0.98328 | 13.5257 | 6429.8021
1556 | 0.024485 | 21 | 0.90424 | 0.1464 | 0.83398 | 0.74238 | 0.08873 | 103 | 0.032101 | 0.93352 | 0.51521 | 0.8589 | 0.78791 | 0.67148 | 0.065355 | 62.7823 | 0.38477 | 6.0568 | 5634.2499
1557 | 0.36416 | 24 | 0.54753 | 0.083493 | 0.9691 | 0.77514 | 0.98013 | 113 | 0.946 | 1.1813 | 0.18341 | 0.74836 | 0.55707 | 0.60446 | 0.74668 | 106.4118 | 0.13352 | 4.282 | 6410.7855
1558 | 0.022061 | 21 | 0.34516 | 0.059839 | 0.6304 | 0.71402 | 0.5744 | 107 | 0.80227 | 1.1185 | 0.41048 | 0.82386 | 0.95958 | 0.75516 | 0.4993 | 88.7199 | 0.92426 | 11.8621 | 6136.1983
1559 | 0.58016 | 25 | 0.11271 | 0.033573 | 0.24362 | 0.6698 | 0.050046 | 102 | 0.49618 | 1.04 | 0.079792 | 0.69785 | 0.28864 | 0.51916 | 0.98022 | 137.8198 | 0.10127 | 3.9874 | 6055.6232
1560 | 0.47518 | 25 | 0.05508 | 0.023469 | 0.60246 | 0.71083 | 0.30283 | 105 | 0.64264 | 1.0732 | 0.58164 | 0.88313 | 0.64037 | 0.6266 | 0.037369 | 59.6655 | 0.63592 | 8.1203 | 6198.6791
1561 | 0.39923 | 24 | 0.40197 | 0.066056 | 0.092289 | 0.64296 | 0.39856 | 106 | 0.72044 | 1.0936 | 0.41341 | 0.82479 | 0.43681 | 0.5696 | 0.72979 | 104.9821 | 0.069688 | 3.6486 | 6297.7269
1562 | 0.76383 | 27 | 0.40055 | 0.065897 | 0.80025 | 0.73679 | 0.70991 | 108 | 0.59208 | 1.0611 | 0.62727 | 0.90091 | 0.31342 | 0.52837 | 0.087217 | 64.7663 | 0.95793 | 12.6613 | 6395.5105
1563 | 0.66668 | 26 | 0.41164 | 0.067144 | 0.97521 | 0.77773 | 0.95425 | 112 | 0.72184 | 1.094 | 0.62499 | 0.9 | 0.57543 | 0.60944 | 0.97208 | 135.5304 | 0.55167 | 7.3657 | 6848.4298
1564 | 0.65875 | 26 | 0.59361 | 0.089585 | 0.9895 | 0.78551 | 0.80865 | 110 | 0.41742 | 1.0242 | 0.26866 | 0.77955 | 0.021454 | 0.35975 | 0.78079 | 109.4532 | 0.72933 | 9.0681 | 5872.8184
1565 | 0.22649 | 23 | 0.91262 | 0.1488 | 0.99936 | 0.79642 | 0.86515 | 111 | 0.54589 | 1.0507 | 0.33947 | 0.80184 | 0.93905 | 0.74039 | 0.96837 | 134.5985 | 0.50109 | 6.9466 | 6586.4862
1566 | 0.38484 | 24 | 0.19258 | 0.043884 | 0.90175 | 0.75567 | 0.95807 | 112 | 0.26294 | 0.99593 | 0.9549 | 1.096 | 0.44915 | 0.57338 | 0.3165 | 78.4021 | 0.66594 | 8.41 | 6238.6751
1567 | 0.64924 | 26 | 0.42377 | 0.06852 | 0.10257 | 0.64529 | 0.087761 | 103 | 0.2246 | 0.98866 | 0.41442 | 0.82511 | 0.23125 | 0.49617 | 0.95017 | 130.6672 | 0.70095 | 8.7649 | 6306.9074
1568 | 0.69003 | 26 | 0.22609 | 0.047549 | 0.93324 | 0.76346 | 0.85596 | 110 | 0.20591 | 0.98489 | 0.65629 | 0.91279 | 0.28065 | 0.5161 | 0.45106 | 85.8357 | 0.24378 | 5.0849 | 6106.455
1569 | 0.30131 | 24 | 0.98453 | 0.17846 | 0.033363 | 0.62583 | 0.47139 | 106 | 0.89393 | 1.1537 | 0.95907 | 1.1009 | 0.2655 | 0.51019 | 0.19806 | 72.252 | 0.9839 | 13.5531 | 6803.7767
1570 | 0.18308 | 23 | 0.26274 | 0.051279 | 0.0631 | 0.63552 | 0.51498 | 106 | 0.52082 | 1.0452 | 0.96306 | 1.1058 | 0.17777 | 0.47199 | 0.54924 | 91.8565 | 0.65289 | 8.2826 | 6133.9281
1571 | 0.67169 | 26 | 0.14614 | 0.038228 | 0.94741 | 0.76757 | 0.82966 | 110 | 0.096461 | 0.9581 | 0.57616 | 0.88106 | 0.35618 | 0.54345 | 0.56741 | 93.0399 | 0.50566 | 6.9835 | 6084.3576
1572 | 0.92531 | 28 | 0.19483 | 0.04414 | 0.24836 | 0.67048 | 0.12216 | 103 | 0.83874 | 1.1312 | 0.56587 | 0.87721 | 0.68124 | 0.63793 | 0.592 | 94.6827 | 0.25479 | 5.1574 | 7038.6015
1573 | 0.14924 | 23 | 0.41277 | 0.067272 | 0.14122 | 0.65315 | 0.25196 | 104 | 0.45507 | 1.0316 | 0.14984 | 0.73409 | 0.65368 | 0.63022 | 0.65249 | 98.9475 | 0.86203 | 10.7649 | 6004.9057
1574 | 0.44117 | 25 | 0.10459 | 0.03234 | 0.31814 | 0.67977 | 0.75641 | 109 | 0.85938 | 1.1391 | 0.3039 | 0.79097 | 0.31162 | 0.52771 | 0.50195 | 88.8826 | 0.59079 | 7.7063 | 6245.8717
1575 | 0.1086 | 22 | 0.18769 | 0.043323 | 0.39947 | 0.68938 | 0.84554 | 110 | 0.74774 | 1.1014 | 0.38475 | 0.81574 | 0.068557 | 0.40681 | 0.44821 | 85.6696 | 0.50367 | 6.9674 | 5550.1499
1576 | 0.24928 | 24 | 0.82732 | 0.12803 | 0.1692 | 0.65817 | 0.52201 | 107 | 0.60294 | 1.0636 | 0.090252 | 0.70407 | 0.29594 | 0.52191 | 0.95894 | 132.4507 | 0.95063 | 12.4666 | 6284.7067
1577 | 0.97504 | 29 | 0.4528 | 0.071875 | 0.73853 | 0.72769 | 0.50797 | 106 | 0.27081 | 0.99736 | 0.5389 | 0.86734 | 0.094149 | 0.42517 | 0.8239 | 113.6584 | 0.08628 | 3.8344 | 6411.6344
1578 | 0.6863 | 26 | 0.41159 | 0.067138 | 0.48145 | 0.69813 | 0.9121 | 111 | 0.8289 | 1.1276 | 0.38182 | 0.81482 | 0.40937 | 0.561 | 0.15229 | 69.512 | 0.51079 | 7.0252 | 6449.7272
1579 | 0.69842 | 26 | 0.8963 | 0.14422 | 0.24088 | 0.66941 | 0.59356 | 107 | 0.081743 | 0.95349 | 0.76953 | 0.96481 | 0.82563 | 0.68534 | 0.25535 | 75.2677 | 0.62499 | 8.0178 | 6750.4475
1580 | 0.47135 | 25 | 0.75152 | 0.11366 | 0.67827 | 0.71978 | 0.628 | 108 | 0.37674 | 1.0165 | 0.3998 | 0.82046 | 0.81888 | 0.68276 | 0.28313 | 76.675 | 0.69093 | 8.6613 | 6413.8811
1581 | 0.59698 | 26 | 0.41159 | 0.067138 | 0.7086 | 0.72366 | 0.56026 | 107 | 0.072137 | 0.95025 | 0.38421 | 0.81557 | 0.64654 | 0.62827 | 0.55497 | 92.2271 | 0.076318 | 3.7252 | 6211.257
1582 | 0.63973 | 26 | 0.47 | 0.073905 | 0.99045 | 0.78618 | 0.64274 | 108 | 0.35539 | 1.0125 | 0.57351 | 0.88007 | 0.36043 | 0.5449 | 0.39458 | 82.6158 | 0.93611 | 12.1179 | 6203.7349
1583 | 0.79898 | 27 | 0.49712 | 0.077173 | 0.64334 | 0.71554 | 0.4967 | 106 | 0.9829 | 1.2113 | 0.27171 | 0.78057 | 0.76374 | 0.66325 | 0.82637 | 113.9141 | 0.010262 | 2.6326 | 7111.4622
1584 | 0.99732 | 30 | 0.63735 | 0.095695 | 0.31688 | 0.67961 | 0.13302 | 103 | 0.2502 | 0.99358 | 0.68231 | 0.92387 | 0.81694 | 0.68202 | 0.030725 | 58.7643 | 0.98876 | 13.791 | 7133.3914
1585 | 0.51251 | 25 | 0.67566 | 0.10136 | 0.37791 | 0.68694 | 0.99722 | 114 | 0.81865 | 1.124 | 0.023607 | 0.65322 | 0.80978 | 0.67935 | 0.13399 | 68.3023 | 0.49719 | 6.9151 | 6452.9775
1586 | 0.82117 | 27 | 0.95935 | 0.16508 | 0.60933 | 0.71161 | 0.18495 | 104 | 0.93547 | 1.1749 | 0.1766 | 0.74558 | 0.19377 | 0.47956 | 0.13839 | 68.6005 | 0.21915 | 4.9235 | 6480.9511
1587 | 0.94359 | 28 | 0.20568 | 0.045352 | 0.35474 | 0.68423 | 0.2789 | 105 | 0.03188 | 0.9334 | 0.12231 | 0.72115 | 0.69435 | 0.64171 | 0.050573 | 61.2442 | 0.078396 | 3.7486 | 6133.2109
1588 | 0.78004 | 27 | 0.19165 | 0.043778 | 0.043785 | 0.62959 | 0.586 | 107 | 0.76796 | 1.1075 | 0.13863 | 0.72898 | 0.95305 | 0.75012 | 0.9969 | 145.1807 | 0.7583 | 9.3945 | 7257.7473
1589 | 0.89362 | 28 | 0.86459 | 0.13626 | 0.19143 | 0.66187 | 0.20951 | 104 | 0.84264 | 1.1327 | 0.82106 | 0.99277 | 0.55503 | 0.6039 | 0.073232 | 63.5307 | 0.26003 | 5.192 | 7215.0442
1590 | 0.75619 | 27 | 0.13777 | 0.037117 | 0.65626 | 0.71709 | 0.26207 | 104 | 0.1642 | 0.97581 | 0.18311 | 0.74824 | 0.93791 | 0.73964 | 0.10791 | 66.4245 | 0.15427 | 4.4528 | 6310.5634
1591 | 0.093329 | 22 | 0.91402 | 0.14921 | 0.015996 | 0.61789 | 0.99236 | 114 | 0.72513 | 1.0949 | 0.11816 | 0.71908 | 0.93919 | 0.74048 | 0.96268 | 133.2703 | 0.64876 | 8.2427 | 6680.5485
1592 | 0.18908 | 23 | 0.93686 | 0.15648 | 0.55078 | 0.70521 | 0.8701 | 111 | 0.60334 | 1.0637 | 0.90636 | 1.0501 | 0.36671 | 0.54702 | 0.8757 | 119.4669 | 0.7298 | 9.0732 | 6611.5885
1593 | 0.86176 | 27 | 0.47405 | 0.074388 | 0.63615 | 0.71469 | 0.38115 | 105 | 0.9792 | 1.2073 | 0.18729 | 0.74992 | 0.20354 | 0.48404 | 0.047838 | 60.936 | 0.43906 | 6.4605 | 6346.0962
1594 | 0.1833 | 23 | 0.2601 | 0.051013 | 0.40314 | 0.68979 | 0.53427 | 107 | 0.16672 | 0.97639 | 0.8618 | 1.0179 | 0.24405 | 0.50152 | 0.90228 | 122.9286 | 0.90396 | 11.4665 | 6079.0222
1595 | 0.46572 | 25 | 0.58337 | 0.088201 | 0.3465 | 0.68325 | 0.015832 | 101 | 0.72974 | 1.0962 | 0.26012 | 0.77668 | 0.25414 | 0.50564 | 0.94739 | 130.137 | 0.93338 | 12.0571 | 6339.2028
1596 | 0.25408 | 24 | 0.086287 | 0.029375 | 0.28588 | 0.67562 | 0.44205 | 106 | 0.0091461 | 0.91789 | 0.18337 | 0.74834 | 0.15098 | 0.4585 | 0.38613 | 82.1471 | 0.041735 | 3.2758 | 5386.1547
1597 | 0.23238 | 23 | 0.29901 | 0.054984 | 0.69637 | 0.72207 | 0.76644 | 109 | 0.2815 | 0.99926 | 0.89309 | 1.0398 | 0.36117 | 0.54515 | 0.27441 | 76.2305 | 0.5612 | 7.4473 | 5980.4179
1598 | 0.38367 | 24 | 0.96016 | 0.16543 | 0.63038 | 0.71402 | 0.013396 | 101 | 0.77853 | 1.1108 | 0.53668 | 0.86654 | 0.30361 | 0.52477 | 0.18249 | 71.3597 | 0.64073 | 8.1659 | 6207.6546
1599 | 0.78214 | 27 | 0.58638 | 0.088606 | 0.6137 | 0.7121 | 0.25302 | 104 | 0.1858 | 0.98064 | 0.70903 | 0.93574 | 0.49925 | 0.58823 | 0.0985 | 65.6924 | 0.99447 | 14.1524 | 6453.5314
1600 | 0.58819 | 25 | 0.80726 | 0.12396 | 0.78999 | 0.73519 | 0.15001 | 103 | 0.63136 | 1.0704 | 0.55823 | 0.87438 | 0.83274 | 0.68811 | 0.40008 | 82.9224 | 0.7395 | 9.1806 | 6594.0866
1601 | 0.84893 | 27 | 0.44981 | 0.071525 | 0.7651 | 0.73146 | 0.94293 | 112 | 0.8339 | 1.1294 | 0.62653 | 0.90061 | 0.027539 | 0.36769 | 0.30872 | 77.9959 | 0.16537 | 4.5396 | 6240.6574
1602 | 0.079269 | 22 | 0.27505 | 0.052526 | 0.32407 | 0.68051 | 0.085697 | 103 | 0.07718 | 0.95197 | 0.39683 | 0.81953 | 0.45548 | 0.5753 | 0.74292 | 106.0903 | 0.6853 | 8.6038 | 5676.0336
1603 | 0.61289 | 26 | 0.13322 | 0.036499 | 0.55535 | 0.7057 | 0.19797 | 104 | 0.84061 | 1.1319 | 0.19719 | 0.75383 | 0.39923 | 0.55774 | 0.0056295 | 53.7515 | 0.91311 | 11.6392 | 6135.3881
1604 | 0.776 | 27 | 0.1885 | 0.043416 | 0.045643 | 0.63021 | 0.072214 | 102 | 0.17237 | 0.97767 | 0.42008 | 0.82693 | 0.33595 | 0.53644 | 0.24522 | 74.7599 | 0.81024 | 10.0332 | 6182.7742
1605 | 0.62238 | 26 | 0.32222 | 0.057405 | 0.48279 | 0.69826 | 0.92062 | 112 | 0.45458 | 1.0315 | 0.71005 | 0.9362 | 0.79897 | 0.67541 | 0.82557 | 113.8304 | 0.40088 | 6.1747 | 6887.2787
1606 | 0.20781 | 23 | 0.68305 | 0.10249 | 0.0096647 | 0.6139 | 0.34702 | 105 | 0.28254 | 0.99944 | 0.42167 | 0.82744 | 0.22295 | 0.49261 | 0.31686 | 78.4211 | 0.94429 | 12.3089 | 5832.7433
1607 | 0.29007 | 24 | 0.14804 | 0.038476 | 0.27094 | 0.67361 | 0.75131 | 109 | 0.41995 | 1.0247 | 0.4378 | 0.83267 | 0.21179 | 0.48773 | 0.61793 | 96.4696 | 0.41805 | 6.3021 | 5896.4403
1608 | 0.19591 | 23 | 0.44606 | 0.071088 | 0.39778 | 0.68919 | 0.92438 | 112 | 0.80576 | 1.1196 | 0.057974 | 0.68341 | 0.92871 | 0.73389 | 0.33061 | 79.1451 | 0.35192 | 5.8212 | 6256.3625
1609 | 0.99051 | 29 | 0.67932 | 0.10192 | 0.43905 | 0.69371 | 0.77408 | 109 | 0.27942 | 0.99889 | 0.14279 | 0.7309 | 0.13977 | 0.4525 | 0.2607 | 75.5372 | 0.02943 | 3.0713 | 6231.8002
1610 | 0.43478 | 25 | 0.1227 | 0.035028 | 0.93081 | 0.7628 | 0.54901 | 107 | 0.61967 | 1.0676 | 0.2375 | 0.76882 | 0.87137 | 0.70434 | 0.59385 | 94.8086 | 0.54438 | 7.3039 | 6331.9742
1611 | 0.861 | 27 | 0.3896 | 0.064679 | 0.5112 | 0.70113 | 0.7186 | 109 | 0.94747 | 1.1822 | 0.38846 | 0.81689 | 0.87576 | 0.70633 | 0.7423 | 106.0368 | 0.31266 | 5.5473 | 7228.3102
1612 | 0.39856 | 24 | 0.33881 | 0.05916 | 0.61433 | 0.71217 | 0.46875 | 106 | 0.21161 | 0.98606 | 0.23393 | 0.76755 | 0.50144 | 0.58886 | 0.27725 | 76.3749 | 0.43035 | 6.3945 | 5802.5628
1613 | 0.44789 | 25 | 0.88144 | 0.14036 | 0.38496 | 0.68775 | 0.61188 | 107 | 0.78559 | 1.113 | 0.33604 | 0.80081 | 0.63317 | 0.62468 | 0.16829 | 70.5117 | 0.42416 | 6.3479 | 6524.7377
1614 | 0.67587 | 26 | 0.52367 | 0.080459 | 0.76177 | 0.73097 | 0.62763 | 108 | 0.9734 | 1.2018 | 0.041587 | 0.67064 | 0.4204 | 0.56449 | 0.48244 | 87.6967 | 0.15008 | 4.4194 | 6429.4254
1615 | 0.39612 | 24 | 0.96303 | 0.1667 | 0.24695 | 0.67028 | 0.4311 | 106 | 0.94559 | 1.181 | 0.065384 | 0.68858 | 0.12018 | 0.44141 | 0.12813 | 67.8974 | 0.30131 | 5.4695 | 6028.6103
1616 | 0.10485 | 22 | 0.36903 | 0.062417 | 0.40689 | 0.69021 | 0.13138 | 103 | 0.82486 | 1.1262 | 0.57504 | 0.88064 | 0.91155 | 0.72409 | 0.63837 | 97.9208 | 0.40105 | 6.176 | 6331.9671
1617 | 0.25675 | 24 | 0.80118 | 0.12277 | 0.88104 | 0.75122 | 0.31269 | 105 | 0.35029 | 1.0116 | 0.061225 | 0.68571 | 0.75912 | 0.66172 | 0.78034 | 109.4111 | 0.41703 | 6.2945 | 6121.1974
1618 | 0.69236 | 26 | 0.28053 | 0.053085 | 0.2813 | 0.67501 | 0.84761 | 110 | 0.18863 | 0.98125 | 0.71394 | 0.93798 | 0.57569 | 0.60951 | 0.843 | 115.6848 | 0.78855 | 9.757 | 6640.3401
1619 | 0.1761 | 23 | 0.1513 | 0.038897 | 0.74395 | 0.72844 | 0.77994 | 109 | 0.36237 | 1.0138 | 0.43886 | 0.83302 | 0.58598 | 0.61226 | 0.71018 | 103.3775 | 0.25044 | 5.1287 | 5958.175
1620 | 0.015164 | 21 | 0.94398 | 0.15901 | 0.44031 | 0.69384 | 0.44606 | 106 | 0.91003 | 1.1613 | 0.23845 | 0.76916 | 0.35765 | 0.54395 | 0.38965 | 82.3421 | 0.77481 | 9.5894 | 5939.0889
1621 | 0.97383 | 29 | 0.59886 | 0.090299 | 0.85436 | 0.74603 | 0.7134 | 108 | 0.50429 | 1.0417 | 0.36274 | 0.80892 | 0.92359 | 0.73086 | 0.72134 | 104.2836 | 0.99617 | 14.2945 | 7215.675
1622 | 0.076388 | 22 | 0.3203 | 0.057202 | 0.37712 | 0.68685 | 0.86099 | 110 | 0.95223 | 1.1853 | 0.19988 | 0.75487 | 0.81566 | 0.68154 | 0.61945 | 96.5763 | 0.74021 | 9.1885 | 6286.9606
1623 | 0.46386 | 25 | 0.94929 | 0.16099 | 0.64821 | 0.71612 | 0.83143 | 110 | 0.16023 | 0.97489 | 0.93204 | 1.0723 | 0.38574 | 0.55335 | 0.20298 | 72.5268 | 0.9902 | 13.8713 | 6539.8718
1624 | 0.23221 | 23 | 0.28815 | 0.053865 | 0.15068 | 0.6549 | 0.12517 | 103 | 0.32242 | 1.0065 | 0.14065 | 0.72992 | 0.092342 | 0.42396 | 0.5518 | 92.0215 | 0.38632 | 6.0681 | 5462.9561
1625 | 0.90631 | 28 | 0.6473 | 0.097136 | 0.70548 | 0.72325 | 0.69955 | 108 | 0.89003 | 1.1519 | 0.20986 | 0.75869 | 0.15622 | 0.46123 | 0.50598 | 89.13 | 0.30823 | 5.5168 | 6530.565
1626 | 0.95839 | 29 | 0.766 | 0.11622 | 0.7891 | 0.73505 | 0.40307 | 106 | 0.4993 | 1.0407 | 0.019384 | 0.64823 | 0.18131 | 0.4737 | 0.090979 | 65.0814 | 0.13626 | 4.3053 | 6140.3606
1627 | 0.47063 | 25 | 0.52724 | 0.080908 | 0.54739 | 0.70486 | 0.5749 | 107 | 0.17895 | 0.97914 | 0.32038 | 0.79607 | 0.22298 | 0.49262 | 0.097263 | 65.5935 | 0.0019796 | 2.2779 | 5754.0196
1628 | 0.44114 | 25 | 0.095444 | 0.030894 | 0.20753 | 0.66442 | 0.82461 | 110 | 0.017689 | 0.92488 | 0.49927 | 0.85334 | 0.81146 | 0.67997 | 0.89595 | 122.0645 | 0.57566 | 7.5728 | 6379.5939
1629 | 0.13977 | 23 | 0.78513 | 0.11971 | 0.53891 | 0.70397 | 0.0004426 | 100 | 0.7491 | 1.1018 | 0.27231 | 0.78077 | 0.50351 | 0.58945 | 0.99478 | 143.7414 | 0.35389 | 5.8352 | 6327.569
1630 | 0.11629 | 22 | 0.46624 | 0.073459 | 0.60519 | 0.71114 | 0.52982 | 107 | 0.79454 | 1.1159 | 0.74408 | 0.95217 | 0.30228 | 0.52428 | 0.51406 | 89.6298 | 0.4133 | 6.2667 | 5997.2681
1631 | 0.78816 | 27 | 0.45644 | 0.072302 | 0.43483 | 0.69326 | 0.94087 | 112 | 0.24586 | 0.99276 | 0.037797 | 0.66735 | 0.53774 | 0.59913 | 0.7975 | 111.0292 | 0.30345 | 5.4841 | 6366.9277
1632 | 0.18097 | 23 | 0.012603 | 0.011226 | 0.96021 | 0.77179 | 0.47822 | 106 | 0.79528 | 1.1162 | 0.52897 | 0.86378 | 0.065274 | 0.40422 | 0.52877 | 90.5504 | 0.79249 | 9.8061 | 5582.2973
1633 | 0.95322 | 28 | 0.35065 | 0.060427 | 0.85901 | 0.7469 | 0.29343 | 105 | 0.63576 | 1.0715 | 0.58902 | 0.88594 | 0.65357 | 0.63019 | 0.30791 | 77.9538 | 0.6257 | 8.0244 | 6754.5249
1634 | 0.49922 | 25 | 0.96426 | 0.16725 | 0.94287 | 0.7662 | 0.88225 | 111 | 0.37368 | 1.0159 | 0.80221 | 0.98212 | 0.23526 | 0.49786 | 0.51805 | 89.8781 | 0.13585 | 4.3018 | 6381.8187
1635 | 0.29416 | 24 | 0.53421 | 0.08179 | 0.49012 | 0.69901 | 0.61273 | 107 | 0.6583 | 1.0771 | 0.52677 | 0.86299 | 0.6475 | 0.62853 | 0.11088 | 66.6491 | 0.51542 | 7.063 | 6237.5779
1636 | 0.96227 | 29 | 0.53946 | 0.082458 | 0.84577 | 0.74446 | 0.49315 | 106 | 0.11855 | 0.96441 | 0.53825 | 0.8671 | 0.072985 | 0.4102 | 0.47206 | 87.0752 | 0.28386 | 5.3513 | 6179.5822
1637 | 0.3478 | 24 | 0.12146 | 0.034851 | 0.81802 | 0.73967 | 0.41966 | 106 | 0.57799 | 1.0578 | 0.83537 | 1.0012 | 0.90904 | 0.72274 | 0.45226 | 85.9059 | 0.16168 | 4.5111 | 6508.9964
1638 | 0.53336 | 25 | 0.48989 | 0.076294 | 0.30852 | 0.67855 | 0.35875 | 105 | 0.69382 | 1.0863 | 0.82979 | 0.99788 | 0.97709 | 0.77119 | 0.34404 | 79.8596 | 0.3703 | 5.9523 | 6989.671
1639 | 0.30757 | 24 | 0.86408 | 0.13614 | 0.78146 | 0.73389 | 0.10983 | 103 | 0.95298 | 1.1859 | 0.94577 | 1.0859 | 0.31131 | 0.5276 | 0.73607 | 105.509 | 0.29444 | 5.4228 | 6732.6181
1640 | 0.84813 | 27 | 0.3139 | 0.056532 | 0.52852 | 0.70289 | 0.24736 | 104 | 0.93507 | 1.1746 | 0.19279 | 0.7521 | 0.95419 | 0.75098 | 0.3679 | 81.1469 | 0.042034 | 3.2804 | 6974.6487
1641 | 0.84339 | 27 | 0.72407 | 0.10902 | 0.29793 | 0.67719 | 0.76915 | 109 | 0.17184 | 0.97755 | 0.96496 | 1.1083 | 0.30294 | 0.52452 | 0.87205 | 119.0221 | 0.19108 | 4.7299 | 6921.7422
1642 | 0.63446 | 26 | 0.17449 | 0.041772 | 0.027259 | 0.62335 | 0.78724 | 109 | 0.82048 | 1.1247 | 0.45623 | 0.83875 | 0.64526 | 0.62792 | 0.26098 | 75.5512 | 0.33414 | 5.6962 | 6691.0129
1643 | 0.30885 | 24 | 0.11382 | 0.033737 | 0.68342 | 0.72043 | 0.58383 | 107 | 0.12471 | 0.96607 | 0.93966 | 1.0797 | 0.072734 | 0.41001 | 0.087023 | 64.7499 | 0.48204 | 6.7942 | 5687.4531
1644 | 0.86707 | 27 | 0.05001 | 0.022363 | 0.5595 | 0.70614 | 0.088154 | 103 | 0.73768 | 1.0985 | 0.1443 | 0.73159 | 0.7737 | 0.66659 | 0.78115 | 109.4861 | 0.35234 | 5.8242 | 6614.6545
1645 | 0.90791 | 28 | 0.57042 | 0.086477 | 0.30742 | 0.67841 | 0.1642 | 104 | 0.40669 | 1.0222 | 0.83702 | 1.0022 | 0.68428 | 0.6388 | 0.41017 | 83.4892 | 0.67038 | 8.454 | 7028.7008
1646 | 0.69581 | 26 | 0.13389 | 0.036591 | 0.59609 | 0.71012 | 0.87068 | 111 | 0.056741 | 0.94456 | 0.43599 | 0.83208 | 0.22101 | 0.49177 | 0.52613 | 90.3846 | 0.7384 | 9.1683 | 5948.8592
1647 | 0.75401 | 26 | 0.62353 | 0.093726 | 0.33373 | 0.6817 | 0.68367 | 108 | 0.22561 | 0.98886 | 0.51169 | 0.85766 | 0.47151 | 0.58011 | 0.96425 | 133.6258 | 0.27538 | 5.2943 | 6597.9285
1648 | 0.4503 | 25 | 0.032382 | 0.017995 | 0.23708 | 0.66886 | 0.67427 | 108 | 0.16427 | 0.97583 | 0.25974 | 0.77655 | 0.62967 | 0.62375 | 0.63648 | 97.7849 | 0.876 | 10.985 | 6108.6532
1649 | 0.67836 | 26 | 0.22212 | 0.04713 | 0.68203 | 0.72025 | 0.81262 | 110 | 0.7591 | 1.1048 | 0.66926 | 0.91826 | 0.76464 | 0.66355 | 0.77864 | 109.2545 | 0.54322 | 7.2941 | 6907.9195
1650 | 0.79554 | 27 | 0.63277 | 0.095038 | 0.95635 | 0.77045 | 0.76504 | 109 | 0.46911 | 1.0345 | 0.29691 | 0.78876 | 0.051218 | 0.39232 | 0.90063 | 122.7003 | 0.37947 | 6.0184 | 6156.7731
1651 | 0.089724 | 22 | 0.56829 | 0.086196 | 0.69372 | 0.72173 | 0.13232 | 103 | 0.15914 | 0.97463 | 0.0084589 | 0.63186 | 0.42841 | 0.567 | 0.35361 | 80.3728 | 0.51508 | 7.0603 | 5363.1775
1652 | 0.064571 | 22 | 0.90391 | 0.14631 | 0.80543 | 0.73762 | 0.56091 | 107 | 0.93395 | 1.174 | 0.83902 | 1.0034 | 0.80964 | 0.6793 | 0.37517 | 81.5441 | 0.62926 | 8.0577 | 6592.9546
1653 | 0.8369 | 27 | 0.99123 | 0.18378 | 0.96715 | 0.77437 | 0.70512 | 108 | 0.39488 | 1.0199 | 0.040414 | 0.66964 | 0.10712 | 0.43351 | 0.45512 | 86.0736 | 0.87495 | 10.9681 | 6073.7911
1654 | 0.099696 | 22 | 0.79629 | 0.12183 | 0.72866 | 0.72633 | 0.72582 | 109 | 0.6028 | 1.0636 | 0.24399 | 0.77111 | 0.18441 | 0.47517 | 0.98353 | 138.8847 | 0.14656 | 4.3908 | 5941.649
1655 | 0.91293 | 28 | 0.50179 | 0.077745 | 0.74358 | 0.72839 | 0.30728 | 105 | 0.70238 | 1.0886 | 0.45849 | 0.8395 | 0.99687 | 0.80197 | 0.61742 | 96.4333 | 0.89834 | 11.3646 | 7317.7892
1656 | 0.47523 | 25 | 0.35911 | 0.06134 | 0.031847 | 0.62524 | 0.8058 | 110 | 0.13711 | 0.96927 | 0.92218 | 1.0633 | 0.044359 | 0.38591 | 0.86913 | 118.6702 | 0.41612 | 6.2877 | 6203.9883
1657 | 0.96012 | 29 | 0.94777 | 0.16042 | 0.69404 | 0.72177 | 0.43013 | 106 | 0.12365 | 0.96579 | 0.95254 | 1.0933 | 0.26229 | 0.50891 | 0.79814 | 111.0903 | 0.79838 | 9.8804 | 7114.8541
1658 | 0.02123 | 21 | 0.80214 | 0.12296 | 0.54674 | 0.70479 | 0.35844 | 105 | 0.19256 | 0.98209 | 0.90884 | 1.0521 | 0.41326 | 0.56223 | 0.6575 | 99.3171 | 0.52529 | 7.1443 | 5958.4069
1659 | 0.13313 | 23 | 0.079391 | 0.028176 | 0.06938 | 0.63725 | 0.39401 | 105 | 0.97607 | 1.2042 | 0.62448 | 0.89979 | 0.24732 | 0.50286 | 0.54224 | 91.4067 | 0.31905 | 5.5913 | 6178.1187
1660 | 0.95975 | 29 | 0.06302 | 0.025104 | 0.37756 | 0.6869 | 0.53359 | 107 | 0.72185 | 1.094 | 0.56028 | 0.87514 | 0.036362 | 0.37779 | 0.78731 | 110.0605 | 0.044543 | 3.318 | 6460.1403
1661 | 0.99157 | 29 | 0.23433 | 0.048407 | 0.098528 | 0.64439 | 0.1587 | 103 | 0.078811 | 0.95252 | 0.78513 | 0.97291 | 0.16903 | 0.46771 | 0.78992 | 110.3066 | 0.54918 | 7.3445 | 6601.5979
1662 | 0.99379 | 29 | 0.71668 | 0.10781 | 0.95905 | 0.77138 | 0.61452 | 107 | 0.045515 | 0.93991 | 0.082269 | 0.69936 | 0.61528 | 0.61997 | 0.61802 | 96.4754 | 0.95294 | 12.5266 | 6448.1324
1663 | 0.88213 | 28 | 0.3608 | 0.061523 | 0.39506 | 0.68889 | 0.10118 | 103 | 0.16023 | 0.97489 | 0.83241 | 0.99945 | 0.30942 | 0.52691 | 0.79378 | 110.6722 | 0.68222 | 8.5726 | 6684.7014
1664 | 0.22264 | 23 | 0.4999 | 0.077513 | 0.47651 | 0.69762 | 0.72946 | 109 | 0.06087 | 0.94616 | 0.62132 | 0.89853 | 0.5406 | 0.59993 | 0.20463 | 72.6182 | 0.85221 | 10.6168 | 5878.3939
1665 | 0.5923 | 25 | 0.31095 | 0.056224 | 0.61572 | 0.71233 | 0.14885 | 103 | 0.73655 | 1.0982 | 0.33796 | 0.80139 | 0.49027 | 0.58562 | 0.31041 | 78.084 | 0.69944 | 8.7492 | 6184.4332
1666 | 0.79311 | 27 | 0.5043 | 0.078053 | 0.22583 | 0.66721 | 0.67291 | 108 | 0.53856 | 1.0491 | 0.67001 | 0.91858 | 0.16438 | 0.46539 | 0.40211 | 83.036 | 0.59913 | 7.7811 | 6430.3653
1667 | 0.80593 | 27 | 0.50617 | 0.078283 | 0.79863 | 0.73654 | 0.55939 | 107 | 0.58567 | 1.0596 | 0.85848 | 1.0157 | 0.16467 | 0.46553 | 0.84245 | 115.6255 | 0.82253 | 10.1968 | 6660.4259
1668 | 0.13665 | 23 | 0.3957 | 0.065356 | 0.32006 | 0.68001 | 0.82413 | 110 | 0.10784 | 0.96144 | 0.85878 | 1.0159 | 0.91269 | 0.72471 | 0.19569 | 72.1183 | 0.49492 | 6.8969 | 6303.02
1669 | 0.62809 | 26 | 0.62463 | 0.093881 | 0.77073 | 0.73228 | 0.26057 | 104 | 0.87193 | 1.1441 | 0.57225 | 0.8796 | 0.15065 | 0.45833 | 0.24759 | 74.8792 | 0.16469 | 4.5344 | 6262.3989
1670 | 0.2945 | 24 | 0.62326 | 0.093688 | 0.90053 | 0.7554 | 0.93106 | 112 | 0.68594 | 1.0842 | 0.0041011 | 0.62218 | 0.83987 | 0.69095 | 0.45974 | 86.3453 | 0.27017 | 5.2595 | 6142.8932
1671 | 0.56993 | 25 | 0.79717 | 0.12199 | 0.83518 | 0.74259 | 0.043994 | 102 | 0.4052 | 1.0219 | 0.93885 | 1.0789 | 0.66533 | 0.63344 | 0.85365 | 116.8693 | 0.71377 | 8.9 | 6810.8819
1672 | 0.047446 | 22 | 0.81372 | 0.12524 | 0.35016 | 0.68369 | 0.49105 | 106 | 0.98621 | 1.2153 | 0.31346 | 0.79395 | 0.98779 | 0.78436 | 0.3421 | 79.7558 | 0.13151 | 4.2647 | 6608.1308
1673 | 0.31217 | 24 | 0.54584 | 0.083275 | 0.89096 | 0.7533 | 0.31763 | 105 | 0.67757 | 1.082 | 0.50053 | 0.85377 | 0.59841 | 0.61556 | 0.41054 | 83.5098 | 0.81075 | 10.0398 | 6209.6369
1674 | 0.96695 | 29 | 0.015076 | 0.012279 | 0.90971 | 0.75751 | 0.32975 | 105 | 0.27389 | 0.99791 | 0.60542 | 0.89227 | 0.76095 | 0.66233 | 0.017841 | 56.6785 | 0.82277 | 10.2 | 6586.1456
1675 | 0.64087 | 26 | 0.31566 | 0.056716 | 0.35938 | 0.68478 | 0.40681 | 106 | 0.7304 | 1.0964 | 0.56274 | 0.87605 | 0.27558 | 0.51414 | 0.64799 | 98.6186 | 0.06692 | 3.6155 | 6417.5641
1676 | 0.72259 | 26 | 0.1003 | 0.031671 | 0.51071 | 0.70108 | 0.57026 | 107 | 0.77475 | 1.1096 | 0.50054 | 0.85378 | 0.29688 | 0.52226 | 0.33232 | 79.2357 | 0.087184 | 3.844 | 6272.229
1677 | 0.75485 | 26 | 0.42711 | 0.068902 | 0.23768 | 0.66895 | 0.80549 | 110 | 0.93876 | 1.1768 | 0.92305 | 1.0641 | 0.2515 | 0.50457 | 0.44536 | 85.5032 | 0.92408 | 11.8584 | 6906.2576
1678 | 0.78723 | 27 | 0.64383 | 0.096631 | 0.54215 | 0.70431 | 0.45427 | 106 | 0.63082 | 1.0703 | 0.78777 | 0.97431 | 0.0096153 | 0.34 | 0.45763 | 86.2207 | 0.70432 | 8.8001 | 6229.6362
1679 | 0.80497 | 27 | 0.39185 | 0.064928 | 0.85632 | 0.74639 | 0.62467 | 107 | 0.63522 | 1.0713 | 0.21067 | 0.759 | 0.18073 | 0.47342 | 0.96734 | 134.3491 | 0.84484 | 10.5088 | 6392.994
1680 | 0.66886 | 26 | 0.54709 | 0.083436 | 0.64043 | 0.7152 | 0.35159 | 105 | 0.68837 | 1.0849 | 0.64391 | 0.90766 | 0.79328 | 0.67338 | 0.79921 | 111.1941 | 0.086854 | 3.8405 | 6877.4143
1681 | 0.57971 | 25 | 0.34946 | 0.0603 | 0.39907 | 0.68934 | 0.094973 | 103 | 0.8412 | 1.1321 | 0.94907 | 1.0894 | 0.97652 | 0.77059 | 0.73873 | 105.7337 | 0.19817 | 4.7801 | 7284.6059
1682 | 0.77591 | 27 | 0.56589 | 0.08588 | 0.94595 | 0.76712 | 0.92569 | 112 | 0.21601 | 0.98695 | 0.64702 | 0.90894 | 0.71541 | 0.64796 | 0.88222 | 120.2788 | 0.1516 | 4.4315 | 6812.5798
1683 | 0.8435 | 27 | 0.88337 | 0.14085 | 0.58588 | 0.70899 | 0.44037 | 106 | 0.85457 | 1.1372 | 0.10697 | 0.7133 | 0.083475 | 0.41786 | 0.90397 | 123.1633 | 0.49612 | 6.9065 | 6471.353
1684 | 0.53053 | 25 | 0.44334 | 0.070772 | 0.64931 | 0.71625 | 0.98522 | 114 | 0.13874 | 0.96969 | 0.32905 | 0.79871 | 0.51272 | 0.59209 | 0.94499 | 129.6884 | 0.15333 | 4.4454 | 6315.0379
1685 | 0.84871 | 27 | 0.1157 | 0.034014 | 0.89126 | 0.75336 | 0.094307 | 103 | 0.034147 | 0.93457 | 0.43374 | 0.83135 | 0.91455 | 0.72573 | 0.53914 | 91.2081 | 0.85468 | 10.6535 | 6398.9042
1686 | 0.12902 | 23 | 0.52362 | 0.080453 | 0.13888 | 0.6527 | 0.94157 | 112 | 0.087892 | 0.95546 | 0.6065 | 0.89269 | 0.95156 | 0.74903 | 0.63174 | 97.4454 | 0.53544 | 7.2288 | 6378.3192
1687 | 0.13902 | 23 | 0.092878 | 0.030476 | 0.94671 | 0.76735 | 0.87035 | 111 | 0.30316 | 1.0031 | 0.86447 | 1.0196 | 0.14778 | 0.45681 | 0.52736 | 90.4616 | 0.077678 | 3.7405 | 5749.9729
1688 | 0.52211 | 25 | 0.37479 | 0.063047 | 0.030619 | 0.62475 | 0.49181 | 106 | 0.35084 | 1.0117 | 0.011528 | 0.63719 | 0.15823 | 0.46226 | 0.50932 | 89.3361 | 0.17977 | 4.6478 | 5727.3971
1689 | 0.38517 | 24 | 0.53144 | 0.081439 | 0.024073 | 0.62194 | 0.40783 | 106 | 0.087408 | 0.95531 | 0.48132 | 0.84718 | 0.51344 | 0.59229 | 0.46528 | 86.6724 | 0.54266 | 7.2893 | 6068.0055
1690 | 0.54884 | 25 | 0.64732 | 0.097139 | 0.54793 | 0.70491 | 0.57383 | 107 | 0.32822 | 1.0076 | 0.62031 | 0.89813 | 0.41611 | 0.56313 | 0.56268 | 92.7297 | 0.37307 | 5.9722 | 6289.5371
1691 | 0.074311 | 22 | 0.45896 | 0.072598 | 0.69555 | 0.72197 | 0.5309 | 107 | 0.37169 | 1.0155 | 0.73991 | 0.95016 | 0.96347 | 0.75836 | 0.39305 | 82.5303 | 0.62408 | 8.0094 | 6227.3008
1692 | 0.764 | 27 | 0.90505 | 0.14663 | 0.13576 | 0.65211 | 0.91085 | 111 | 0.86227 | 1.1402 | 0.55025 | 0.87146 | 0.68961 | 0.64033 | 0.88126 | 120.1577 | 0.21821 | 4.9172 | 7398.5895
1693 | 0.69541 | 26 | 0.7101 | 0.10674 | 0.7544 | 0.72991 | 0.044042 | 102 | 0.19382 | 0.98236 | 0.28465 | 0.78482 | 0.32649 | 0.53308 | 0.37452 | 81.5082 | 0.75645 | 9.3731 | 6032.5913
1694 | 0.58837 | 25 | 0.0785 | 0.028018 | 0.12237 | 0.64947 | 0.45453 | 106 | 0.25079 | 0.99369 | 0.44517 | 0.83509 | 0.31838 | 0.53017 | 0.80168 | 111.4333 | 0.64259 | 8.1836 | 6114.1953
1695 | 0.80617 | 27 | 0.36702 | 0.062198 | 0.69832 | 0.72232 | 0.41592 | 106 | 0.22408 | 0.98856 | 0.042207 | 0.67117 | 0.93457 | 0.73751 | 0.63849 | 97.9296 | 0.66996 | 8.4498 | 6461.1497
1696 | 0.24476 | 23 | 0.86414 | 0.13616 | 0.62305 | 0.71317 | 0.89376 | 111 | 0.44085 | 1.0288 | 0.030366 | 0.66036 | 0.18867 | 0.47718 | 0.035379 | 59.4046 | 0.94275 | 12.2719 | 5581.7873
1697 | 0.61042 | 26 | 0.43989 | 0.070372 | 0.35808 | 0.68463 | 0.20464 | 104 | 0.41329 | 1.0234 | 0.21486 | 0.76057 | 0.67411 | 0.6359 | 0.9266 | 126.5379 | 0.61431 | 7.919 | 6527.8709
1698 | 0.23243 | 23 | 0.95187 | 0.162 | 0.076537 | 0.63912 | 0.40322 | 106 | 0.79484 | 1.116 | 0.9679 | 1.1122 | 0.0085443 | 0.33771 | 0.43648 | 84.9891 | 0.86105 | 10.75 | 6177.7444
1699 | 0.44172 | 25 | 0.50824 | 0.078538 | 0.71338 | 0.72429 | 0.89234 | 111 | 0.079455 | 0.95273 | 0.99215 | 1.1566 | 0.9403 | 0.7412 | 0.38112 | 81.8705 | 0.13941 | 4.3318 | 6867.3307
1700 | 0.065254 | 22 | 0.32346 | 0.057535 | 0.48733 | 0.69873 | 0.26834 | 104 | 0.53108 | 1.0474 | 0.20255 | 0.7559 | 0.004763 | 0.32815 | 0.74609 | 106.3615 | 0.1663 | 4.5467 | 5304.4831
1701 | 0.04198 | 21 | 0.23721 | 0.048704 | 0.17368 | 0.65894 | 0.39111 | 105 | 0.56141 | 1.0541 | 0.74266 | 0.95148 | 0.67145 | 0.63515 | 0.60439 | 95.529 | 0.71006 | 8.8606 | 5987.143
1702 | 0.4101 | 25 | 0.46946 | 0.073841 | 0.22454 | 0.66701 | 0.86579 | 111 | 0.52475 | 1.0461 | 0.01842 | 0.64702 | 0.66111 | 0.63226 | 0.73367 | 105.3067 | 0.68834 | 8.6348 | 6283.7648
1703 | 0.12203 | 22 | 0.3696 | 0.062479 | 0.3697 | 0.68599 | 0.26443 | 104 | 0.37902 | 1.0169 | 0.63793 | 0.90522 | 0.17139 | 0.46888 | 0.060121 | 62.2597 | 0.019451 | 2.871 | 5476.6226
1704 | 0.70551 | 26 | 0.97264 | 0.17135 | 0.99232 | 0.78761 | 0.17435 | 104 | 0.51188 | 1.0433 | 0.79528 | 0.97834 | 0.93772 | 0.73952 | 0.23599 | 74.2896 | 0.96123 | 12.7551 | 6970.5442
1705 | 0.67453 | 26 | 0.71641 | 0.10776 | 0.26786 | 0.67319 | 0.59724 | 107 | 0.33269 | 1.0084 | 0.36897 | 0.81084 | 0.79889 | 0.67538 | 0.44843 | 85.682 | 0.88799 | 11.1841 | 6603.1923
1706 | 0.55401 | 25 | 0.63098 | 0.094783 | 0.20977 | 0.66477 | 0.026334 | 101 | 0.40955 | 1.0227 | 0.99898 | 1.1844 | 0.16944 | 0.46792 | 0.77382 | 108.8135 | 0.13885 | 4.3271 | 6541.7245
1707 | 0.27855 | 24 | 0.35558 | 0.060958 | 0.61186 | 0.71189 | 0.71269 | 108 | 0.1113 | 0.96241 | 0.90082 | 1.0457 | 0.36309 | 0.5458 | 0.91222 | 124.3419 | 0.72065 | 8.9738 | 6318.7717
1708 | 0.11506 | 22 | 0.86921 | 0.13736 | 0.43143 | 0.69289 | 0.63922 | 108 | 0.62541 | 1.069 | 0.56157 | 0.87562 | 0.76788 | 0.66463 | 0.97076 | 135.1919 | 0.2365 | 5.0373 | 6491.9317
1709 | 0.93966 | 28 | 0.12031 | 0.034686 | 0.74183 | 0.72814 | 0.40563 | 106 | 0.089086 | 0.95584 | 0.59161 | 0.88693 | 0.81612 | 0.68171 | 0.88287 | 120.3607 | 0.24041 | 5.0629 | 6780.8103
1710 | 0.45762 | 25 | 0.93987 | 0.15753 | 0.035625 | 0.62669 | 0.1142 | 103 | 0.2034 | 0.98437 | 0.13123 | 0.72549 | 0.98817 | 0.78493 | 0.77591 | 109.0041 | 0.9737 | 13.1511 | 6754.6769
1711 | 0.23735 | 23 | 0.85333 | 0.13367 | 0.64535 | 0.71578 | 0.75642 | 109 | 0.041421 | 0.93808 | 0.57159 | 0.87935 | 0.76028 | 0.6621 | 0.66492 | 99.8694 | 0.59853 | 7.7756 | 6180.4104
1712 | 0.50579 | 25 | 0.99274 | 0.18524 | 0.30997 | 0.67874 | 0.21546 | 104 | 0.19797 | 0.98324 | 0.31261 | 0.79368 | 0.36617 | 0.54684 | 0.20218 | 72.4821 | 0.84664 | 10.535 | 6174.8811
1713 | 0.20035 | 23 | 0.27674 | 0.052698 | 0.0050588 | 0.61006 | 0.45381 | 106 | 0.60037 | 1.063 | 0.68266 | 0.92403 | 0.34702 | 0.5403 | 0.50873 | 89.2999 | 0.3654 | 5.9171 | 6103.7582
1714 | 0.92956 | 28 | 0.45042 | 0.071597 | 0.52579 | 0.70261 | 0.6219 | 107 | 0.28241 | 0.99942 | 0.2641 | 0.77802 | 0.58491 | 0.61198 | 0.076129 | 63.7958 | 0.052112 | 3.4256 | 6390.4195
1715 | 0.084782 | 22 | 0.54024 | 0.082557 | 0.68347 | 0.72044 | 0.18925 | 104 | 0.033986 | 0.93449 | 0.96415 | 1.1072 | 0.40544 | 0.55974 | 0.60081 | 95.2831 | 0.044973 | 3.3244 | 5919.7544
1716 | 0.98766 | 29 | 0.3151 | 0.056658 | 0.96072 | 0.77197 | 0.51663 | 106 | 0.23609 | 0.9909 | 0.84329 | 1.0061 | 0.89833 | 0.71717 | 0.70312 | 102.8133 | 0.2366 | 5.038 | 7197.4771
1717 | 0.10821 | 22 | 0.09206 | 0.030341 | 0.32068 | 0.68008 | 0.85024 | 110 | 0.96842 | 1.1974 | 0.43601 | 0.83209 | 0.9539 | 0.75076 | 0.78401 | 109.7514 | 0.43964 | 6.4649 | 6563.0415
1718 | 0.28467 | 24 | 0.32976 | 0.0582 | 0.82845 | 0.74142 | 0.30418 | 105 | 0.27906 | 0.99883 | 0.36751 | 0.81039 | 0.3739 | 0.54943 | 0.6573 | 99.3023 | 0.67766 | 8.5267 | 5884.909
1719 | 0.28282 | 24 | 0.71007 | 0.10674 | 0.028649 | 0.62394 | 0.16898 | 104 | 0.89317 | 1.1533 | 0.17899 | 0.74655 | 0.92663 | 0.73265 | 0.74296 | 106.0934 | 0.56627 | 7.491 | 6793.9799
1720 | 0.55857 | 25 | 0.37135 | 0.06267 | 0.70108 | 0.72268 | 0.4685 | 106 | 0.98559 | 1.2145 | 0.48922 | 0.84988 | 0.059395 | 0.39941 | 0.82401 | 113.6689 | 0.15453 | 4.4549 | 6250.9305
1721 | 0.23509 | 23 | 0.93715 | 0.15658 | 0.038675 | 0.62781 | 0.30868 | 105 | 0.85595 | 1.1377 | 0.7338 | 0.94724 | 0.75584 | 0.66065 | 0.57856 | 93.7793 | 0.95098 | 12.4755 | 6803.6685
1722 | 0.93953 | 28 | 0.58583 | 0.088532 | 0.68063 | 0.72008 | 0.25701 | 104 | 0.0030759 | 0.91038 | 0.24177 | 0.77033 | 0.37458 | 0.54966 | 0.15183 | 69.4825 | 0.20855 | 4.8519 | 6041.0986
1723 | 0.096512 | 22 | 0.2711 | 0.052125 | 0.97691 | 0.77851 | 0.12328 | 103 | 0.10459 | 0.9605 | 0.2262 | 0.76475 | 0.47992 | 0.58259 | 0.77094 | 108.5515 | 0.19271 | 4.7415 | 5517.1471
1724 | 0.90377 | 28 | 0.48547 | 0.075759 | 0.96788 | 0.77466 | 0.74017 | 109 | 0.41591 | 1.0239 | 0.59883 | 0.88971 | 0.63646 | 0.62556 | 0.92676 | 126.5633 | 0.35679 | 5.8557 | 6919.4407
1725 | 0.085008 | 22 | 0.13947 | 0.037346 | 0.10331 | 0.64545 | 0.19649 | 104 | 0.88191 | 1.1483 | 0.55389 | 0.87279 | 0.16226 | 0.46432 | 0.881 | 120.1247 | 0.88977 | 11.2145 | 5985.1238
1726 | 0.19504 | 23 | 0.34733 | 0.060071 | 0.066793 | 0.63655 | 0.47209 | 106 | 0.29068 | 1.0009 | 0.79035 | 0.97569 | 0.095456 | 0.42603 | 0.24829 | 74.9142 | 0.77409 | 9.5808 | 5736.432
1727 | 0.61364 | 26 | 0.78582 | 0.11984 | 0.46656 | 0.6966 | 0.87187 | 111 | 0.33518 | 1.0088 | 0.683 | 0.92417 | 0.94782 | 0.74633 | 0.017273 | 56.5714 | 0.91603 | 11.696 | 6845.6208
1728 | 0.40182 | 24 | 0.55402 | 0.084331 | 0.44451 | 0.69429 | 0.98354 | 113 | 0.91946 | 1.166 | 0.15475 | 0.73627 | 0.43356 | 0.5686 | 0.016281 | 56.3799 | 0.77732 | 9.6196 | 6170.8801
1729 | 0.10549 | 22 | 0.69575 | 0.10446 | 0.71693 | 0.72476 | 0.3034 | 105 | 0.28982 | 1.0007 | 0.23535 | 0.76806 | 0.61075 | 0.61879 | 0.31684 | 78.4201 | 0.70439 | 8.8009 | 5725.5548
1730 | 0.39062 | 24 | 0.85502 | 0.13405 | 0.35353 | 0.68409 | 0.62606 | 108 | 0.44316 | 1.0293 | 0.28709 | 0.78561 | 0.097195 | 0.42717 | 0.88213 | 120.2681 | 0.70929 | 8.8525 | 6041.8525
1731 | 0.34577 | 24 | 0.83488 | 0.12962 | 0.11817 | 0.64862 | 0.39381 | 105 | 0.43842 | 1.0283 | 0.65246 | 0.91119 | 0.090546 | 0.42275 | 0.17305 | 70.7995 | 0.68916 | 8.6431 | 5937.3047
1732 | 0.19065 | 23 | 0.12624 | 0.035531 | 0.43446 | 0.69322 | 0.54399 | 107 | 0.76163 | 1.1056 | 0.35199 | 0.80564 | 0.29918 | 0.52312 | 0.45204 | 85.8931 | 0.14356 | 4.3662 | 5846.5992
1733 | 0.055356 | 22 | 0.10499 | 0.032403 | 0.8431 | 0.74398 | 0.7172 | 108 | 0.094584 | 0.95754 | 0.18372 | 0.74848 | 0.27823 | 0.51517 | 0.26495 | 75.7511 | 0.1815 | 4.6605 | 5259.7661
1734 | 0.19816 | 23 | 0.67705 | 0.10157 | 0.36552 | 0.6855 | 0.17204 | 104 | 0.72041 | 1.0936 | 0.89138 | 1.0385 | 0.81567 | 0.68154 | 0.51717 | 89.8231 | 0.66071 | 8.3587 | 6625.9759
1735 | 0.98128 | 29 | 0.063754 | 0.025249 | 0.17875 | 0.65979 | 0.75892 | 109 | 0.30745 | 1.0038 | 0.51855 | 0.86008 | 0.36831 | 0.54756 | 0.18558 | 71.5393 | 0.027909 | 3.0433 | 6533.6986
1736 | 0.59714 | 26 | 0.22873 | 0.047825 | 0.36443 | 0.68537 | 0.18017 | 104 | 0.37182 | 1.0156 | 0.13648 | 0.72798 | 0.73634 | 0.65441 | 0.79761 | 111.0397 | 0.41001 | 6.2422 | 6362.647
1737 | 0.72149 | 26 | 0.79336 | 0.12127 | 0.27916 | 0.67472 | 0.042512 | 102 | 0.90582 | 1.1592 | 0.76432 | 0.96217 | 0.57847 | 0.61025 | 0.49525 | 88.4725 | 0.64839 | 8.2391 | 6992.6725
1738 | 0.035522 | 21 | 0.76726 | 0.11644 | 0.06934 | 0.63724 | 0.55056 | 107 | 0.79833 | 1.1172 | 0.57643 | 0.88116 | 0.16695 | 0.46668 | 0.79405 | 110.6984 | 0.4142 | 6.2734 | 5946.5556
1739 | 0.70073 | 26 | 0.67201 | 0.1008 | 0.36987 | 0.68601 | 0.84399 | 110 | 0.61846 | 1.0673 | 0.029139 | 0.65913 | 0.58468 | 0.61191 | 0.68314 | 101.251 | 0.64745 | 8.2301 | 6440.7403
1740 | 0.59319 | 25 | 0.91689 | 0.15007 | 0.075926 | 0.63897 | 0.98848 | 114 | 0.010993 | 0.91962 | 0.85438 | 1.0131 | 0.31199 | 0.52785 | 0.99886 | 147.0744 | 0.89484 | 11.3027 | 6743.316
1741 | 0.58568 | 25 | 0.3821 | 0.063849 | 0.33894 | 0.68233 | 0.25838 | 104 | 0.62009 | 1.0677 | 0.52431 | 0.86212 | 0.45037 | 0.57375 | 0.60356 | 95.4718 | 0.7671 | 9.4976 | 6343.1349
1742 | 0.12165 | 22 | 0.4021 | 0.066071 | 0.87103 | 0.74921 | 0.084768 | 103 | 0.082299 | 0.95367 | 0.54851 | 0.87082 | 0.034992 | 0.37631 | 0.79429 | 110.7211 | 0.616 | 7.9346 | 5363.9918
1743 | 0.60275 | 26 | 0.86211 | 0.13568 | 0.85503 | 0.74615 | 0.78617 | 109 | 0.035252 | 0.93513 | 0.23621 | 0.76836 | 0.90375 | 0.71995 | 0.68142 | 101.1188 | 0.0048967 | 2.437 | 6474.5825
1744 | 0.46043 | 25 | 0.11321 | 0.033646 | 0.055493 | 0.63331 | 0.6064 | 107 | 0.25055 | 0.99364 | 0.095662 | 0.70714 | 0.045763 | 0.38726 | 0.88814 | 121.0353 | 0.37428 | 5.9809 | 5728.734
1745 | 0.2321 | 23 | 0.55493 | 0.084449 | 0.15059 | 0.65488 | 0.59375 | 107 | 0.62071 | 1.0678 | 0.76623 | 0.96314 | 0.44096 | 0.57088 | 0.1862 | 71.5756 | 0.4823 | 6.7963 | 6169.0774
1746 | 0.29519 | 24 | 0.31426 | 0.05657 | 0.87075 | 0.74916 | 0.090708 | 103 | 0.028356 | 0.9315 | 0.40042 | 0.82066 | 0.95445 | 0.75118 | 0.026691 | 58.1687 | 0.67947 | 8.5448 | 5901.5107
1747 | 0.91915 | 28 | 0.57137 | 0.086603 | 0.09995 | 0.64471 | 0.29446 | 105 | 0.41123 | 1.023 | 0.69808 | 0.93082 | 0.39117 | 0.55513 | 0.77129 | 108.5837 | 0.41422 | 6.2735 | 6883.9902
1748 | 0.028487 | 21 | 0.58021 | 0.087779 | 0.45498 | 0.69539 | 0.73786 | 109 | 0.60602 | 1.0643 | 0.60284 | 0.89126 | 0.053691 | 0.39452 | 0.6284 | 97.2077 | 0.33184 | 5.6801 | 5552.7366
1749 | 0.28036 | 24 | 0.079982 | 0.028281 | 0.88921 | 0.75293 | 0.69675 | 108 | 0.66206 | 1.078 | 0.021861 | 0.65122 | 0.88056 | 0.70855 | 0.072569 | 63.4693 | 0.55709 | 7.412 | 5906.1348
1750 | 0.96606 | 29 | 0.2784 | 0.052867 | 0.58218 | 0.70859 | 0.55738 | 107 | 0.27075 | 0.99735 | 0.15624 | 0.73693 | 0.97067 | 0.76477 | 0.87553 | 119.4464 | 0.7955 | 9.844 | 7063.8697
1751 | 0.1194 | 22 | 0.83813 | 0.13031 | 0.25358 | 0.67121 | 0.46906 | 106 | 0.36818 | 1.0149 | 0.12218 | 0.72109 | 0.48695 | 0.58466 | 0.20337 | 72.5482 | 0.5181 | 7.085 | 5724.8789
1752 | 0.38653 | 24 | 0.89496 | 0.14387 | 0.57793 | 0.70812 | 0.61369 | 107 | 0.24423 | 0.99246 | 0.3801 | 0.81429 | 0.32075 | 0.53102 | 0.65954 | 99.4681 | 0.030407 | 3.089 | 6065.9573
1753 | 0.9268 | 28 | 0.3831 | 0.063959 | 0.73826 | 0.72765 | 0.76424 | 109 | 0.082867 | 0.95385 | 0.8488 | 1.0095 | 0.14868 | 0.45729 | 0.486 | 87.9116 | 0.96034 | 12.7294 | 6413.8908
1754 | 0.7288 | 26 | 0.76799 | 0.11657 | 0.94553 | 0.76699 | 0.67749 | 108 | 0.6939 | 1.0863 | 0.18834 | 0.75034 | 0.157 | 0.46163 | 0.36106 | 80.7753 | 0.341 | 5.7442 | 6070.0381
1755 | 0.16931 | 23 | 0.50293 | 0.077885 | 0.49385 | 0.69938 | 0.94631 | 112 | 0.64027 | 1.0726 | 0.42703 | 0.82917 | 0.62117 | 0.62151 | 0.32238 | 78.711 | 0.19511 | 4.7585 | 6121.6355
1756 | 0.9695 | 29 | 0.71233 | 0.1071 | 0.50069 | 0.70007 | 0.89016 | 111 | 0.37797 | 1.0167 | 0.58159 | 0.88311 | 0.035121 | 0.37645 | 0.22853 | 73.9024 | 0.32298 | 5.6185 | 6340.2238
1757 | 0.075564 | 22 | 0.66404 | 0.099606 | 0.10389 | 0.64558 | 0.0032057 | 100 | 0.14714 | 0.97176 | 0.090347 | 0.70412 | 0.17101 | 0.46869 | 0.16522 | 70.3238 | 0.69225 | 8.6749 | 5326.0839
1758 | 0.41412 | 25 | 0.064352 | 0.025368 | 0.092152 | 0.64293 | 0.00060213 | 100 | 0.083821 | 0.95416 | 0.078486 | 0.69705 | 0.19324 | 0.47932 | 0.43529 | 84.9206 | 0.61504 | 7.9257 | 5553.9132
1759 | 0.54633 | 25 | 0.59036 | 0.089143 | 0.81628 | 0.73938 | 0.3152 | 105 | 0.50431 | 1.0417 | 0.37414 | 0.81243 | 0.68346 | 0.63856 | 0.50579 | 89.1182 | 0.5766 | 7.5809 | 6301.7528
1760 | 0.080869 | 22 | 0.022837 | 0.015112 | 0.40218 | 0.68969 | 0.34897 | 105 | 0.36275 | 1.0139 | 0.42052 | 0.82707 | 0.37232 | 0.54891 | 0.7231 | 104.4285 | 0.41299 | 6.2643 | 5658.6205
1761 | 0.49788 | 25 | 0.070901 | 0.026627 | 0.93892 | 0.76505 | 0.10661 | 103 | 0.13288 | 0.9682 | 0.04976 | 0.67727 | 0.90999 | 0.72324 | 0.90023 | 122.6456 | 0.93719 | 12.1426 | 6095.7259
1762 | 0.87446 | 27 | 0.12135 | 0.034835 | 0.63514 | 0.71458 | 0.3951 | 105 | 0.50581 | 1.0421 | 0.54649 | 0.87009 | 0.30866 | 0.52663 | 0.53795 | 91.1329 | 0.9959 | 14.2697 | 6367.9829
1763 | 0.092382 | 22 | 0.74849 | 0.11314 | 0.074345 | 0.63856 | 0.69941 | 108 | 0.73437 | 1.0975 | 0.98296 | 1.136 | 0.65739 | 0.63124 | 0.3125 | 78.1932 | 0.86235 | 10.7699 | 6574.3554
1764 | 0.32658 | 24 | 0.65737 | 0.098615 | 0.98534 | 0.78288 | 0.31333 | 105 | 0.33031 | 1.0079 | 0.84861 | 1.0094 | 0.25086 | 0.50431 | 0.1958 | 72.1247 | 0.050116 | 3.398 | 5947.5086
1765 | 0.36999 | 24 | 0.91945 | 0.15084 | 0.37485 | 0.68659 | 0.064874 | 102 | 0.088062 | 0.95552 | 0.98619 | 1.1424 | 0.74083 | 0.65583 | 0.32638 | 78.9217 | 0.62535 | 8.0212 | 6608.6746
1766 | 0.67526 | 26 | 0.49064 | 0.076385 | 0.23232 | 0.66816 | 0.2953 | 105 | 0.10906 | 0.96178 | 0.50727 | 0.85612 | 0.25135 | 0.50451 | 0.29181 | 77.1206 | 0.083322 | 3.8026 | 6026.8237
1767 | 0.84654 | 27 | 0.3448 | 0.0598 | 0.216 | 0.66573 | 0.25237 | 104 | 0.5723 | 1.0565 | 0.30223 | 0.79044 | 0.52237 | 0.59483 | 0.68027 | 101.0311 | 0.60928 | 7.873 | 6571.9799
1768 | 0.99945 | 30 | 0.37859 | 0.063463 | 0.00054929 | 0.60331 | 0.20908 | 104 | 0.78819 | 1.1139 | 0.25803 | 0.77596 | 0.37265 | 0.54902 | 0.79282 | 110.5813 | 0.33132 | 5.6764 | 7139.7867
1769 | 0.88197 | 28 | 0.25613 | 0.050614 | 0.23928 | 0.66918 | 0.12217 | 103 | 0.51801 | 1.0446 | 0.88046 | 1.0306 | 0.11684 | 0.43944 | 0.6259 | 97.0306 | 0.1483 | 4.4049 | 6580.1617
1770 | 0.21642 | 23 | 0.14744 | 0.038398 | 0.37739 | 0.68688 | 0.48608 | 106 | 0.00034366 | 0.90347 | 0.016884 | 0.64501 | 0.38734 | 0.55388 | 0.90018 | 122.6389 | 0.43152 | 6.4034 | 5508.8242
1771 | 0.83314 | 27 | 0.62901 | 0.094503 | 0.65256 | 0.71664 | 0.059805 | 102 | 0.19696 | 0.98303 | 0.97507 | 1.1227 | 0.54646 | 0.60155 | 0.5971 | 95.0293 | 0.080073 | 3.7672 | 6853.7037
1772 | 0.80601 | 27 | 0.61482 | 0.092504 | 0.46229 | 0.69615 | 0.48419 | 106 | 0.5928 | 1.0612 | 0.9712 | 1.1169 | 0.22889 | 0.49516 | 0.13673 | 68.4887 | 0.74415 | 9.2328 | 6718.0529
1773 | 0.85065 | 27 | 0.29814 | 0.054894 | 0.32539 | 0.68067 | 0.24374 | 104 | 0.26132 | 0.99564 | 0.21808 | 0.76177 | 0.61775 | 0.62061 | 0.58202 | 94.0101 | 0.35517 | 5.8442 | 6363.586
1774 | 0.99497 | 29 | 0.11284 | 0.033592 | 0.76526 | 0.73148 | 0.73621 | 109 | 0.17001 | 0.97714 | 0.23097 | 0.76648 | 0.5372 | 0.59898 | 0.69593 | 102.2448 | 0.022101 | 2.9284 | 6507.7768
1775 | 0.079938 | 22 | 0.3446 | 0.059779 | 0.50513 | 0.70051 | 0.56237 | 107 | 0.28932 | 1.0006 | 0.46123 | 0.84041 | 0.15865 | 0.46248 | 0.29587 | 77.3295 | 0.96365 | 12.8262 | 5493.4062
1776 | 0.67994 | 26 | 0.3529 | 0.06067 | 0.67089 | 0.71887 | 0.73471 | 109 | 0.90995 | 1.1612 | 0.15508 | 0.73641 | 0.78896 | 0.67185 | 0.62844 | 97.211 | 0.50978 | 7.017 | 6735.167
1777 | 0.35201 | 24 | 0.60988 | 0.091817 | 0.61554 | 0.71231 | 0.93426 | 112 | 0.28199 | 0.99935 | 0.096661 | 0.7077 | 0.14718 | 0.45649 | 0.46867 | 86.8734 | 0.9434 | 12.2875 | 5713.8642
1778 | 0.13129 | 23 | 0.44052 | 0.070446 | 0.12229 | 0.64945 | 0.005474 | 101 | 0.62458 | 1.0688 | 0.29567 | 0.78836 | 0.116 | 0.43893 | 0.89286 | 121.6525 | 0.93753 | 12.1503 | 5874.912
1779 | 0.53032 | 25 | 0.23051 | 0.048011 | 0.62296 | 0.71316 | 0.17701 | 104 | 0.487 | 1.0381 | 0.79154 | 0.97632 | 0.60921 | 0.61839 | 0.99054 | 141.5746 | 0.53525 | 7.2272 | 6682.6207
1780 | 0.85103 | 27 | 0.44813 | 0.071329 | 0.60707 | 0.71135 | 0.77915 | 109 | 0.0058235 | 0.91428 | 0.054945 | 0.6812 | 0.20696 | 0.48558 | 0.061738 | 62.4236 | 0.32583 | 5.6383 | 5670.2402
1781 | 0.72857 | 26 | 0.65666 | 0.09851 | 0.92193 | 0.76049 | 0.3427 | 105 | 0.84239 | 1.1326 | 0.75296 | 0.9565 | 0.091237 | 0.42321 | 0.15648 | 69.7791 | 0.40207 | 6.1835 | 6224.5052
1782 | 0.25579 | 24 | 0.87918 | 0.13979 | 0.83009 | 0.74171 | 0.76615 | 109 | 0.8483 | 1.1348 | 0.43747 | 0.83257 | 0.69581 | 0.64214 | 0.8068 | 111.9346 | 0.77868 | 9.6361 | 6680.012
1783 | 0.88585 | 28 | 0.34244 | 0.059548 | 0.76845 | 0.73195 | 0.2666 | 104 | 0.6332 | 1.0708 | 0.083086 | 0.69985 | 0.74242 | 0.65633 | 0.95999 | 132.6768 | 0.86529 | 10.8153 | 6804.5688
1784 | 0.60745 | 26 | 0.48506 | 0.075709 | 0.19483 | 0.66242 | 0.26233 | 104 | 0.26589 | 0.99647 | 0.70501 | 0.93392 | 0.17031 | 0.46835 | 0.83989 | 115.3468 | 0.0051292 | 2.4473 | 6306.6619
1785 | 0.51002 | 25 | 0.31317 | 0.056456 | 0.33313 | 0.68162 | 0.71661 | 108 | 0.30934 | 1.0042 | 0.43207 | 0.83081 | 0.69296 | 0.6413 | 0.56002 | 92.556 | 0.96537 | 12.8783 | 6339.6898
1786 | 0.027935 | 21 | 0.61985 | 0.093209 | 0.017301 | 0.6186 | 0.43829 | 106 | 0.16981 | 0.97709 | 0.9572 | 1.0986 | 0.91948 | 0.72849 | 0.82958 | 114.2483 | 0.37915 | 6.0161 | 6438.0014
1787 | 0.51523 | 25 | 0.61086 | 0.091952 | 0.48444 | 0.69843 | 0.2127 | 104 | 0.94722 | 1.182 | 0.68567 | 0.92534 | 0.66156 | 0.63239 | 0.79872 | 111.1468 | 0.54817 | 7.336 | 6919.951
1788 | 0.18586 | 23 | 0.90666 | 0.14708 | 0.24496 | 0.66999 | 0.96001 | 113 | 0.68938 | 1.0851 | 0.9856 | 1.1412 | 0.65513 | 0.63062 | 0.11586 | 67.0193 | 0.68159 | 8.5662 | 6744.3493
1789 | 0.14438 | 23 | 0.43504 | 0.069812 | 0.61049 | 0.71174 | 0.10505 | 103 | 0.36758 | 1.0148 | 0.67271 | 0.91973 | 0.90989 | 0.72319 | 0.1498 | 69.3517 | 0.68272 | 8.5777 | 6163.013
1790 | 0.59326 | 25 | 0.0094908 | 0.0097421 | 0.45157 | 0.69503 | 0.60157 | 107 | 0.82026 | 1.1246 | 0.69561 | 0.92972 | 0.49447 | 0.58685 | 0.54845 | 91.8052 | 0.03433 | 3.1571 | 6440.1594
1791 | 0.84373 | 27 | 0.69407 | 0.1042 | 0.35301 | 0.68403 | 0.67459 | 108 | 0.88046 | 1.1477 | 0.64764 | 0.9092 | 0.80765 | 0.67856 | 0.31142 | 78.1366 | 0.33567 | 5.7069 | 7182.9236
1792 | 0.068441 | 22 | 0.80025 | 0.12259 | 0.44903 | 0.69477 | 0.73244 | 109 | 0.23516 | 0.99072 | 0.78559 | 0.97316 | 0.30067 | 0.52368 | 0.38949 | 82.333 | 0.1964 | 4.7676 | 5895.7872
1793 | 0.58119 | 25 | 0.14678 | 0.038312 | 0.13783 | 0.6525 | 0.31579 | 105 | 0.21676 | 0.9871 | 0.55606 | 0.87359 | 0.31601 | 0.52931 | 0.20415 | 72.5917 | 0.33089 | 5.6735 | 5952.6942
1794 | 0.52859 | 25 | 0.247 | 0.049699 | 0.38536 | 0.68779 | 0.080702 | 102 | 0.24653 | 0.99289 | 0.1682 | 0.74207 | 0.87834 | 0.70752 | 0.78529 | 109.871 | 0.65951 | 8.347 | 6286.6712
1795 | 0.99802 | 30 | 0.47371 | 0.074347 | 0.95399 | 0.76966 | 0.77362 | 109 | 0.38648 | 1.0183 | 0.62122 | 0.89849 | 0.098925 | 0.4283 | 0.31304 | 78.2211 | 0.85276 | 10.6249 | 6478.1864
1796 | 0.21387 | 23 | 0.063172 | 0.025134 | 0.15939 | 0.65646 | 0.69682 | 108 | 0.89653 | 1.1549 | 0.98416 | 1.1383 | 0.9984 | 0.80712 | 0.053465 | 61.5613 | 0.31254 | 5.5464 | 6964.2094
1797 | 0.16134 | 23 | 0.57331 | 0.08686 | 0.56748 | 0.70699 | 0.77961 | 109 | 0.10797 | 0.96147 | 0.89632 | 1.0423 | 0.8074 | 0.67847 | 0.4667 | 86.7566 | 0.048432 | 3.3744 | 6304.5032
1798 | 0.057388 | 22 | 0.16184 | 0.040229 | 0.60295 | 0.71089 | 0.46252 | 106 | 0.78423 | 1.1126 | 0.47918 | 0.84645 | 0.93259 | 0.73627 | 0.54625 | 91.6638 | 0.93948 | 12.195 | 6239.8851
1799 | 0.69441 | 26 | 0.96259 | 0.1665 | 0.1652 | 0.65748 | 0.31371 | 105 | 0.40637 | 1.0221 | 0.28549 | 0.78509 | 0.63397 | 0.62489 | 0.043641 | 60.4452 | 0.59158 | 7.7134 | 6469.5406
1800 | 0.51371 | 25 | 0.11662 | 0.03415 | 0.012347 | 0.61571 | 0.015428 | 101 | 0.11298 | 0.96288 | 0.61698 | 0.89681 | 0.38531 | 0.55321 | 0.94527 | 129.7395 | 0.65947 | 8.3465 | 6281.4844
1801 | 0.73697 | 26 | 0.80926 | 0.12436 | 0.87517 | 0.75003 | 0.055918 | 102 | 0.34234 | 1.0101 | 0.98956 | 1.1499 | 0.27921 | 0.51555 | 0.037958 | 59.7414 | 0.97613 | 13.2386 | 6487.7598
1802 | 0.40451 | 24 | 0.46894 | 0.073779 | 0.18212 | 0.66035 | 0.34046 | 105 | 0.98018 | 1.2084 | 0.95098 | 1.0915 | 0.52509 | 0.59559 | 0.82212 | 113.4751 | 0.034273 | 3.1561 | 6981.6674
1803 | 0.92425 | 28 | 0.37104 | 0.062636 | 0.37976 | 0.68715 | 0.34523 | 105 | 0.27574 | 0.99824 | 0.9639 | 1.1069 | 0.3298 | 0.53426 | 0.68188 | 101.1543 | 0.95451 | 12.5682 | 6922.9673
1804 | 0.67548 | 26 | 0.40938 | 0.066889 | 0.60945 | 0.71162 | 0.25064 | 104 | 0.71898 | 1.0932 | 0.11907 | 0.71953 | 0.22237 | 0.49236 | 0.92246 | 125.8846 | 0.12792 | 4.2336 | 6241.9492
1805 | 0.59583 | 26 | 0.29148 | 0.054208 | 0.10151 | 0.64506 | 0.0607 | 102 | 0.54742 | 1.051 | 0.7883 | 0.9746 | 0.9968 | 0.80174 | 0.26615 | 75.812 | 0.75378 | 9.3423 | 7067.0504
1806 | 0.13041 | 23 | 0.90872 | 0.14767 | 0.96579 | 0.77384 | 0.4481 | 106 | 0.14485 | 0.9712 | 0.81902 | 0.99159 | 0.26285 | 0.50914 | 0.16336 | 70.209 | 0.30352 | 5.4847 | 5868.6453
1807 | 0.76484 | 27 | 0.55381 | 0.084303 | 0.22491 | 0.66707 | 0.20059 | 104 | 0.153 | 0.97318 | 0.1907 | 0.75127 | 0.44492 | 0.57209 | 0.27861 | 76.4446 | 0.069597 | 3.6475 | 6174.9165
1808 | 0.69449 | 26 | 0.27428 | 0.052448 | 0.73793 | 0.7276 | 0.35026 | 105 | 0.73045 | 1.0964 | 0.25185 | 0.77385 | 0.57144 | 0.60836 | 0.13251 | 68.2011 | 0.55506 | 7.3946 | 6267.0581
1809 | 0.27388 | 24 | 0.61623 | 0.092701 | 0.67018 | 0.71878 | 0.37113 | 105 | 0.016705 | 0.92418 | 0.60569 | 0.89237 | 0.66106 | 0.63225 | 0.017197 | 56.5568 | 0.34512 | 5.7732 | 5883.4095
1810 | 0.095219 | 22 | 0.25533 | 0.050534 | 0.21767 | 0.66598 | 0.29022 | 105 | 0.666 | 1.079 | 0.10132 | 0.71026 | 0.18558 | 0.47573 | 0.66145 | 99.6104 | 0.76962 | 9.5274 | 5599.9103
1811 | 0.60886 | 26 | 0.8247 | 0.12748 | 0.669 | 0.71864 | 0.55451 | 107 | 0.58904 | 1.0604 | 0.54565 | 0.86978 | 0.62323 | 0.62205 | 0.15137 | 69.4535 | 0.58571 | 7.6612 | 6574.2399
1812 | 0.60576 | 26 | 0.29566 | 0.054638 | 0.29745 | 0.67713 | 0.313 | 105 | 0.36151 | 1.0136 | 0.85323 | 1.0123 | 0.13688 | 0.45092 | 0.89745 | 122.2668 | 0.0094994 | 2.6087 | 6388.6038
1813 | 0.77949 | 27 | 0.58526 | 0.088455 | 0.6497 | 0.7163 | 0.045834 | 102 | 0.60692 | 1.0645 | 0.25463 | 0.7748 | 0.87551 | 0.70622 | 0.3509 | 80.227 | 0.69348 | 8.6875 | 6674.7543
1814 | 0.38621 | 24 | 0.89928 | 0.14503 | 0.14343 | 0.65356 | 0.82697 | 110 | 0.50237 | 1.0413 | 0.57499 | 0.88062 | 0.57002 | 0.60798 | 0.99299 | 142.7498 | 0.931 | 12.005 | 6779.2998
1815 | 0.008044 | 21 | 0.27805 | 0.052832 | 0.2712 | 0.67365 | 0.016634 | 101 | 0.54914 | 1.0514 | 0.79521 | 0.9783 | 0.31064 | 0.52735 | 0.62285 | 96.8152 | 0.42548 | 6.3578 | 5753.4676
1816 | 0.91805 | 28 | 0.18719 | 0.043266 | 0.45757 | 0.69566 | 0.48269 | 106 | 0.60288 | 1.0636 | 0.65589 | 0.91262 | 0.95435 | 0.75109 | 0.67747 | 100.8165 | 0.59385 | 7.7337 | 7256.2555
1817 | 0.055878 | 22 | 0.24048 | 0.049038 | 0.34915 | 0.68356 | 0.59717 | 107 | 0.34866 | 1.0113 | 0.62059 | 0.89824 | 0.25935 | 0.50774 | 0.60296 | 95.4309 | 0.51601 | 7.0678 | 5721.397
1818 | 0.22321 | 23 | 0.44951 | 0.071491 | 0.17898 | 0.65983 | 0.22775 | 104 | 0.62951 | 1.07 | 0.564 | 0.87652 | 0.76964 | 0.66522 | 0.14702 | 69.1714 | 0.43165 | 6.4043 | 6176.1715
1819 | 0.63561 | 26 | 0.079172 | 0.028138 | 0.14247 | 0.65338 | 0.33922 | 105 | 0.68785 | 1.0847 | 0.75264 | 0.95635 | 0.79111 | 0.67261 | 0.84948 | 116.4013 | 0.020223 | 2.8881 | 6947.511
1820 | 0.72455 | 26 | 0.36871 | 0.062382 | 0.31837 | 0.6798 | 0.52428 | 107 | 0.28203 | 0.99935 | 0.3335 | 0.80005 | 0.33255 | 0.53524 | 0.59508 | 94.8917 | 0.015573 | 2.7793 | 6155.6774
1821 | 0.58381 | 25 | 0.85139 | 0.13323 | 0.39034 | 0.68836 | 0.45836 | 106 | 0.29174 | 1.0011 | 0.0504 | 0.67777 | 0.69622 | 0.64226 | 0.21477 | 73.1715 | 0.51811 | 7.0851 | 6121.2542
1822 | 0.45421 | 25 | 0.10826 | 0.032903 | 0.93043 | 0.7627 | 0.071239 | 102 | 0.13945 | 0.96986 | 0.18635 | 0.74954 | 0.16988 | 0.46813 | 0.62817 | 97.1917 | 0.65583 | 8.311 | 5584.0424
1823 | 0.85373 | 27 | 0.26391 | 0.051397 | 0.93445 | 0.76379 | 0.50376 | 106 | 0.25539 | 0.99455 | 0.62229 | 0.89892 | 0.80979 | 0.67935 | 0.3064 | 77.8752 | 0.92226 | 11.8209 | 6554.8574
1824 | 0.953 | 28 | 0.72838 | 0.10973 | 0.69355 | 0.72171 | 0.84926 | 110 | 0.5018 | 1.0412 | 0.99012 | 1.1513 | 0.59515 | 0.6147 | 0.28806 | 76.9275 | 0.7844 | 9.7059 | 7294.9222
1825 | 0.052767 | 22 | 0.49608 | 0.077046 | 0.94724 | 0.76752 | 0.31079 | 105 | 0.0066405 | 0.91525 | 0.03282 | 0.66276 | 0.74423 | 0.65691 | 0.86063 | 117.6692 | 0.23437 | 5.0234 | 5560.8283
1826 | 0.806 | 27 | 0.24352 | 0.049348 | 0.89621 | 0.75444 | 0.40917 | 106 | 0.8805 | 1.1477 | 0.89092 | 1.0382 | 0.97293 | 0.76694 | 0.53529 | 90.9636 | 0.89839 | 11.3655 | 7444.3582
1827 | 0.9932 | 29 | 0.75734 | 0.11468 | 0.80371 | 0.73734 | 0.13869 | 103 | 0.96484 | 1.1945 | 0.20821 | 0.75807 | 0.047821 | 0.3892 | 0.27609 | 76.316 | 0.1345 | 4.2903 | 6439.0325
1828 | 0.5046 | 25 | 0.088477 | 0.029745 | 0.32802 | 0.681 | 0.64494 | 108 | 0.24758 | 0.99309 | 0.69459 | 0.92927 | 0.62194 | 0.62171 | 0.060664 | 62.315 | 0.97283 | 13.1207 | 6207.6321
1829 | 0.24351 | 23 | 0.040346 | 0.020086 | 0.11968 | 0.64892 | 0.1493 | 103 | 0.83575 | 1.1301 | 0.42569 | 0.82874 | 0.19267 | 0.47905 | 0.17916 | 71.1634 | 0.5272 | 7.1601 | 5750.0213
1830 | 0.42506 | 25 | 0.90772 | 0.14739 | 0.8333 | 0.74226 | 0.18801 | 104 | 0.14774 | 0.97191 | 0.45832 | 0.83944 | 0.3595 | 0.54458 | 0.88675 | 120.8554 | 0.098692 | 3.9619 | 6254.9248
1831 | 0.36689 | 24 | 0.57057 | 0.086497 | 0.58945 | 0.70939 | 0.60147 | 107 | 0.94373 | 1.1798 | 0.69221 | 0.92821 | 0.80258 | 0.67671 | 0.14365 | 68.9507 | 0.28964 | 5.3903 | 6656.4359
1832 | 0.32174 | 24 | 0.78843 | 0.12033 | 0.28975 | 0.67613 | 0.52791 | 107 | 0.61305 | 1.066 | 0.46924 | 0.84309 | 0.6653 | 0.63343 | 0.55008 | 91.9107 | 0.72409 | 9.011 | 6448.5286
1833 | 0.24784 | 24 | 0.76183 | 0.11547 | 0.018614 | 0.61929 | 0.84477 | 110 | 0.24478 | 0.99256 | 0.68888 | 0.92674 | 0.20695 | 0.48557 | 0.27708 | 76.3664 | 0.75517 | 9.3584 | 6101.7571
1834 | 0.081136 | 22 | 0.075361 | 0.027452 | 0.70205 | 0.72281 | 0.31859 | 105 | 0.57706 | 1.0576 | 0.10283 | 0.71109 | 0.82851 | 0.68645 | 0.096751 | 65.5524 | 0.39827 | 6.1555 | 5636.9258
1835 | 0.23217 | 23 | 0.87708 | 0.13927 | 0.27555 | 0.67424 | 0.29221 | 105 | 0.22263 | 0.98827 | 0.059045 | 0.68417 | 0.37037 | 0.54825 | 0.29545 | 77.3082 | 0.20612 | 4.8353 | 5705.7466
1836 | 0.30789 | 24 | 0.47019 | 0.073927 | 0.83312 | 0.74223 | 0.27819 | 105 | 0.4566 | 1.0319 | 0.40897 | 0.82337 | 0.067984 | 0.40636 | 0.86471 | 118.1455 | 0.35683 | 5.856 | 5794.8995
1837 | 0.21667 | 23 | 0.76654 | 0.11631 | 0.65827 | 0.71733 | 0.58103 | 107 | 0.75229 | 1.1028 | 0.5392 | 0.86745 | 0.63704 | 0.62571 | 0.078656 | 64.0228 | 0.94167 | 12.2464 | 6208.727
1838 | 0.078716 | 22 | 0.25289 | 0.05029 | 0.55872 | 0.70605 | 0.28627 | 105 | 0.65734 | 1.0768 | 0.44235 | 0.83416 | 0.12282 | 0.44296 | 0.8448 | 115.8824 | 0.87214 | 10.9231 | 5717.5728
1839 | 0.98133 | 29 | 0.12049 | 0.034712 | 0.033848 | 0.62602 | 0.50059 | 106 | 0.063345 | 0.94709 | 0.33125 | 0.79937 | 0.50916 | 0.59107 | 0.40064 | 82.9537 | 0.45711 | 6.599 | 6504.8517
1840 | 0.79049 | 27 | 0.087352 | 0.029555 | 0.91943 | 0.75986 | 0.49182 | 106 | 0.46989 | 1.0346 | 0.89437 | 1.0408 | 0.88135 | 0.70892 | 0.56916 | 93.1554 | 0.30088 | 5.4666 | 6953.7291
1841 | 0.41092 | 25 | 0.68696 | 0.10309 | 0.72395 | 0.7257 | 0.63219 | 108 | 0.84479 | 1.1335 | 0.85669 | 1.0145 | 0.29495 | 0.52154 | 0.39521 | 82.6508 | 0.48753 | 6.8378 | 6567.5838
1842 | 0.47284 | 25 | 0.86496 | 0.13635 | 0.88615 | 0.75228 | 0.85047 | 110 | 0.72991 | 1.0963 | 0.0070117 | 0.62901 | 0.91058 | 0.72357 | 0.6324 | 97.4932 | 0.7667 | 9.4928 | 6529.5633
1843 | 0.051604 | 22 | 0.93632 | 0.15629 | 0.74546 | 0.72865 | 0.48554 | 106 | 0.38564 | 1.0181 | 0.093202 | 0.70576 | 0.81127 | 0.6799 | 0.3364 | 79.4521 | 0.087772 | 3.8502 | 5886.4451
1844 | 0.28381 | 24 | 0.21548 | 0.046419 | 0.17993 | 0.65999 | 0.5081 | 106 | 0.83851 | 1.1311 | 0.1321 | 0.7259 | 0.70463 | 0.64473 | 0.37819 | 81.7094 | 0.30734 | 5.5108 | 6229.2588
1845 | 0.87706 | 28 | 0.12444 | 0.035276 | 0.36653 | 0.68562 | 0.645 | 108 | 0.27137 | 0.99746 | 0.089609 | 0.7037 | 0.13958 | 0.4524 | 0.51588 | 89.7428 | 0.94477 | 12.3205 | 6040.6306
1846 | 0.18884 | 23 | 0.41274 | 0.067268 | 0.92299 | 0.76076 | 0.64989 | 108 | 0.079593 | 0.95278 | 0.22692 | 0.76502 | 0.38338 | 0.55257 | 0.14273 | 68.8896 | 0.29762 | 5.4444 | 5484.1346
1847 | 0.91596 | 28 | 0.9078 | 0.14741 | 0.8396 | 0.74336 | 0.38997 | 105 | 0.56166 | 1.0542 | 0.34949 | 0.80488 | 0.79256 | 0.67312 | 0.93565 | 128.0316 | 0.70058 | 8.761 | 7133.204
1848 | 0.24028 | 23 | 0.061896 | 0.024879 | 0.36678 | 0.68565 | 0.66191 | 108 | 0.80823 | 1.1205 | 0.85494 | 1.0134 | 0.81928 | 0.68291 | 0.66567 | 99.9255 | 0.59781 | 7.7692 | 6578.5093
1849 | 0.033322 | 21 | 0.94678 | 0.16004 | 0.83165 | 0.74197 | 0.57038 | 107 | 0.07205 | 0.95022 | 0.72666 | 0.94387 | 0.61769 | 0.6206 | 0.14936 | 69.3232 | 0.80029 | 9.9046 | 5804.8048
1850 | 0.11636 | 22 | 0.69436 | 0.10424 | 0.8415 | 0.7437 | 0.94431 | 112 | 0.061204 | 0.94628 | 0.38687 | 0.8164 | 0.67099 | 0.63502 | 0.74895 | 106.6075 | 0.56607 | 7.4893 | 5898.8781
1851 | 0.19211 | 23 | 0.03712 | 0.019267 | 0.64714 | 0.71599 | 0.041108 | 102 | 0.56559 | 1.055 | 0.99951 | 1.1891 | 0.82644 | 0.68565 | 0.82598 | 113.8731 | 0.15501 | 4.4587 | 6615.8367
1852 | 0.48353 | 25 | 0.57577 | 0.087186 | 0.6181 | 0.7126 | 0.18799 | 104 | 0.13317 | 0.96827 | 0.10894 | 0.71434 | 0.99707 | 0.80254 | 0.25763 | 75.3824 | 0.92451 | 11.8672 | 6287.5983
1853 | 0.73923 | 26 | 0.18865 | 0.043434 | 0.40188 | 0.68965 | 0.80231 | 110 | 0.89224 | 1.1529 | 0.57455 | 0.88045 | 0.32501 | 0.53255 | 0.49443 | 88.4224 | 0.78506 | 9.714 | 6585.7107
1854 | 0.17953 | 23 | 0.98799 | 0.18102 | 0.21567 | 0.66568 | 0.26596 | 104 | 0.99889 | 1.2401 | 0.92847 | 1.069 | 0.50264 | 0.5892 | 0.55902 | 92.4904 | 0.12123 | 4.1744 | 6948.039
1855 | 0.7723 | 27 | 0.70991 | 0.10671 | 0.089094 | 0.64221 | 0.66532 | 108 | 0.61623 | 1.0668 | 0.31752 | 0.7952 | 0.86017 | 0.69941 | 0.529 | 90.5652 | 0.43029 | 6.3941 | 6982.3047
1856 | 0.65224 | 26 | 0.98745 | 0.1806 | 0.68454 | 0.72057 | 0.71174 | 108 | 0.64558 | 1.0739 | 0.80432 | 0.98329 | 0.38749 | 0.55393 | 0.53092 | 90.6862 | 0.50434 | 6.9728 | 6841.2114
1857 | 0.16634 | 23 | 0.95171 | 0.16194 | 0.16363 | 0.65721 | 0.19401 | 104 | 0.17269 | 0.97775 | 0.82528 | 0.99522 | 0.062469 | 0.40195 | 0.56624 | 92.9632 | 0.40859 | 6.2317 | 5925.6744
1858 | 0.29274 | 24 | 0.66288 | 0.099433 | 0.89041 | 0.75318 | 0.95246 | 112 | 0.33291 | 1.0084 | 0.041269 | 0.67037 | 0.84764 | 0.69412 | 0.79878 | 111.1526 | 0.40136 | 6.1782 | 6196.2604
1859 | 0.20825 | 23 | 0.4007 | 0.065915 | 0.76289 | 0.73114 | 0.71317 | 108 | 0.027197 | 0.93085 | 0.016217 | 0.64411 | 0.88401 | 0.71017 | 0.4116 | 83.5693 | 0.74596 | 9.2532 | 5674.0311
1860 | 0.25295 | 24 | 0.80413 | 0.12334 | 0.49447 | 0.69945 | 0.39611 | 105 | 0.62263 | 1.0683 | 0.84243 | 1.0055 | 0.76596 | 0.66399 | 0.29702 | 77.3892 | 0.6032 | 7.8178 | 6620.8368
1861 | 0.63275 | 26 | 0.81467 | 0.12543 | 0.72683 | 0.72609 | 0.38583 | 105 | 0.54673 | 1.0508 | 0.13776 | 0.72857 | 0.65153 | 0.62963 | 0.019642 | 57.0074 | 0.52155 | 7.1134 | 6249.4509
1862 | 0.33254 | 24 | 0.11404 | 0.03377 | 0.36899 | 0.68591 | 0.2819 | 105 | 0.91349 | 1.163 | 0.42391 | 0.82816 | 0.93619 | 0.73854 | 0.50321 | 88.9596 | 0.89728 | 11.3457 | 6636.4042
1863 | 0.17286 | 23 | 0.10378 | 0.032215 | 0.7215 | 0.72537 | 0.6387 | 108 | 0.73017 | 1.0963 | 0.10215 | 0.71072 | 0.11464 | 0.43811 | 0.4865 | 87.9418 | 0.91229 | 11.6233 | 5556.3757
1864 | 0.57041 | 25 | 0.42351 | 0.068491 | 0.70658 | 0.72339 | 0.45769 | 106 | 0.85757 | 1.1384 | 0.63615 | 0.9045 | 0.23037 | 0.49579 | 0.80181 | 111.4458 | 0.59991 | 7.7881 | 6418.3201
1865 | 0.90698 | 28 | 0.61661 | 0.092754 | 0.2599 | 0.6721 | 0.34458 | 105 | 0.91007 | 1.1613 | 0.98309 | 1.1363 | 0.08243 | 0.41712 | 0.14151 | 68.809 | 0.65143 | 8.2684 | 6914.1826
1866 | 0.36046 | 24 | 0.7581 | 0.11481 | 0.46608 | 0.69655 | 0.20766 | 104 | 0.51343 | 1.0437 | 0.96444 | 1.1076 | 0.13269 | 0.44859 | 0.33135 | 79.184 | 0.099772 | 3.9726 | 6183.3685
1867 | 0.02811 | 21 | 0.56791 | 0.086146 | 0.92574 | 0.76146 | 0.12496 | 103 | 0.042722 | 0.93867 | 0.97743 | 1.1264 | 0.73928 | 0.65533 | 0.50182 | 88.8742 | 0.18857 | 4.7119 | 5918.1878
1868 | 0.24314 | 23 | 0.62959 | 0.094586 | 0.50583 | 0.70058 | 0.93892 | 112 | 0.045689 | 0.93999 | 0.40823 | 0.82314 | 0.3868 | 0.5537 | 0.87154 | 118.9609 | 0.58416 | 7.6475 | 5961.5698
1869 | 0.30237 | 24 | 0.68259 | 0.10242 | 0.35885 | 0.68472 | 0.45017 | 106 | 0.72984 | 1.0962 | 0.89465 | 1.041 | 0.40958 | 0.56106 | 0.24663 | 74.831 | 0.72692 | 9.0418 | 6473.312
1870 | 0.36611 | 24 | 0.85819 | 0.13478 | 0.1003 | 0.64479 | 0.094706 | 103 | 0.65361 | 1.0759 | 0.28811 | 0.78594 | 0.60254 | 0.61664 | 0.10872 | 66.4867 | 0.33454 | 5.699 | 6240.645
1871 | 0.097564 | 22 | 0.36269 | 0.061727 | 0.36776 | 0.68576 | 0.94923 | 112 | 0.37413 | 1.016 | 0.55967 | 0.87492 | 0.91283 | 0.72479 | 0.14567 | 69.0836 | 0.20292 | 4.8132 | 6054.444
1872 | 0.032015 | 21 | 0.19822 | 0.044522 | 0.86459 | 0.74796 | 0.08725 | 103 | 0.92865 | 1.171 | 0.37035 | 0.81126 | 0.1784 | 0.47229 | 0.91546 | 124.8196 | 0.87682 | 10.9983 | 5735.1195
1873 | 0.54319 | 25 | 0.60781 | 0.09153 | 0.32113 | 0.68014 | 0.091318 | 103 | 0.324 | 1.0068 | 0.28835 | 0.78602 | 0.52995 | 0.59696 | 0.80872 | 112.1234 | 0.37524 | 5.9879 | 6273.018
1874 | 0.10476 | 22 | 0.24438 | 0.049435 | 0.33564 | 0.68193 | 0.86613 | 111 | 0.441 | 1.0288 | 0.8773 | 1.0284 | 0.7562 | 0.66077 | 0.12366 | 67.5827 | 0.86516 | 10.8132 | 6145.5982
1875 | 0.86748 | 27 | 0.69493 | 0.10433 | 0.53604 | 0.70367 | 0.17195 | 104 | 0.73638 | 1.0981 | 0.9392 | 1.0792 | 0.5164 | 0.59314 | 0.25295 | 75.1479 | 0.34797 | 5.7932 | 7006.1862
1876 | 0.36796 | 24 | 0.43988 | 0.070371 | 0.96118 | 0.77214 | 0.91894 | 112 | 0.20912 | 0.98555 | 0.050687 | 0.67799 | 0.90744 | 0.72189 | 0.12628 | 67.7679 | 0.11235 | 4.0932 | 5893.9399
1877 | 0.29084 | 24 | 0.32121 | 0.057298 | 0.049112 | 0.63134 | 0.40123 | 106 | 0.25809 | 0.99504 | 0.01287 | 0.6393 | 0.97117 | 0.76525 | 0.017363 | 56.5884 | 0.92719 | 11.9235 | 6005.4883
1878 | 0.92305 | 28 | 0.24576 | 0.049575 | 0.52036 | 0.70206 | 0.84979 | 110 | 0.50074 | 1.041 | 0.32845 | 0.79853 | 0.43032 | 0.56759 | 0.78893 | 110.2132 | 0.057131 | 3.4927 | 6644.4673
1879 | 0.16898 | 23 | 0.72997 | 0.11 | 0.97892 | 0.77947 | 0.43561 | 106 | 0.14508 | 0.97126 | 0.038422 | 0.6679 | 0.98341 | 0.77846 | 0.88692 | 120.8773 | 0.2955 | 5.43 | 6088.7489
1880 | 0.076222 | 22 | 0.68015 | 0.10204 | 0.67865 | 0.71983 | 0.98867 | 114 | 0.83029 | 1.1281 | 0.23313 | 0.76726 | 0.30575 | 0.52556 | 0.32389 | 78.7902 | 0.71294 | 8.8912 | 5891.3294
1881 | 0.95179 | 28 | 0.97439 | 0.17228 | 0.4572 | 0.69562 | 0.29158 | 105 | 0.20924 | 0.98558 | 0.87905 | 1.0296 | 0.93094 | 0.73525 | 0.03461 | 59.3019 | 0.68436 | 8.5943 | 7280.5093
1882 | 0.4526 | 25 | 0.30348 | 0.055447 | 0.77308 | 0.73263 | 0.84128 | 110 | 0.99558 | 1.2303 | 0.75847 | 0.95924 | 0.82528 | 0.6852 | 0.29964 | 77.5246 | 0.29209 | 5.4069 | 6983.6396
1883 | 0.23101 | 23 | 0.10407 | 0.032259 | 0.62492 | 0.71339 | 0.16873 | 104 | 0.74097 | 1.0995 | 0.052569 | 0.67942 | 0.89068 | 0.71337 | 0.17206 | 70.7403 | 0.96363 | 12.8255 | 5937.8329
1884 | 0.47502 | 25 | 0.3261 | 0.057814 | 0.47447 | 0.69741 | 0.31347 | 105 | 0.37431 | 1.016 | 0.38785 | 0.8167 | 0.18895 | 0.47732 | 0.77822 | 109.2155 | 0.37962 | 6.0195 | 5997.0524
1885 | 0.40695 | 25 | 0.91784 | 0.15035 | 0.60291 | 0.71088 | 0.091918 | 103 | 0.19605 | 0.98284 | 0.53981 | 0.86767 | 0.2819 | 0.51658 | 0.048264 | 60.9846 | 0.97869 | 13.3356 | 6040.7364
1886 | 0.21583 | 23 | 0.36109 | 0.061554 | 0.09544 | 0.64369 | 0.014852 | 101 | 0.55118 | 1.0518 | 0.20124 | 0.7554 | 0.45779 | 0.576 | 0.25085 | 75.0426 | 0.46973 | 6.6973 | 5798.3741
1887 | 0.24283 | 23 | 0.18915 | 0.043492 | 0.92623 | 0.76159 | 0.588 | 107 | 0.63128 | 1.0704 | 0.52999 | 0.86414 | 0.84384 | 0.69256 | 0.036774 | 59.5883 | 0.071901 | 3.6746 | 5989.9008
1888 | 0.72411 | 26 | 0.19606 | 0.044279 | 0.98017 | 0.78009 | 0.44359 | 106 | 0.68303 | 1.0835 | 0.31454 | 0.79428 | 0.82714 | 0.68592 | 0.066344 | 62.8786 | 0.48518 | 6.8191 | 6326.2804
1889 | 0.47112 | 25 | 0.20159 | 0.044898 | 0.88709 | 0.75248 | 0.41685 | 106 | 0.78734 | 1.1136 | 0.43277 | 0.83103 | 0.72085 | 0.64961 | 0.9385 | 128.5229 | 0.54469 | 7.3064 | 6600.0855
1890 | 0.043588 | 21 | 0.20525 | 0.045304 | 0.81346 | 0.73892 | 0.80014 | 110 | 0.89729 | 1.1552 | 0.60897 | 0.89365 | 0.52649 | 0.59599 | 0.91598 | 124.8966 | 0.45619 | 6.5919 | 6113.4306
1891 | 0.10006 | 22 | 0.3223 | 0.057413 | 0.18338 | 0.66056 | 0.23024 | 104 | 0.26474 | 0.99626 | 0.57422 | 0.88033 | 0.18119 | 0.47364 | 0.97031 | 135.0766 | 0.62126 | 7.9831 | 5827.115
1892 | 0.41035 | 25 | 0.86077 | 0.13537 | 0.6377 | 0.71488 | 0.28358 | 105 | 0.70202 | 1.0885 | 0.34259 | 0.80279 | 0.92762 | 0.73324 | 0.28056 | 76.5439 | 0.69795 | 8.7337 | 6673.8851
1893 | 0.62081 | 26 | 0.83195 | 0.129 | 0.55298 | 0.70545 | 0.36826 | 105 | 0.3277 | 1.0075 | 0.43491 | 0.83173 | 0.20603 | 0.48516 | 0.93171 | 127.3686 | 0.4241 | 6.3474 | 6379.3828
1894 | 0.23574 | 23 | 0.32223 | 0.057405 | 0.2241 | 0.66695 | 0.94907 | 112 | 0.54263 | 1.05 | 0.41524 | 0.82538 | 0.42622 | 0.56631 | 0.79357 | 110.6523 | 0.82221 | 10.1925 | 6136.9463
1895 | 0.63014 | 26 | 0.7607 | 0.11527 | 0.59117 | 0.70958 | 0.76893 | 109 | 0.46632 | 1.0339 | 0.67956 | 0.92268 | 0.80867 | 0.67894 | 0.96655 | 134.1601 | 0.4166 | 6.2912 | 7054.3714
1896 | 0.98281 | 29 | 0.35661 | 0.061069 | 0.2268 | 0.66735 | 0.53389 | 107 | 0.3563 | 1.0127 | 0.75981 | 0.95991 | 0.86639 | 0.70212 | 0.38672 | 82.1797 | 0.41368 | 6.2695 | 7232.3141
1897 | 0.21681 | 23 | 0.76941 | 0.11683 | 0.93574 | 0.76415 | 0.91365 | 111 | 0.051152 | 0.94231 | 0.54867 | 0.87088 | 0.77681 | 0.66765 | 0.29815 | 77.4474 | 0.16131 | 4.5082 | 5990.3558
1898 | 0.099518 | 22 | 0.15191 | 0.038976 | 0.86868 | 0.74875 | 0.25014 | 104 | 0.11599 | 0.96372 | 0.86587 | 1.0206 | 0.71912 | 0.64909 | 0.93846 | 128.5157 | 0.29061 | 5.3969 | 6085.2537
1899 | 0.43836 | 25 | 0.019322 | 0.0139 | 0.553 | 0.70545 | 0.16723 | 104 | 0.13719 | 0.96929 | 0.79659 | 0.97905 | 0.71334 | 0.64734 | 0.37147 | 81.3416 | 0.41623 | 6.2885 | 6230.9205
1900 | 0.38759 | 24 | 0.88859 | 0.14219 | 0.51558 | 0.70157 | 0.30684 | 105 | 0.15239 | 0.97303 | 0.4777 | 0.84595 | 0.85997 | 0.69932 | 0.03854 | 59.8158 | 0.51693 | 7.0754 | 6206.2556
1901 | 0.38683 | 24 | 0.62172 | 0.093471 | 0.13551 | 0.65206 | 0.57766 | 107 | 0.48021 | 1.0367 | 0.23867 | 0.76923 | 0.27156 | 0.51257 | 0.94801 | 130.2543 | 0.61919 | 7.964 | 6193.8344
1902 | 0.73535 | 26 | 0.053023 | 0.023027 | 0.028185 | 0.62374 | 0.093488 | 103 | 0.91716 | 1.1649 | 0.97416 | 1.1213 | 0.20703 | 0.48561 | 0.71733 | 103.9564 | 0.62834 | 8.049 | 6861.8079
1903 | 0.40759 | 25 | 0.3677 | 0.062272 | 0.93608 | 0.76425 | 0.80361 | 110 | 0.87494 | 1.1454 | 0.58648 | 0.88497 | 0.26136 | 0.50854 | 0.20573 | 72.679 | 0.46034 | 6.6241 | 6219.3833
1904 | 0.42875 | 25 | 0.20103 | 0.044836 | 0.34466 | 0.68302 | 0.77488 | 109 | 0.057985 | 0.94505 | 0.38301 | 0.81519 | 0.30317 | 0.52461 | 0.26557 | 75.7824 | 0.25495 | 5.1584 | 5806.7407
1905 | 0.49295 | 25 | 0.059328 | 0.024357 | 0.33761 | 0.68217 | 0.82381 | 110 | 0.89816 | 1.1556 | 0.62811 | 0.90125 | 0.15388 | 0.46002 | 0.23711 | 74.3471 | 0.78313 | 9.6903 | 6196.586
1906 | 0.30393 | 24 | 0.045766 | 0.021393 | 0.28263 | 0.67518 | 0.59792 | 107 | 0.40418 | 1.0217 | 0.49239 | 0.85096 | 0.75241 | 0.65953 | 0.52486 | 90.3046 | 0.46584 | 6.6669 | 6181.937
1907 | 0.10274 | 22 | 0.97028 | 0.17014 | 0.94113 | 0.76569 | 0.49422 | 106 | 0.60946 | 1.0651 | 0.31032 | 0.79297 | 0.2696 | 0.51181 | 0.12277 | 67.5189 | 0.42487 | 6.3532 | 5720.153
1908 | 0.61873 | 26 | 0.11794 | 0.034342 | 0.65838 | 0.71734 | 0.27175 | 105 | 0.45867 | 1.0324 | 0.59367 | 0.88772 | 0.51883 | 0.59382 | 0.35544 | 80.4715 | 0.77638 | 9.6083 | 6310.0831
1909 | 0.96182 | 29 | 0.48638 | 0.075868 | 0.19663 | 0.66271 | 0.12002 | 103 | 0.039427 | 0.93715 | 0.86114 | 1.0174 | 0.74247 | 0.65634 | 0.48165 | 87.6494 | 0.89559 | 11.3158 | 7052.4805
1910 | 0.92048 | 28 | 0.043704 | 0.020905 | 0.52336 | 0.70236 | 0.9092 | 111 | 0.43541 | 1.0277 | 0.66619 | 0.91695 | 0.24207 | 0.5007 | 0.73235 | 105.1963 | 0.66295 | 8.3806 | 6578.9521
1911 | 0.3617 | 24 | 0.88494 | 0.14125 | 0.49525 | 0.69952 | 0.88661 | 111 | 0.92345 | 1.1682 | 0.92244 | 1.0636 | 0.70988 | 0.6463 | 0.70985 | 103.3509 | 0.89607 | 11.3243 | 7142.2352
1912 | 0.90567 | 28 | 0.069526 | 0.026368 | 0.10704 | 0.64627 | 0.24469 | 104 | 0.63515 | 1.0713 | 0.30019 | 0.7898 | 0.93107 | 0.73533 | 0.075963 | 63.7807 | 0.54836 | 7.3375 | 6856.2769
1913 | 0.70856 | 26 | 0.18432 | 0.042932 | 0.83763 | 0.74301 | 0.87914 | 111 | 0.055027 | 0.94389 | 0.95331 | 1.0941 | 0.84625 | 0.69355 | 0.17802 | 71.0965 | 0.43649 | 6.441 | 6649.2147
1914 | 0.53969 | 25 | 0.10239 | 0.031998 | 0.69619 | 0.72205 | 0.38526 | 105 | 0.31785 | 1.0057 | 0.52393 | 0.86198 | 0.57645 | 0.60971 | 0.93133 | 127.3056 | 0.74266 | 9.216 | 6333.3376
1915 | 0.44263 | 25 | 0.98737 | 0.18053 | 0.25719 | 0.67172 | 0.89451 | 111 | 0.098314 | 0.95866 | 0.78818 | 0.97453 | 0.24241 | 0.50084 | 0.7742 | 108.848 | 0.69821 | 8.7364 | 6514.5346
1916 | 0.024676 | 21 | 0.48117 | 0.075241 | 0.49791 | 0.69979 | 0.81186 | 110 | 0.65171 | 1.0754 | 0.59881 | 0.8897 | 0.15167 | 0.45887 | 0.40559 | 83.2312 | 0.1965 | 4.7683 | 5594.777
1917 | 0.29585 | 24 | 0.076396 | 0.02764 | 0.72611 | 0.72599 | 0.66556 | 108 | 0.42637 | 1.026 | 0.66884 | 0.91808 | 0.84942 | 0.69486 | 0.12904 | 67.9608 | 0.2382 | 5.0484 | 6200.0308
1918 | 0.41835 | 25 | 0.17237 | 0.041518 | 0.54661 | 0.70477 | 0.4432 | 106 | 0.75801 | 1.1045 | 0.22427 | 0.76405 | 0.82197 | 0.68393 | 0.54015 | 91.2728 | 0.42586 | 6.3606 | 6429.404
1919 | 0.75806 | 27 | 0.14335 | 0.037862 | 0.99819 | 0.79399 | 0.92775 | 112 | 0.27034 | 0.99727 | 0.03771 | 0.66727 | 0.10625 | 0.43296 | 0.12567 | 67.725 | 0.86586 | 10.8241 | 5636.9543
1920 | 0.26171 | 24 | 0.083551 | 0.028905 | 0.10058 | 0.64485 | 0.88106 | 111 | 0.064925 | 0.94767 | 0.023224 | 0.65279 | 0.71149 | 0.64678 | 0.17317 | 70.807 | 0.2822 | 5.3401 | 5704.5782
1921 | 0.48803 | 25 | 0.21632 | 0.04651 | 0.9262 | 0.76158 | 0.081046 | 102 | 0.69188 | 1.0858 | 0.97964 | 1.1301 | 0.90109 | 0.71857 | 0.17424 | 70.871 | 0.77581 | 9.6014 | 6800.8358
1922 | 0.68814 | 26 | 0.67544 | 0.10133 | 0.77543 | 0.73298 | 0.17092 | 104 | 0.15326 | 0.97324 | 0.60414 | 0.89177 | 0.97111 | 0.76519 | 0.35743 | 80.5792 | 0.32894 | 5.6599 | 6649.1756
1923 | 0.59942 | 26 | 0.47652 | 0.074683 | 0.2695 | 0.67342 | 0.48027 | 106 | 0.042034 | 0.93836 | 0.53726 | 0.86675 | 0.51826 | 0.59366 | 0.37755 | 81.6746 | 0.26422 | 5.2198 | 6212.4155
1924 | 0.39386 | 24 | 0.7416 | 0.11195 | 0.26292 | 0.67252 | 0.97259 | 113 | 0.56447 | 1.0548 | 0.61216 | 0.89491 | 0.28378 | 0.5173 | 0.51646 | 89.7791 | 0.73781 | 9.1618 | 6286.6641
1925 | 6.8792e-05 | 20 | 0.37946 | 0.063559 | 0.48527 | 0.69852 | 0.025975 | 101 | 0.19129 | 0.98182 | 0.55849 | 0.87448 | 0.61595 | 0.62015 | 0.79334 | 110.631 | 0.09148 | 3.8888 | 5595.641
1926 | 0.89759 | 28 | 0.060046 | 0.024504 | 0.76824 | 0.73192 | 0.1433 | 103 | 0.36402 | 1.0141 | 0.46565 | 0.84189 | 0.75175 | 0.65932 | 0.85061 | 116.5273 | 0.14836 | 4.4054 | 6704.4488
1927 | 0.4754 | 25 | 0.87768 | 0.13942 | 0.37312 | 0.68638 | 0.98214 | 113 | 0.5463 | 1.0508 | 0.30242 | 0.7905 | 0.26966 | 0.51183 | 0.77584 | 108.9971 | 0.43128 | 6.4015 | 6390.3533
1928 | 0.84063 | 27 | 0.43027 | 0.069264 | 0.62497 | 0.71339 | 0.48119 | 106 | 0.76643 | 1.107 | 0.58738 | 0.88531 | 0.53589 | 0.59862 | 0.16379 | 70.2357 | 0.81682 | 10.1201 | 6675.3306
1929 | 0.050868 | 22 | 0.44485 | 0.070947 | 0.16333 | 0.65715 | 0.78004 | 109 | 0.80295 | 1.1187 | 0.44331 | 0.83448 | 0.97604 | 0.77008 | 0.62325 | 96.8434 | 0.53045 | 7.1871 | 6484.0118
1930 | 0.27105 | 24 | 0.055215 | 0.023498 | 0.40605 | 0.69012 | 0.50463 | 106 | 0.75055 | 1.1023 | 0.30195 | 0.79035 | 0.97664 | 0.77071 | 0.79985 | 111.2554 | 0.14776 | 4.4005 | 6571.7969
1931 | 0.94956 | 28 | 0.36435 | 0.061908 | 0.4849 | 0.69848 | 0.65127 | 108 | 0.17633 | 0.97856 | 0.74031 | 0.95035 | 0.52018 | 0.59421 | 0.25573 | 75.2869 | 0.353 | 5.8288 | 6640.1598
1932 | 0.47455 | 25 | 0.14326 | 0.03785 | 0.97442 | 0.77738 | 0.29898 | 105 | 0.86693 | 1.1421 | 0.023097 | 0.65265 | 0.62766 | 0.62322 | 0.65112 | 98.8472 | 0.55106 | 7.3605 | 6127.9402
1933 | 0.1688 | 23 | 0.24212 | 0.049206 | 0.036858 | 0.62715 | 0.47013 | 106 | 0.09357 | 0.95723 | 0.40344 | 0.82162 | 0.78681 | 0.6711 | 0.30651 | 77.8808 | 0.46275 | 6.6428 | 5931.2886
1934 | 0.85971 | 27 | 0.67191 | 0.10079 | 0.30584 | 0.67821 | 0.86084 | 110 | 0.24052 | 0.99175 | 0.52933 | 0.8639 | 0.013319 | 0.34708 | 0.5032 | 88.9589 | 0.82 | 10.1627 | 6051.6853
1935 | 0.93228 | 28 | 0.90691 | 0.14715 | 0.15062 | 0.65489 | 0.028362 | 101 | 0.1544 | 0.97351 | 0.24254 | 0.7706 | 0.032333 | 0.37335 | 0.89981 | 122.588 | 0.9195 | 11.7651 | 6277.6601
1936 | 0.20207 | 23 | 0.84239 | 0.13124 | 0.51616 | 0.70163 | 0.34985 | 105 | 0.69703 | 1.0872 | 0.85361 | 1.0126 | 0.38588 | 0.5534 | 0.90844 | 123.7944 | 0.33082 | 5.673 | 6509.6
1937 | 0.87145 | 27 | 0.87504 | 0.13877 | 0.25254 | 0.67107 | 0.036674 | 102 | 0.49092 | 1.0389 | 0.70848 | 0.93549 | 0.25841 | 0.50736 | 0.075932 | 63.7779 | 0.33434 | 5.6976 | 6486.0156
1938 | 0.44108 | 25 | 0.74092 | 0.11184 | 0.26836 | 0.67326 | 0.069476 | 102 | 0.18434 | 0.98032 | 0.60127 | 0.89065 | 0.30374 | 0.52482 | 0.15005 | 69.368 | 0.72178 | 8.986 | 6056.9246
1939 | 0.14726 | 23 | 0.66437 | 0.099657 | 0.49095 | 0.69909 | 0.09685 | 103 | 0.42688 | 1.0261 | 0.19211 | 0.75183 | 0.43024 | 0.56757 | 0.57353 | 93.4443 | 0.63771 | 8.1373 | 5859.714
1940 | 0.6251 | 26 | 0.63181 | 0.094901 | 0.46013 | 0.69593 | 0.32948 | 105 | 0.43774 | 1.0282 | 0.26838 | 0.77946 | 0.32937 | 0.53411 | 0.0079198 | 54.4497 | 0.36913 | 5.9439 | 6027.0558
1941 | 0.77659 | 27 | 0.94008 | 0.1576 | 0.33905 | 0.68235 | 0.4065 | 106 | 0.17199 | 0.97759 | 0.81064 | 0.98682 | 0.41298 | 0.56215 | 0.62637 | 97.0637 | 0.21237 | 4.878 | 6790.4838
1942 | 0.16953 | 23 | 0.16446 | 0.040553 | 0.96027 | 0.77181 | 0.59667 | 107 | 0.66469 | 1.0787 | 0.27282 | 0.78094 | 0.27953 | 0.51567 | 0.97188 | 135.4778 | 0.59275 | 7.7239 | 5929.4027
1943 | 0.63601 | 26 | 0.46264 | 0.073032 | 0.12824 | 0.65064 | 0.74205 | 109 | 0.7694 | 1.108 | 0.36127 | 0.80847 | 0.7165 | 0.64829 | 0.54913 | 91.8492 | 0.63156 | 8.0792 | 6774.8457
1944 | 0.011709 | 21 | 0.18856 | 0.043424 | 0.085028 | 0.64124 | 0.17468 | 104 | 0.19872 | 0.9834 | 0.043245 | 0.67204 | 0.76827 | 0.66476 | 0.12833 | 67.9116 | 0.016145 | 2.7935 | 5390.9699
1945 | 0.4511 | 25 | 0.23856 | 0.048843 | 0.90154 | 0.75563 | 0.16046 | 103 | 0.10212 | 0.95978 | 0.018381 | 0.64697 | 0.16989 | 0.46814 | 0.38876 | 82.2927 | 0.13582 | 4.3015 | 5391.309
1946 | 0.83315 | 27 | 0.82866 | 0.1283 | 0.37179 | 0.68623 | 0.28425 | 105 | 0.40207 | 1.0213 | 0.98567 | 1.1414 | 0.47443 | 0.58097 | 0.47065 | 86.9909 | 0.79804 | 9.8761 | 7064.5761
1947 | 0.15485 | 23 | 0.26908 | 0.05192 | 0.2977 | 0.67716 | 0.55948 | 107 | 0.0064534 | 0.91503 | 0.4198 | 0.82684 | 0.83433 | 0.68874 | 0.69242 | 101.9704 | 0.25612 | 5.1662 | 5950.4827
1948 | 0.47976 | 25 | 0.8161 | 0.12572 | 0.28867 | 0.67598 | 0.89806 | 111 | 0.36138 | 1.0136 | 0.51102 | 0.85743 | 0.13263 | 0.44856 | 0.14154 | 68.8111 | 0.028542 | 3.055 | 6005.4488
1949 | 0.35818 | 24 | 0.89732 | 0.1445 | 0.3673 | 0.68571 | 0.50215 | 106 | 0.3931 | 1.0196 | 0.73843 | 0.94945 | 0.0075708 | 0.33549 | 0.61035 | 95.9411 | 0.80957 | 10.0245 | 5912.3998
1950 | 0.50462 | 25 | 0.69617 | 0.10453 | 0.64431 | 0.71566 | 0.67372 | 108 | 0.28549 | 0.99996 | 0.5093 | 0.85683 | 0.54219 | 0.60037 | 0.03707 | 59.6267 | 0.68372 | 8.5878 | 6156.5272
1951 | 0.22676 | 23 | 0.2573 | 0.050732 | 0.25569 | 0.67151 | 0.62854 | 108 | 0.78582 | 1.1131 | 0.95847 | 1.1002 | 0.014951 | 0.34988 | 0.42991 | 84.6115 | 0.8985 | 11.3675 | 5926.842
1952 | 0.41348 | 25 | 0.074704 | 0.027332 | 0.21804 | 0.66604 | 0.81392 | 110 | 0.53879 | 1.0491 | 0.1132 | 0.71655 | 0.06163 | 0.40127 | 0.37113 | 81.3231 | 0.62282 | 7.9976 | 5667.7916
1953 | 0.24743 | 24 | 0.31018 | 0.056144 | 0.50056 | 0.70006 | 0.29548 | 105 | 0.16094 | 0.97505 | 0.11812 | 0.71905 | 0.086702 | 0.42011 | 0.65003 | 98.7673 | 0.63515 | 8.113 | 5516.1792
1954 | 0.86669 | 27 | 0.87301 | 0.13828 | 0.24059 | 0.66937 | 0.11813 | 103 | 0.33206 | 1.0082 | 0.42687 | 0.82912 | 0.89846 | 0.71724 | 0.81467 | 112.7174 | 0.268 | 5.245 | 6996.585
1955 | 0.028982 | 21 | 0.67449 | 0.10118 | 0.069608 | 0.63731 | 0.67071 | 108 | 0.87799 | 1.1467 | 0.998 | 1.1781 | 0.58749 | 0.61266 | 0.029673 | 58.613 | 0.80369 | 9.9482 | 6385.1218
1956 | 0.68598 | 26 | 0.37037 | 0.062563 | 0.18768 | 0.66127 | 0.35827 | 105 | 0.36196 | 1.0137 | 0.24771 | 0.77241 | 0.86961 | 0.70355 | 0.64999 | 98.7646 | 0.27997 | 5.3251 | 6546.8619
1957 | 0.93677 | 28 | 0.98063 | 0.1759 | 0.99031 | 0.78608 | 0.31927 | 105 | 0.063495 | 0.94714 | 0.92094 | 1.0623 | 0.17437 | 0.47034 | 0.48792 | 88.0275 | 0.83067 | 10.3082 | 6619.9643
1958 | 0.36983 | 24 | 0.85169 | 0.1333 | 0.2144 | 0.66548 | 0.77983 | 109 | 0.7451 | 1.1007 | 0.81993 | 0.99211 | 0.41418 | 0.56253 | 0.93922 | 128.6486 | 0.53558 | 7.2299 | 6808.7438
1959 | 0.22471 | 23 | 0.36778 | 0.062281 | 0.30318 | 0.67787 | 0.84799 | 110 | 0.14629 | 0.97156 | 0.15906 | 0.73815 | 0.0090366 | 0.33878 | 0.60203 | 95.3668 | 0.23397 | 5.0208 | 5320.052
1960 | 0.24851 | 24 | 0.79445 | 0.12147 | 0.35451 | 0.6842 | 0.35327 | 105 | 0.49875 | 1.0406 | 0.4351 | 0.83179 | 0.24959 | 0.50379 | 0.97615 | 136.6247 | 0.29822 | 5.4485 | 6284.3708
1961 | 0.49022 | 25 | 0.69681 | 0.10463 | 0.52759 | 0.7028 | 0.086805 | 103 | 0.1784 | 0.97902 | 0.79294 | 0.97708 | 0.65723 | 0.63119 | 0.5752 | 93.5552 | 0.85886 | 10.7165 | 6488.9478
1962 | 0.094221 | 22 | 0.21145 | 0.045983 | 0.6936 | 0.72172 | 0.17028 | 104 | 0.1731 | 0.97784 | 0.258 | 0.77595 | 0.25228 | 0.50489 | 0.51778 | 89.8611 | 0.11376 | 4.1063 | 5392.2311
1963 | 0.73074 | 26 | 0.39527 | 0.065308 | 0.085049 | 0.64124 | 0.34081 | 105 | 0.78025 | 1.1113 | 0.059345 | 0.68439 | 0.15524 | 0.46072 | 0.7317 | 105.1421 | 0.75782 | 9.389 | 6192.1313
1964 | 0.30689 | 24 | 0.9404 | 0.15772 | 0.24469 | 0.66996 | 0.11686 | 103 | 0.74899 | 1.1018 | 0.16813 | 0.74204 | 0.95277 | 0.74991 | 0.5098 | 89.3657 | 0.37033 | 5.9525 | 6640.0064
1965 | 0.77411 | 27 | 0.54494 | 0.083159 | 0.49786 | 0.69979 | 0.45572 | 106 | 0.44221 | 1.0291 | 0.81691 | 0.99038 | 0.18703 | 0.47641 | 0.070118 | 63.2399 | 0.92003 | 11.7756 | 6380.6997
1966 | 0.5597 | 25 | 0.16882 | 0.041087 | 0.19568 | 0.66256 | 0.59339 | 107 | 0.25133 | 0.99379 | 0.22163 | 0.76308 | 0.82786 | 0.6862 | 0.5519 | 92.0281 | 0.00050913 | 2.1409 | 6233.0983
1967 | 0.52159 | 25 | 0.2277 | 0.047718 | 0.60834 | 0.71149 | 0.60712 | 107 | 0.31274 | 1.0048 | 0.66766 | 0.91758 | 0.43768 | 0.56987 | 0.23413 | 74.1936 | 0.13458 | 4.291 | 6107.1861
1968 | 0.71394 | 26 | 0.89744 | 0.14453 | 0.088167 | 0.64199 | 0.13332 | 103 | 0.23814 | 0.9913 | 0.59738 | 0.88915 | 0.55655 | 0.60432 | 0.23084 | 74.0228 | 0.66546 | 8.4053 | 6530.6214
1969 | 0.86466 | 27 | 0.80284 | 0.12309 | 0.63381 | 0.71442 | 0.9438 | 112 | 0.060976 | 0.9462 | 0.49777 | 0.85282 | 0.808 | 0.67869 | 0.75616 | 107.2352 | 0.84895 | 10.5688 | 6809.5765
1970 | 0.13273 | 23 | 0.16856 | 0.041056 | 0.52539 | 0.70257 | 0.41958 | 106 | 0.08582 | 0.95481 | 0.28738 | 0.7857 | 0.47426 | 0.58092 | 0.29139 | 77.0986 | 0.4423 | 6.4852 | 5598.3213
1971 | 0.38709 | 24 | 0.81856 | 0.12622 | 0.87449 | 0.7499 | 0.022239 | 101 | 0.44552 | 1.0297 | 0.089688 | 0.70374 | 0.79315 | 0.67333 | 0.84547 | 115.9562 | 0.63447 | 8.1066 | 6205.9708
1972 | 0.8705 | 27 | 0.56792 | 0.086147 | 0.79326 | 0.7357 | 0.13836 | 103 | 0.38767 | 1.0185 | 0.28745 | 0.78573 | 0.61982 | 0.62116 | 0.99041 | 141.517 | 0.45439 | 6.5781 | 6669.9168
1973 | 0.71024 | 26 | 0.049155 | 0.022171 | 0.5709 | 0.70736 | 0.1979 | 104 | 0.77797 | 1.1106 | 0.88289 | 1.0324 | 0.75676 | 0.66095 | 0.85688 | 117.2372 | 0.65739 | 8.3262 | 7015.6963
1974 | 0.83664 | 27 | 0.0098285 | 0.0099139 | 0.8789 | 0.75079 | 0.71563 | 108 | 0.56264 | 1.0544 | 0.62371 | 0.89949 | 0.41833 | 0.56384 | 0.90538 | 123.3611 | 0.66379 | 8.3888 | 6591.7555
1975 | 0.81725 | 27 | 0.51791 | 0.079739 | 0.33674 | 0.68207 | 0.17092 | 104 | 0.72522 | 1.0949 | 0.6556 | 0.9125 | 0.46719 | 0.57882 | 0.59269 | 94.7298 | 0.29136 | 5.4019 | 6783.981
1976 | 0.97642 | 29 | 0.28529 | 0.053571 | 0.73765 | 0.72756 | 0.20388 | 104 | 0.39567 | 1.02 | 0.97766 | 1.1268 | 0.6897 | 0.64036 | 0.1012 | 65.9064 | 0.34476 | 5.7706 | 7133.7368
1977 | 0.0086285 | 21 | 0.95618 | 0.16374 | 0.60823 | 0.71148 | 0.7555 | 109 | 0.2994 | 1.0024 | 0.33067 | 0.7992 | 0.71796 | 0.64873 | 0.93169 | 127.3655 | 0.017563 | 2.8276 | 6089.3275
1978 | 0.41574 | 25 | 0.18479 | 0.042987 | 0.17377 | 0.65895 | 0.43888 | 106 | 0.84865 | 1.1349 | 0.69943 | 0.93142 | 0.055824 | 0.39638 | 0.37719 | 81.6549 | 0.51883 | 7.091 | 6090.1418
1979 | 0.56366 | 25 | 0.74802 | 0.11305 | 0.6408 | 0.71524 | 0.77877 | 109 | 0.58944 | 1.0605 | 0.41696 | 0.82593 | 0.064797 | 0.40384 | 0.12273 | 67.5168 | 0.44338 | 6.4935 | 5876.255
1980 | 0.45817 | 25 | 0.82667 | 0.12789 | 0.79897 | 0.73659 | 0.0060001 | 101 | 0.69219 | 1.0859 | 0.48471 | 0.84833 | 0.51835 | 0.59369 | 0.49395 | 88.3935 | 0.99536 | 14.2236 | 6416.9644
1981 | 0.13225 | 23 | 0.47298 | 0.07426 | 0.40195 | 0.68966 | 0.95128 | 112 | 0.28807 | 1.0004 | 0.28393 | 0.78458 | 0.56007 | 0.60528 | 0.057745 | 62.0151 | 0.071297 | 3.6675 | 5795.0056
1982 | 0.16176 | 23 | 0.5526 | 0.084146 | 0.15561 | 0.65579 | 0.27285 | 105 | 0.1859 | 0.98066 | 0.78477 | 0.97272 | 0.7265 | 0.65135 | 0.0077181 | 54.3926 | 0.72226 | 8.9911 | 6074.1917
1983 | 0.10854 | 22 | 0.52927 | 0.081164 | 0.74901 | 0.72915 | 0.71511 | 108 | 0.088349 | 0.95561 | 0.44771 | 0.83593 | 0.60128 | 0.61631 | 0.38505 | 82.0872 | 0.54672 | 7.3236 | 5708.0609
1984 | 0.088074 | 22 | 0.25124 | 0.050124 | 0.80108 | 0.73693 | 0.64045 | 108 | 0.81126 | 1.1215 | 0.10238 | 0.71084 | 0.50002 | 0.58845 | 0.39665 | 82.7311 | 0.81473 | 10.0923 | 5752.4808
1985 | 0.59303 | 25 | 0.91387 | 0.14917 | 0.6525 | 0.71663 | 0.79113 | 109 | 0.97685 | 1.205 | 0.74185 | 0.95109 | 0.17375 | 0.47004 | 0.39297 | 82.5259 | 0.23771 | 5.0452 | 6618.5852
1986 | 0.39648 | 24 | 0.49907 | 0.077412 | 0.62893 | 0.71385 | 0.72421 | 109 | 0.64796 | 1.0745 | 0.95748 | 1.099 | 0.94075 | 0.7415 | 0.51312 | 89.5716 | 0.42851 | 6.3806 | 6931.9813
1987 | 0.78051 | 27 | 0.080511 | 0.028375 | 0.55973 | 0.70616 | 0.90078 | 111 | 0.73215 | 1.0969 | 0.50895 | 0.85671 | 0.80959 | 0.67928 | 0.8167 | 112.9227 | 0.73399 | 9.1194 | 7005.7457
1988 | 0.13022 | 23 | 0.42112 | 0.068218 | 0.34988 | 0.68365 | 0.44058 | 106 | 0.37201 | 1.0156 | 0.50983 | 0.85701 | 0.079357 | 0.41491 | 0.68124 | 101.1049 | 0.29511 | 5.4274 | 5679.2696
1989 | 0.29823 | 24 | 0.73949 | 0.1116 | 0.8124 | 0.73875 | 0.68256 | 108 | 0.25049 | 0.99363 | 0.0041701 | 0.62237 | 0.42498 | 0.56593 | 0.87416 | 119.2787 | 0.40461 | 6.2023 | 5898.4098
1990 | 0.78822 | 27 | 0.84285 | 0.13134 | 0.33181 | 0.68146 | 0.7617 | 109 | 0.74027 | 1.0992 | 0.98559 | 1.1412 | 0.66386 | 0.63303 | 0.44855 | 85.6891 | 0.50704 | 6.9947 | 7433.9034
1991 | 0.66058 | 26 | 0.83397 | 0.12942 | 0.1824 | 0.6604 | 0.73347 | 109 | 0.64006 | 1.0725 | 0.29696 | 0.78877 | 0.97337 | 0.76738 | 0.59739 | 95.0495 | 0.38915 | 6.0887 | 7048.4492
1992 | 0.082627 | 22 | 0.98517 | 0.17891 | 0.34369 | 0.68291 | 0.58445 | 107 | 0.24073 | 0.99179 | 0.55801 | 0.8743 | 0.60149 | 0.61637 | 0.63384 | 97.5961 | 0.92433 | 11.8636 | 6183.3586
1993 | 0.34525 | 24 | 0.028357 | 0.016839 | 0.19021 | 0.66168 | 0.82714 | 110 | 0.98116 | 1.2094 | 0.23951 | 0.76953 | 0.82469 | 0.68497 | 0.43933 | 85.1541 | 0.054097 | 3.4525 | 6545.6586
1994 | 0.40312 | 24 | 0.31547 | 0.056697 | 0.83228 | 0.74208 | 0.56573 | 107 | 0.13976 | 0.96994 | 0.90434 | 1.0485 | 0.18418 | 0.47506 | 0.86262 | 117.9009 | 0.39791 | 6.1529 | 6085.3302
1995 | 0.3079 | 24 | 0.37836 | 0.063438 | 0.37531 | 0.68664 | 0.90202 | 111 | 0.076499 | 0.95174 | 0.44063 | 0.8336 | 0.12255 | 0.4428 | 0.001223 | 51.7485 | 0.31049 | 5.5323 | 5496.0178
1996 | 0.29828 | 24 | 0.34017 | 0.059305 | 0.36708 | 0.68568 | 0.62344 | 107 | 0.57994 | 1.0583 | 0.22215 | 0.76327 | 0.55864 | 0.60489 | 0.36025 | 80.7317 | 0.72282 | 8.9972 | 6058.911
1997 | 0.34954 | 24 | 0.92239 | 0.15175 | 0.48224 | 0.69821 | 0.51018 | 106 | 0.40206 | 1.0213 | 0.2561 | 0.7753 | 0.78489 | 0.67043 | 0.42742 | 84.4686 | 0.071729 | 3.6726 | 6295.6728
1998 | 0.72075 | 26 | 0.41269 | 0.067263 | 0.2205 | 0.66641 | 0.6585 | 108 | 0.22981 | 0.98969 | 0.50199 | 0.85428 | 0.85093 | 0.69549 | 0.39737 | 82.7712 | 0.083554 | 3.8052 | 6551.4226
1999 | 0.18191 | 23 | 0.32683 | 0.057891 | 0.11223 | 0.64738 | 0.38839 | 105 | 0.69645 | 1.087 | 0.29052 | 0.78671 | 0.9863 | 0.78225 | 0.75024 | 106.7197 | 0.089999 | 3.8735 | 6500.9734
2000 | 0.025578 | 21 | 0.67018 | 0.10053 | 0.0010298 | 0.60454 | 0.67566 | 108 | 0.61212 | 1.0658 | 0.82117 | 0.99283 | 0.68196 | 0.63813 | 0.0060415 | 53.8864 | 0.62205 | 7.9905 | 6061.2844

## Sources
Sources
# | Used for | Reference | Link
1 | Number of ships; £2.2bn approved acquisition budget and scope; through-life support excluded; recent inflation not reflected | MoD Permanent Secretary letter to the Public Accounts Committee, 'Type 31 General Purpose Frigate Costs', 25 May 2023 | https://committees.parliament.uk/publications/40198/documents/196331/default/
2 | Type 23 average direct operating cost per ship (£11.735m, FY2013-14) and its inclusions/exclusions | MoD Navy Command FOI 2015/06440, Average annual operating costs of RN surface vessels, Aug 2015 | https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/458670/Revised_2015-06440_Average_costs_RN_Surface_vessels.pdf
3 | Type 23 crew of 185 (accommodation for up to 205) | Royal Navy, HMS St Albans ship page | https://www.royalnavy.mod.uk/organisation/units-and-squadrons/type-23/hms-st-albans
4 | GDP deflator 2013-14 = 76.189 (2023-24 = 100) | HM Treasury, GDP deflators at market prices and money GDP, June 2024 (Quarterly National Accounts) | https://www.gov.uk/government/collections/gdp-deflators-at-market-prices-and-money-gdp
5 | Type 23 upkeep spend £941.2m since 2014; HMS Iron Duke refit >£100m | Naval Technology, 'UK's Type 23 frigates rack up billion-pound upkeep bill since 2014' (citing written PQ, 17 Mar 2025) | https://www.naval-technology.com/news/uks-type-23-frigates-rack-up-billion-pound-upkeep-bill-since-2014/
6 | Type 31 crew of up to 105 | GOV.UK press release, 'New Inspiration Class Type-31 warships named' | https://www.gov.uk/government/news/new-inspiration-class-type-31-warships-named
7 | HMS Venturer crew around 115 | Royal Navy, HMS Venturer ship page | https://www.royalnavy.mod.uk/organisation/units-and-squadrons/type-31/hms-venturer
8 | £1.25bn Babcock contract, £250m average per ship, £90m Babcock loss; service entry from 2027 | Naval Technology, 'Babcock recognises £90m loss on Type 31 frigate contract', July 2024 | https://www.naval-technology.com/news/babcock-recognises-90m-loss-on-type-31-frigate-contract/
9 | US FFG-62 frigate: O&S cost by element per ship-year, acquisition cost, 25-year life, disposal cost | US DoD, FFG(62) Constellation Class Frigate Selected Acquisition Report, December 2022 | https://www.esd.whs.mil/Portals/54/Documents/FOID/Reading%20Room/Selected_Acquisition_Reports/FY_2022_SARS/FFG(62)_SAR_DEC_2022_final.pdf
10 | About 70% of ship life-cycle cost is operations and maintenance; sustainment costs underestimated | US Government Accountability Office, GAO-20-2, Navy Shipbuilding: Increasing Focus on Sustainment Early in the Acquisition Process Could Save Billions (2019) | https://www.gao.gov/products/gao-20-2
11 | Canadian Surface Combatant life-cycle cost breakdown (O&S 71.8%) | Parliamentary Budget Officer (Canada), The Life Cycle Cost of the Canadian Surface Combatants – A Fiscal Analysis, Oct 2022 | https://www.pbo-dpb.ca/en/publications/RP-2223-016-C--life-cycle-cost-canadian-surface-combatants-fiscal-analysis--cout-cycle-vie-navires-combat-surface-canadien-analyse-financiere
12 | ANZAC class frigate sustainment budget A$374m in 2018-19 for 8 ships | Australian National Audit Office, Anzac Class Frigates – Sustainment (2019) | https://anao.gov.au/work/performance-audit/anzac-class-frigates-sustainment
13 | Iver Huitfeldt class cost (US$325m per ship) and crew (165) – low confidence, uncited | Wikipedia, Iver Huitfeldt-class frigate | https://en.wikipedia.org/wiki/Iver_Huitfeldt-class_frigate
14 | Real discount rate 3.5% | HM Treasury, The Green Book: appraisal and evaluation in central government | https://www.gov.uk/government/publications/the-green-book-appraisal-and-evaluation-in-central-government